## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 87e43d99-9765-4d97-8724-3866566a6042 |  | checklist | [5 empty] | Yes | sys - Project Audit Checklist V0 | 44452d47-8de9-47d8-accf-e37f86377bcb
checkpoint-group | 7aa0c859-46ec-406b-ab9a-7394db889fb6 |  | section | Site Establishment (Start-up)
checkpoint-status | 151e5854-2852-45e1-9cae-637d18c0b0e8 |  | checkpoint | Contract with Client signed?
checkpoint-status | 6988618e-903f-4d90-b910-1248253b62ad |  | checkpoint | Subcontractor Agreements signed and on the PCF?
checkpoint-status | c57209ee-794c-4c4d-87e8-fb297911e53b |  | checkpoint | Council Informed of activity?
checkpoint-status | bd88b6ec-4714-4744-a788-2ed294085c84 |  | checkpoint | TMPs approved?
checkpoint-status | a24ce1b0-eb4c-4597-afa9-bf39f573d463 |  | checkpoint | Quality Plan completed?
checkpoint-status | 92292a21-26ad-42dd-85d1-9b8d2385b2bf |  | checkpoint | Inspection and Test Plan completed?
checkpoint-status | 4d156626-5855-4ea2-8960-10b7ab18f341 |  | checkpoint | Safety Plan completed?
checkpoint-status | 2e742ef5-5ff0-4f55-b381-1a644ff08975 |  | checkpoint | Hazard Register completed?
checkpoint-status | 863bf8ab-da1d-40da-997a-6d6a14eb9d8e |  | checkpoint | WorkSafe notified of Hazardous Work?
checkpoint-status | e524d60f-f959-43a0-a9c7-f581c3905926 |  | checkpoint | Information Sign up?
checkpoint-status | df5124c7-7b5e-4a31-9d02-7518a88f3ca7 |  | checkpoint | Dump Site located and agreement with owner signed?
checkpoint-status | db5d8456-486d-4658-a378-c4bcba19e1c5 |  | checkpoint | Construction Drawings on Site?
checkpoint-status | c64f0034-8b95-4b44-bb48-0f664b83c723 |  | checkpoint | Public Notifications done?
checkpoint-status | 6ade308d-362e-44a3-b01e-1e402aff6339 |  | checkpoint | Site Folder established and on Site?
checkpoint-group | cc36a50c-9f83-4fc7-b71c-85fe0491b39b |  | section | Health and Safety Implementation
checkpoint-status | 40e5d520-e0c9-4096-b75a-b560ef33dc1f |  | checkpoint | Is the Site Specific Safety Plan available and on site?
checkpoint-status | 7f75dca7-2b16-4ffb-9225-72330b68c6b9 |  | checkpoint | Is the hazard register on site?
checkpoint-status | 735a775a-535f-4df1-83cb-8bfc4628b95c |  | checkpoint | Are Daily Safety Plan forms available?
checkpoint-status | 3abdf278-95a5-4faf-9473-2635bcc69b8f |  | checkpoint | Are there emergency procedures in place?
checkpoint-status | aaeb5fa1-f8e2-4a66-b2f5-066367f1320c |  | checkpoint | Is there a hazard register board displayed?
checkpoint-status | c4c9dc3a-bdae-4ac6-9169-0a993946984c |  | checkpoint | Is it up to date and reviewed?
checkpoint-status | e258883c-992f-4f3f-884c-7840f39fb393 |  | checkpoint | Is there a qualified first aider available?
checkpoint-status | 8ed4f310-3e25-46ae-9a27-25f149079bd6 |  | checkpoint | Has a drill been carried out?
checkpoint-status | f94c8d49-a9aa-45b5-b373-dc99d0e5e01b |  | checkpoint | Are there toilet facilities available?
checkpoint-status | 1895d40c-9e1f-4e65-a360-883489d445db |  | checkpoint | Is there means to clean hands and dirt from body?
checkpoint-status | 21637e1d-c544-48a1-9f7e-6e34e0bd62ef |  | checkpoint | Is there a smoko room or similar area?
checkpoint-status | f9d04fd8-6766-421e-8ad2-a5de2a2def2d |  | checkpoint | For those working with sewer works have they been immunised?
checkpoint-status | cba73a47-e95e-4d2e-aea5-299d9aefd1d5 |  | checkpoint | SDS file in place matching substances on site?
checkpoint-group | 2074de40-793b-463b-9d4c-2bb0a7749e4e |  | section | PPE
checkpoint-status | fd84c86a-033e-4bd3-8162-987c3d3eea53 |  | checkpoint | Are all staff wearing correct PPE?
checkpoint-status | 0f22ea17-a67f-4d7f-af58-ea68dbe02672 |  | checkpoint | Is it tidy and in good repair?
checkpoint-status | 7cf109b2-df6d-42c2-be3c-f1a4ed422c24 |  | checkpoint | Are staff wearing seatbelts on trucks, rollers and loaders?
checkpoint-status | d67e915c-5266-4e59-b59b-77b5b2f51e81 |  | checkpoint | Are staff wearing hardhats where there are overhead hazards?
checkpoint-group | fb2442f0-56bf-44d1-b5f9-02001911e24e |  | section | Staff Involvement in Safety
checkpoint-status | b8636eb3-9ba7-411a-8077-4b48d772718f |  | checkpoint | Are there completed daily safety plans present?
checkpoint-status | 4c7e1c20-4e05-42cc-9a4a-e674562d0fd4 |  | checkpoint | Are there completed plans for the last few working days? Pick 3
checkpoint-status | 575c9984-9073-41f9-8b0d-2ace85629b57 |  | checkpoint | Is there a record of staff induction? Pick 3 staff – are they inducted?
checkpoint-status | d14506db-1c65-4247-b2b4-865525d5b7ed |  | checkpoint | Have they signed the Daily Safety Plan for the day?
checkpoint-status | ff559225-9e19-49c4-9a0e-3ce7f0711947 |  | checkpoint | Covid 19
checkpoint-status | 5e8d0625-14bc-4ac1-a9e4-dddd57a0e0a8 |  | checkpoint | Is there a site sign in register?
checkpoint-status | 37cc7bc2-bb09-411b-b0d5-b55e5f230c0f |  | checkpoint | Do staff have contact diaries?
checkpoint-status | b51ba2c7-730c-4d0b-81cb-c825e081f299 |  | checkpoint | Staff observing distance rules? Incl site and transport
checkpoint-status | 66c28df5-a85b-47ef-ad5c-3d50f535029c |  | checkpoint | Staff working in assigned bubbles?
checkpoint-status | 112ad1c3-5d09-4e3e-a331-b486b50a4968 |  | checkpoint | Site and facilities being cleaned?
checkpoint-group | 15d2d20f-8bec-4b76-8f4b-1c7c46d624c2 |  | section | Equipment
checkpoint-status | 86628d81-605c-4efa-9498-3284354512f7 |  | checkpoint | Are chains tagged and in test?
checkpoint-status | 9c534ae8-f0ff-432f-aa79-e363d82624ae |  | checkpoint | Is electrical equipment tagged and in test?
checkpoint-status | 582b5b68-d962-4fe4-b05f-69b57a910e52 |  | checkpoint | Is there a first aid kit on site and is it complete?
checkpoint-status | 1324e539-c537-403b-affe-72adcd2eab72 |  | checkpoint | Is there a fire extinguisher on site and is it charged and in test date?
checkpoint-status | 787ba438-c7e0-4024-bc3f-2bfe041f9673 |  | checkpoint | Are diesel containers tagged?
checkpoint-group | ed197e9b-2243-4b04-b7a1-0fc728086727 |  | section | Mobile Equipment
checkpoint-status | 8649d50b-9d08-485f-87aa-f6703333e377 |  | checkpoint | Are maintenance books present on applicable equipment?
checkpoint-status | 57b450f5-76a0-45e4-b5b0-a0216170fe8a |  | checkpoint | Are maintenance sheets up to date?
checkpoint-status | bf58d68a-3cbb-4a62-99f0-bc5480510d45 |  | checkpoint | Are defects being reported?
checkpoint-group | 6c31d002-b814-4574-8b02-d9a67274175c |  | section | Calibration
checkpoint-status | 126fc6ec-86bd-45e9-8dc0-a90e33e2838b |  | checkpoint | Is critical measuring equipment calibrated?
checkpoint-status | e10c1109-f440-4300-8878-5402ba627f57 |  | checkpoint | Is it named with United Civil Id?
checkpoint-status | 691e4e12-9858-4339-aad3-da91e007185a |  | checkpoint | Is there a calibration tag and is it in date?
checkpoint-status | 11b91f44-3a92-40e6-92d0-6279c35a88c1 |  | checkpoint | Is it on the Vault?
checkpoint-group | a65d4676-4838-4f2e-a38a-c6608a80b771 |  | section | Subcontractors
checkpoint-status | f42026e1-2496-4f1f-bfbd-34cdc762a563 |  | checkpoint | Are high risk subcontractors (QHS or E) on the Approved Suppliers List?
checkpoint-status | a8057e4c-8703-4f09-8d7d-db2a9f7a4994 |  | checkpoint | Are they wearing correct PPE?
checkpoint-status | 6ab4af3f-10f3-446a-ae6e-8e843d386f8c |  | checkpoint | Are subcontractor employees inducted?
checkpoint-group | f3855699-632d-4851-9e46-cd2f5360e709 |  | section | Purchasing
checkpoint-status | b6a9e0fe-72cc-474b-8362-73d09a701ba0 |  | checkpoint | Do Purchase orders specify specifically what is being ordered?
checkpoint-status | 339031ae-710d-457f-8e21-a1c6b74a83da |  | checkpoint | Is the purchase amount within the DOA policy?
checkpoint-status | 3e8983ea-ddf6-4aab-a110-d4483121229a |  | checkpoint | Is person signing PO authorised?
checkpoint-group | ffaba44e-2b68-4e07-baa5-0994b8b644d0 |  | section | Training
checkpoint-status | 79257e48-c587-4cda-9223-7221affa2bae |  | checkpoint | Are staff licenced for the machinery they are operating?
checkpoint-status | 0a4a423c-8f86-4b1a-8c2f-e6b0a74cf8a5 |  | checkpoint | Do staff have competency records for the equipment they are using?
checkpoint-status | 497e3158-cd1f-4b94-8733-00d49f8b1299 |  | checkpoint | Training plan developed, including orientation plan for new team members?
checkpoint-status | 98aebc05-91a1-4681-a5b6-1f7fce6d8ad2 |  | checkpoint | Have all required training requirements been met by the project team, i.e., Health, Safety & Environment, etc.?
checkpoint-group | c831af9f-0650-4df6-88c7-24d1b5d0fa6b |  | section | Excavations
checkpoint-status | bf309d99-1288-4512-897f-18a611d98b1d |  | checkpoint | Are excavations 1.5m deep or greater battered, benched or shielded?
checkpoint-status | 649ed389-cec0-49eb-9ba8-ef1e16ab2088 |  | checkpoint | Is approved Code of Practice in place for excavation & trenches?
checkpoint-status | 4038e388-c255-48fd-b4e0-f39ceefb4952 |  | checkpoint | Are excavations protected for after hours?
checkpoint-group | 24b42427-9308-4003-93e5-5f083ffad387 |  | section | Heights and Overhead
checkpoint-status | 877513c9-1196-40c0-bf8e-98d289ab31a7 |  | checkpoint | Are edges protected?
checkpoint-status | e00a21ea-7f54-4d72-8776-e7eada85f255 |  | checkpoint | If working with 4m of power line proximity permits in place?
checkpoint-group | d8436b4d-152a-40d8-ac68-a1babace3200 |  | section | Vehicles
checkpoint-status | 97862ec1-c42f-4fb7-bc6d-1a09f1ea7c8f |  | checkpoint | Are vehicles being driven on the road licensed?
checkpoint-status | ff6da0bc-6911-4405-ab95-9b66ffd659f2 |  | checkpoint | Do they have WOF/COF if applicable?
checkpoint-status | 77b687cb-d7f3-4f34-82bf-8ddd02ef892c |  | checkpoint | Housekeeping – vehicles tidy?
checkpoint-status | fcdb20a7-9008-44d4-84b3-f4fc3a700323 |  | checkpoint | Do the Utes/lights truck have diesel spill emergency response card?
checkpoint-status | 95fd68bc-4c71-4ea6-8e66-8ef86804d5a0 |  | checkpoint | Do the Utes/light trucks have a complete first aid kit?
checkpoint-group | b5d65d7c-6d67-42fa-b84e-3e34a0e04ce9 |  | section | Fences
checkpoint-status | f14233d6-b332-486d-adbd-04dacf98d2d0 |  | checkpoint | Are fences compliant?
checkpoint-status | dffb2a2f-ed61-4722-bbbf-d317617e73f4 |  | checkpoint | Are they in good repair?
checkpoint-status | fd22cdb5-47a8-45c6-8630-16e371b40e35 |  | checkpoint | Are they stable and safe?
checkpoint-status | 4f0e5f36-1682-4486-8d25-ece1f3b407de |  | checkpoint | Would they prevent entry by a child?
checkpoint-group | 5a63ce48-659b-4979-8bb3-79db67afcc16 |  | section | Confined Space
checkpoint-status | fffe8678-37ba-4781-9b0a-37067e564455 |  | checkpoint | Are forms available for CSE?
checkpoint-status | b06ff0aa-66ad-46ae-a378-323cea16ce2f |  | checkpoint | Are there trained CSE people on site?
checkpoint-status | 48dd400e-6d95-49dd-affc-4065929d1abd |  | checkpoint | Are the forms filled out correctly?
checkpoint-group | 4fa4216e-3c92-465c-ad92-49ab39ac6ff2 |  | section | Environmental
checkpoint-status | a29d24bc-a23a-4127-8c4c-3c8925223d8d |  | checkpoint | Is the Environmental Management Plan on site?
checkpoint-status | 2d703dcd-9c6d-49b6-b19a-cb3952379870 |  | checkpoint | Erosion and Sediment Control Plan in place?
checkpoint-status | e6fe50b1-f1b3-4ecf-9526-2af85d464e4a |  | checkpoint | Are applicable Resources Consents present?
checkpoint-status | e099266c-5472-4d8c-8022-42a9df2d74e8 |  | checkpoint | Are consents complete with applicable drawings?
checkpoint-status | 1c951f53-7d6d-439f-8d6d-e8c5e91016a2 |  | checkpoint | Are environmental issue addressed in the Daily Safety Plan?
checkpoint-status | d2991e86-8c70-488a-939a-76ec389c8836 |  | checkpoint | Is a Spill Kit available and complete?
checkpoint-status | d3522e50-4fbd-4442-8d14-62f16286464c |  | checkpoint | Has monitoring been or planned to be carried out for the day?
checkpoint-status | 59f16bd0-55a7-4053-9217-72be67981762 |  | checkpoint | Is there someone who is TP90/GD05 trained on site?
checkpoint-status | 68c61dc6-10b0-4830-b19d-da7d96aeaf8e |  | checkpoint | (Erosion & sediment control - ARC)
checkpoint-status | afd35622-436f-431f-9364-cd5e7e7a2393 |  | checkpoint | Compliant controls in place?
checkpoint-group | 101ed1a3-0bdf-4f12-832e-dc7fbf5b357b |  | section | Quality
checkpoint-status | edd10517-b137-43e6-bea2-4c9987b50ffd |  | checkpoint | Is the Contract Quality Plan on site?
checkpoint-status | f0773f11-afa1-4aca-9c46-2d83c53fb9ad |  | checkpoint | Are relevant Inspection sheets available as required by the ITP?
checkpoint-status | 2bd6f961-5be1-4ec6-abe5-2cb225fcc5b3 |  | checkpoint | Have the relevant inspection sheets been completed to applicable stage in the contract?
checkpoint-status | d46ed425-2d04-43a5-9eb8-bd98d2f74b95 |  | checkpoint | Are Hold Points being signed off by the Engineer?
checkpoint-status | 0665f54c-de46-4ecf-a769-40afbe791504 |  | checkpoint | Are the correct status drawings on site?
checkpoint-status | 7fde6af9-0781-4733-8e6f-3810aae1e152 |  | checkpoint | Are Daily Work Reports being carried out?
checkpoint-status | 6a2620f8-8111-4c7f-b137-8189ab16ea4d |  | checkpoint | Is there an As Built file present that is up to date?
checkpoint-group | 90331bf5-e648-4421-bd8d-bc4245c21788 |  | section | Project Central File (PCF)
checkpoint-status | 5e43bc93-45be-4ce2-bd2d-c0ee1ea610c5 |  | checkpoint | Are documents uniquely identified and version controlled
checkpoint-status | d4c4d48b-fc65-4ab2-8f27-e3b71f63856e |  | checkpoint | Are documents being stored only on backed-up network drives?
checkpoint-status | 09eefc2a-8d0f-4afd-99ce-ff11b3d430d3 |  | checkpoint | Is the electronic PCF the main file?
checkpoint-status | 9180477c-7876-4dc3-9151-725059fcff59 |  | checkpoint | Are all project specific email files stored on Union Square?
checkpoint-status | 4b43a1cd-affa-494a-b947-1c596e536708 |  | checkpoint | Are both physical and electronic document files archived?
checkpoint-group | 01a84aeb-413d-402c-972c-bda3dea7eaeb |  | section | Changes to the Contract
checkpoint-status | 63fbeb61-e169-4ac8-bf80-d343a4171242 |  | checkpoint | Are variations documented and is there as file?
checkpoint-status | 22654ceb-0318-4872-9833-634489000f0a |  | checkpoint | Has the CQP been duly updated to reflect any contract modification(s)?
checkpoint-group | 2ec686c4-671a-4879-abb1-9e36514305f0 |  | section | Concerns, Corrective and Preventive Action
checkpoint-status | bcd5cb19-3516-4b07-a00c-0107d5846362 |  | checkpoint | Is there a concerns register be operated?
checkpoint-status | 3631a3cb-ad13-4116-be33-9cc6ec6501ff |  | checkpoint | Is there a corrective action file and is being?
checkpoint-status | 88942dea-579f-4a09-8a7d-bd6868f1b0f3 |  | checkpoint | Do Corrective Actions identify a root cause?
checkpoint-status | a481b7bf-6ce5-45bf-b5d3-07640622a61b |  | checkpoint | Are Corrective Actions verified to ensure they are effective?
checkpoint-status | e1c4c2a2-fcd3-4b75-a8df-1ffcae07f1ec |  | checkpoint | Is Customer Feedback being recorded?
checkpoint-group | 2d907550-6903-40f5-8cf0-d3ff16a40ada |  | section | Traffic
checkpoint-status | 719e0ed4-e1e4-4143-8b31-aaca18e594df |  | checkpoint | Is the Traffic Management Plan on site?
checkpoint-status | 125a40d6-4778-4b26-b93e-a5c389a4b896 |  | checkpoint | Is the STMS on Site or back up STMS/TC?
checkpoint-status | 9c32375c-87d2-4b85-8f23-e733b106a5df |  | checkpoint | Condition of signs OK?
checkpoint-status | ece4a3cb-6d75-4d1c-9196-e5a795d29cba |  | checkpoint | Set out to plan or modified correctly?
checkpoint-status | 63726f2f-f2b2-40a2-a2cf-2dd7298415b3 |  | checkpoint | Has the set up been monitored as per COPTTM requirements?
checkpoint-group | ae0019a6-6c09-48f3-a3ca-a66d373e09ad |  | section | Recommendations/Observations/NCRs
checkpoint-status | ae45b0ea-a6a7-4516-8d67-8875be306385 |  | checkpoint | Recommendations as per comments
checkpoint-status | 624c679e-ac04-4003-a8b5-ba3182aaa6ec |  | checkpoint | Observations as per comments
checkpoint-status | e6542959-dbf4-4870-9183-89828146f94d |  | checkpoint | NCRs
label | 0cd23a87-5a05-4aae-b584-b3eede19be38 |  | note | NCR number and description
checkpoint-group | 3160291e-5cd8-4954-a89a-ef0590edf8f4 |  | section | Sign off
checkpoint-status | 5fee0c25-0b8b-477e-a434-04c88145dd07 |  | checkpoint | Name and signature of the author
text | 3c5b5fe3-7092-4088-8cab-b0e8060ad566 |  | textbox | Name
text | 6f51a25d-d128-4e61-8ba5-a106c40891ce |  | textbox | Date
holdpoint | 45aea38a-996d-4632-9eaf-9c5cbd6e559c |  | signoff | Signature
checklist-sectioned | 8f5c35b4-23b0-4407-af19-c503bd413c5e |  | checklist | Project Audit |  |  |  |  | Yes | sys - Project Audit Checklist V1 | 518f6bcc-d522-4ace-b291-10071ba36ef8
checkpoint-group | 67fb6e11-129b-437e-a48e-a02a925fc5eb |  | section | Site Establishment (Start-up)
checkpoint-status | a319e313-15f3-4b8a-8dfd-a54a3f622b06 |  | checkpoint | Contract with Client signed?
checkpoint-status | b8552686-13b0-4a53-97ce-de5ba71d15e0 |  | checkpoint | Subcontractor Agreements signed and on the PCF?
checkpoint-status | f14571e6-ab5d-4f12-877e-bc921cea13b6 |  | checkpoint | Council Informed of activity?
checkpoint-status | 5f93ef0c-aad5-4476-a712-60976e43c21a |  | checkpoint | TMPs approved?
checkpoint-status | efef35c5-d1e4-473f-a8d5-abc266daef4d |  | checkpoint | Quality Plan completed?
checkpoint-status | 7a72556f-78c9-4f11-98a8-9081029f1e43 |  | checkpoint | Inspection and Test Plan completed?
checkpoint-status | ae78b035-d728-48f0-8e20-92f76c94ca97 |  | checkpoint | Safety Plan completed?
checkpoint-status | dd399639-ca34-4b8b-8a73-1a72362c22b8 |  | checkpoint | Hazard Register completed?
checkpoint-status | e0d1a91f-336e-414a-bad0-5a4e60cbe592 |  | checkpoint | WorkSafe notified of Hazardous Work?
checkpoint-status | 4f394c09-8cd6-494b-98ed-d7a4a4d9fbbc |  | checkpoint | Information Sign up?
checkpoint-status | 8475bcbe-bcb4-4c7d-9994-3254050994a9 |  | checkpoint | Dump Site located and agreement with owner signed?
checkpoint-status | 05644320-5685-4f6b-87e4-1e6f30ac257a |  | checkpoint | Construction Drawings on Site?
checkpoint-status | 205ad536-12ed-4502-afbb-32d07cec00a1 |  | checkpoint | Public Notifications done?
checkpoint-status | a061ca15-359d-4ac3-b947-133047c28995 |  | checkpoint | Site Folder established and on Site?
checkpoint-group | f25642ff-1f57-4583-a642-53165f2eb50c |  | section | Health and Safety Implementation
checkpoint-status | c700c0ea-4588-46d5-b983-3910be6b329e |  | checkpoint | Is the Site Specific Safety Plan available and on site?
checkpoint-status | cdf20aad-4005-40ab-ae2a-c05511164aef |  | checkpoint | Is the hazard register on site?
checkpoint-status | 2c6eddcf-13b0-43bc-bb56-3dd971e8fe65 |  | checkpoint | Are Daily Safety Plan forms available?
checkpoint-status | 2f2f10db-9b09-41e1-9d09-441b3149cb4a |  | checkpoint | Are there emergency procedures in place?
checkpoint-status | 81f47f4e-f270-41ed-8a6f-dcf894d83bac |  | checkpoint | Is there a hazard register board displayed?
checkpoint-status | ac7b01a4-79c4-4bcc-bd3f-73793ef31232 |  | checkpoint | Is it up to date and reviewed?
checkpoint-status | 237f43ca-002b-46cc-8ffc-68d36e336fff |  | checkpoint | Is there a qualified first aider available?
checkpoint-status | d18c89c6-0475-404f-84d6-29c52a880da1 |  | checkpoint | Has a drill been carried out?
checkpoint-status | ac5cc763-9292-45fd-9907-c84ec784e69f |  | checkpoint | Are there toilet facilities available?
checkpoint-status | 81e714b2-dde2-4e76-8e13-92a3e14f777d |  | checkpoint | Is there means to clean hands and dirt from body?
checkpoint-status | e8052483-56e0-4311-ad12-bac92ad351a5 |  | checkpoint | Is there a smoko room or similar area?
checkpoint-status | cb770a04-8122-4154-ac6a-4f983e658978 |  | checkpoint | For those working with sewer works have they been immunised?
checkpoint-status | 6ba39243-6675-4973-a13e-0289c8b0dd80 |  | checkpoint | SDS file in place matching substances on site?
checkpoint-group | 24eab6d9-00eb-4153-b16c-36cd64c95ebb |  | section | PPE
checkpoint-status | bcd3296a-767d-43e4-93a7-d82ee79dd7a3 |  | checkpoint | Are all staff wearing correct PPE?
checkpoint-status | 39866eb3-fbfd-40b5-8e5d-d8ad4b131157 |  | checkpoint | Is it tidy and in good repair?
checkpoint-status | b514036e-2f79-4f2f-8848-aff9aa112214 |  | checkpoint | Are staff wearing seatbelts on trucks, rollers and loaders?
checkpoint-status | d6dcc8e4-f377-4763-ae92-bd47bfe8622b |  | checkpoint | Are staff wearing hardhats where there are overhead hazards?
checkpoint-group | 30c0a031-939c-4133-8d8b-85784a839ca6 |  | section | Staff Involvement in Safety
checkpoint-status | df54f3e6-b11d-46ab-a883-cbb2c90311a2 |  | checkpoint | Are there completed daily safety plans present?
checkpoint-status | aa1d3490-e28b-4ff2-ae07-c0ef71fa499a |  | checkpoint | Are there completed plans for the last few working days? Pick 3
checkpoint-status | 0b30befc-4686-4180-8d66-c07eb11129d1 |  | checkpoint | Is there a record of staff induction? Pick 3 staff – are they inducted?
checkpoint-status | 2cd43aa0-8d35-4ebc-bab0-9baab383f0e0 |  | checkpoint | Have they signed the Daily Safety Plan for the day?
checkpoint-status | 127df433-45e5-40be-a33f-8b7de62bbfc1 |  | checkpoint | Is there a site Covid 19 sign in register?
checkpoint-status | 403b9ee9-ac1b-4fb9-9e35-99f12d24246f |  | checkpoint | Do staff have Covid19 site diaries?
checkpoint-status | 013a3435-7ed5-4947-bffa-48920753249d |  | checkpoint | Site and facilities being cleaned?
checkpoint-group | 0e181ed7-3304-4d8d-8921-21fbe1a9ac89 |  | section | Equipment
checkpoint-status | c12c5a73-5d81-4c11-b888-d428bc01a6c8 |  | checkpoint | Are chains and other relevant equipment tested and tagged?
checkpoint-status | fed94e67-3ad9-4fa1-8ead-6b41188685e1 |  | checkpoint | Is electrical equipment tagged and in test?
checkpoint-status | 27a84fe8-db4c-4156-a967-3b92649242ce |  | checkpoint | Is there a first aid kit on site and is it complete?
checkpoint-status | 66be10e6-49d2-4e7c-8103-c47cdf0c5c6a |  | checkpoint | Is there a fire extinguisher on site and is it charged and in test date?
checkpoint-status | 9247ac72-5dd2-4af1-a50e-75572462e787 |  | checkpoint | Are diesel and petrol containers tagged?
checkpoint-group | c40a7b30-cd58-4f70-8710-7a008a2de59a |  | section | Mobile Equipment
checkpoint-status | 34e2ada3-8c31-48b3-bf9d-72c2ff204e75 |  | checkpoint | Are maintenance books present on applicable equipment?
checkpoint-status | 1223667a-dead-46b0-b812-e33c8661360a |  | checkpoint | Are maintenance sheets up to date?
checkpoint-status | c0ac8437-105a-473a-9cb5-18ca6d277b96 |  | checkpoint | Are defects being reported?
checkpoint-group | 2277f4f1-0036-4250-89eb-829b2119e277 |  | section | Calibration
checkpoint-status | 157bef85-7917-4f34-8400-14f9a827e83f |  | checkpoint | Is critical measuring equipment calibrated?
checkpoint-status | 4362384f-2acc-46de-a79e-7fe08407121a |  | checkpoint | Is it named with United Civil Id?
checkpoint-status | 7f1226fc-0b88-4ef9-b20f-5ea6e307a6be |  | checkpoint | Is there a calibration tag and is it in date?
checkpoint-status | e059428a-8d20-48a3-95b6-31925e661f1e |  | checkpoint | Is it on the Certification and Calibration Plant Register?
checkpoint-group | 9039b733-4b3d-4f0e-9ed3-b2cc25b3740c |  | section | Subcontractors
checkpoint-status | c0fc8329-7713-455d-8434-949dbe8dff3a |  | checkpoint | Are high risk subcontractors (QHS or E) on the Approved Suppliers List?
checkpoint-status | 2200e659-9a70-499e-8b67-8362c5d1382a |  | checkpoint | Have they provided the required Site documentation i.e. JSA, Task Analysis, etc?
checkpoint-status | 4ee6f8f6-1402-434e-ba3b-afe7640440ec |  | checkpoint | Are they wearing correct PPE?
checkpoint-status | 3bba462f-9396-4c5b-90b5-630952f3b7e1 |  | checkpoint | Are subcontractor employees inducted?
checkpoint-group | 5515cbef-2cdd-4aba-8cac-f99c63eb2da3 |  | section | Purchasing
checkpoint-status | 94c651b9-3b33-428f-a7ae-0cb1a464c73d |  | checkpoint | Do Purchase orders specify specifically what is being ordered?
checkpoint-status | 28ff5a54-09f1-4fa4-8f55-24709b7374fa |  | checkpoint | Is the purchase amount within the DOA policy?
checkpoint-status | 542011b5-50b9-457b-b9f9-086d9e947f89 |  | checkpoint | Is person signing PO authorised?
checkpoint-group | 268d61ed-55f5-4b4e-b283-66c6b33d6333 |  | section | Training
checkpoint-status | b64dae10-548f-4d4a-a79f-12c1af5c79be |  | checkpoint | Are staff licenced for the machinery they are operating?
checkpoint-status | f067c6bb-b7a3-45ed-b90a-7abb2f7e78c5 |  | checkpoint | Do staff have competency records for the equipment they are using?
checkpoint-status | 46e3b6c7-22af-40fa-a18f-e33fedaddee4 |  | checkpoint | Training plan developed, including orientation plan for new team members?
checkpoint-status | e5b491c3-60e4-4767-8a03-cf2e574c1364 |  | checkpoint | Have all required training requirements been met by the project team, i.e., Health, Safety & Environment, etc.?
checkpoint-group | 29277584-4449-475d-a9bf-c78a53667cb8 |  | section | Excavations
checkpoint-status | c7b6df67-0c7d-40e2-85c1-d358ec9bb262 |  | checkpoint | Are excavations 1.5m deep or greater battered, benched or shielded?
checkpoint-status | c508c334-488c-4e31-bc11-f0476d46500b |  | checkpoint | Is approved Code of Practice in place for excavation & trenches?
checkpoint-status | c7f09efe-78cc-435b-ac27-d59fa2bdb764 |  | checkpoint | Are excavations protected for after hours?
checkpoint-group | 6337086c-092b-48a9-a14b-090b67c7938d |  | section | Heights and Overhead
checkpoint-status | 647286de-d4ab-4bd5-a4b0-9eaaa51fb486 |  | checkpoint | Are edges protected?
checkpoint-status | ef44fe28-1d33-4b16-8a4e-9191a31a0ab5 |  | checkpoint | If working with 4m of power line proximity permits in place?
checkpoint-group | ce94275a-ca19-44a7-8bb4-cb6a08de294f |  | section | Vehicles
checkpoint-status | ab51a4eb-ddbf-4b1f-b34e-219274d7e356 |  | checkpoint | Are vehicles being driven on the road licensed?
checkpoint-status | 42e7e738-4057-4e49-886c-db628433b911 |  | checkpoint | Do they have WOF/COF if applicable?
checkpoint-status | 9b979d22-d244-4f8f-9932-686374a86a4f |  | checkpoint | Housekeeping – vehicles tidy?
checkpoint-status | 9d36bed3-231d-493f-a3d9-815e9e92073c |  | checkpoint | Do the Utes/lights truck have diesel spill emergency response card?
checkpoint-status | 83b64486-e62b-4376-bad1-f6823479fc62 |  | checkpoint | Do the Utes/light trucks have a complete first aid kit?
checkpoint-group | 17aeae0e-86e9-4091-895c-4ffe0feb0465 |  | section | Fences
checkpoint-status | 7f89f3c5-e692-4332-8332-21cebb75bca2 |  | checkpoint | Are fences compliant?
checkpoint-status | 1a2b7a20-ef0d-4a51-b1f9-530ed865b4b2 |  | checkpoint | Are they in good repair?
checkpoint-status | 7d0268f3-d4ef-4421-bd9d-545a5fc32faf |  | checkpoint | Are they stable and safe?
checkpoint-status | 9acef8e2-42d6-46a3-aaf9-19141b15e914 |  | checkpoint | Would they prevent entry by a child?
checkpoint-group | 0be86137-c42e-40e7-9bb7-9947fe7f57e8 |  | section | Confined Space
checkpoint-status | ff2e27d5-de6f-4085-823d-f24f728d3b07 |  | checkpoint | Are forms available for CSE?
checkpoint-status | 6843dee7-4184-4045-88fe-159b1122a820 |  | checkpoint | Are there trained CSE people on site?
checkpoint-status | fa5da4ef-e8f4-47a2-8e53-d5d4f72fb51b |  | checkpoint | Are the forms filled out correctly?
checkpoint-group | 48b707d2-b60b-4187-9723-b33cafea2c8d |  | section | Environmental
checkpoint-status | 934a384a-4f59-4dd9-a6b6-c58415646500 |  | checkpoint | Is the Environmental Management Plan on site?
checkpoint-status | c9c4a123-d630-46e4-9a24-2082b89076f8 |  | checkpoint | Erosion and Sediment Control Plan in place?
checkpoint-status | fb9c8ca0-c6c2-4f68-a0d0-6cc8f27a304b |  | checkpoint | Are applicable Resources Consents present?
checkpoint-status | 39077e08-b02f-42d5-8181-737028c141c3 |  | checkpoint | Are consents complete with applicable drawings?
checkpoint-status | bc00a953-d4cd-40c5-b5ce-51713773fab1 |  | checkpoint | Are environmental issue addressed in the Daily Safety Plan?
checkpoint-status | e3cd01ce-16e4-4d74-b685-9fca6157b71d |  | checkpoint | Is a Spill Kit available and complete?
checkpoint-status | 9e830646-4184-4fa2-95f9-4b3ead4e272a |  | checkpoint | Has monitoring been or planned to be carried out for the day?
checkpoint-status | 4414eff5-a6bc-4180-8697-30a085d2e5ed |  | checkpoint | Is there someone who is TP90/GD05 trained on site?
checkpoint-status | 9310ddb5-e470-4f0c-ac05-e16fbb2c3acc |  | checkpoint | (Erosion & sediment control - ARC)
checkpoint-status | 29f9abc2-3465-44f3-9d9f-50122e158174 |  | checkpoint | Compliant controls in place?
checkpoint-group | 9762638e-b6d1-413b-80bf-618dd5f12e4f |  | section | Quality
checkpoint-status | ce003ac4-78ff-4a78-bf61-312437627614 |  | checkpoint | Is the Contract Quality Plan on site?
checkpoint-status | 536a8d15-a28a-4138-9ea2-0301ffdd78a7 |  | checkpoint | Are relevant Inspection sheets available as required by the ITP?
checkpoint-status | 6a181a99-b52d-4bdf-bfcf-bbf6a0d1dd41 |  | checkpoint | Have the relevant inspection sheets been completed to applicable stage in the contract?
checkpoint-status | 3f95241a-b094-434e-aab1-50eb8831ccd4 |  | checkpoint | Are Hold Points being signed off by the Engineer?
checkpoint-status | 7d5501f4-9a3c-4c09-82a4-0e6c9bb8d692 |  | checkpoint | Are the correct status drawings on site?
checkpoint-status | 95d9648a-04ac-43e2-a122-f730fa3f1c98 |  | checkpoint | Are Daily Work Reports being carried out?
checkpoint-status | 99e3efe6-6d53-4816-b7a9-e0cb01e720e1 |  | checkpoint | Is there an As Built file present that is up to date?
checkpoint-group | 6588a699-5e1d-4c05-b61e-89263a205db5 |  | section | Project Central File (PCF)
checkpoint-status | c729105a-a4ce-4a46-99a4-efd2bc4bfa1d |  | checkpoint | Are documents uniquely identified and version controlled
checkpoint-status | ff64b3b6-dd0c-4478-8529-ee2545d82ff7 |  | checkpoint | Are documents being stored only on backed-up network drives?
checkpoint-status | aaede2b4-8b6f-4011-9744-9204d26a3758 |  | checkpoint | Is the electronic PCF the main file?
checkpoint-status | c06631d3-f8ac-456c-b885-30d9e68c2db3 |  | checkpoint | Are all project specific email files stored on Union Square?
checkpoint-status | fbdb1624-1fc7-4ba4-88db-f9fa2a53ebd3 |  | checkpoint | Are both physical and electronic document files archived?
checkpoint-group | 345738da-c4b9-4c2a-90ba-7031d17f457d |  | section | Project Management
checkpoint-status | 591310a7-7ea8-4407-9c76-12c150f3cde9 |  | checkpoint | Are variations documented and is there as file?
checkpoint-status | 7aeda9c3-bd88-4458-b523-2c3ba977158c |  | checkpoint | Has the CQP been duly updated to reflect any contract modification(s)?
checkpoint-status | 140e2ee9-e18e-422c-bef7-443db641ba75 |  | checkpoint | Are payment claims on file and upto date?
checkpoint-status | c2947e07-d3c2-49b2-8988-a04f644b8ce0 |  | checkpoint | Are subcontractor progress claims on file and upto date?
checkpoint-status | cbb2764a-9ef8-48cc-84f8-99b5d6538986 |  | checkpoint | Are payment schedules on file and upto date?
checkpoint-status | 5b0c1abc-9e5e-49cd-92b0-9bc56c7627d6 |  | checkpoint | Are Site meeting minutes kept upto date?
checkpoint-status | fb3a2b69-ef09-4fcd-9308-64aaab52ba22 |  | checkpoint | Are subcontractor payment schedules ok file and kept upto date?
checkpoint-status | 981a8590-5e2e-438f-bf22-fc897eddac2e |  | checkpoint | Is the financial forecasting in place and upto date?
checkpoint-group | 0f91892e-68ec-48a3-ae8c-e2ff76bc1aa1 |  | section | Concerns, Corrective and Preventive Action
checkpoint-status | aad552f2-6fc9-4a04-8bb6-a0ddc5b4f5b5 |  | checkpoint | Is there a concerns register be operated?
checkpoint-status | 5016a939-4dec-4837-bea7-71d4200689eb |  | checkpoint | Is there a corrective action file and is being?
checkpoint-status | f671453c-7ebf-44cf-ac46-bcf9d8c0147b |  | checkpoint | Do Corrective Actions identify a root cause?
checkpoint-status | 508ce249-3ab9-4a83-9617-00809820d204 |  | checkpoint | Are Corrective Actions verified to ensure they are effective?
checkpoint-status | 31f4ae64-d164-4a76-9415-fc93f6adcb16 |  | checkpoint | Is Customer Feedback being recorded?
checkpoint-group | f4de259c-896d-438b-8a81-a6251a51f309 |  | section | Traffic
checkpoint-status | b1ae0f3b-d767-493d-9549-ee4fdf33c153 |  | checkpoint | Is the Traffic Management Plan on site?
checkpoint-status | 9fdf39a0-4c12-4e32-8fe6-f758c1e66d6e |  | checkpoint | Is the STMS on Site or back up STMS/TC?
checkpoint-status | 31800c78-d443-4e1d-9e86-653c7895ebf0 |  | checkpoint | Condition of signs OK?
checkpoint-status | 0c1343ac-258a-4b19-9fba-49896f9c2932 |  | checkpoint | Set out to plan or modified correctly?
checkpoint-status | 8e4c2f17-0556-4eb4-beaf-a8c0804f12df |  | checkpoint | Has the set up been monitored as per COPTTM requirements?
checkpoint-group | 706a40b4-b119-46d6-a903-ceb5d04d2f5e |  | section | Recommendations/Observations/NCRs
checkpoint-status | 898a476e-5b9c-4190-a305-cbf393aeb341 |  | checkpoint | Recommendations as per comments
checkpoint-status | 7f3d44ac-5e4a-47f5-921a-d863c9f23e84 |  | checkpoint | Observations as per comments
checkpoint-status | 26b12192-ba26-4c57-905e-76f9d4cb4e32 |  | checkpoint | NCRs
label | a4e80a10-2184-4fb5-9897-c540d7c59cc8 |  | note | NCR number and description
checkpoint-group | 79407c70-2b4b-4cf4-9db3-ae120ccbe96a |  | section | Sign off
checkpoint-status | 2eecc6c8-64e2-4d30-b1d7-1fdc19ca43f5 |  | checkpoint | Name and signature of the author
text | deaf60c0-fb5b-4a19-922a-88ce184870a7 |  | textbox | Name
text | 2ca80901-c486-4e3b-a34a-2bb4a1d43929 |  | textbox | Date
holdpoint | 9cd5b0ea-0eca-4060-8ab5-fb11877a80cd |  | signoff | Signature
checklist-sectioned | 672e56ec-2bd2-4ce0-a054-2e382a0a0091 |  | checklist | Site Establishment Audit |  |  |  |  | Yes | Site Establishment Audit | 87d3878e-1204-40c1-8ef2-4476d2cef98f
checkpoint-group | c757e267-ecae-4bcf-bb48-bba8b5332182 |  | section | Site Establishment (Start-up)
checkpoint-status | ff4c1fef-b855-4ba5-8e46-a13528c778e5 |  | checkpoint | Contract with Client signed and saved in the PCF?
checkpoint-status | 627ca3b5-8caa-42c3-bfd9-35af27a11b1b |  | checkpoint | Subcontractor Agreements signed and on the PCF?
checkpoint-status | 1d79d2b6-fa6f-4178-9dd6-477cf377c332 |  | checkpoint | Council Informed of activity?
checkpoint-status | e582f96c-0121-4c8e-ba87-4a44ef7cb796 |  | checkpoint | TMPs approved?
checkpoint-status | 8f769e82-92bb-4d38-836a-dbf220f2ca12 |  | checkpoint | Contract Management Plan completed (Approved and Signed)?
checkpoint-status | 3af520a8-304d-4375-a5ab-2763b3e5d23f |  | checkpoint | Inspection and Test Plan completed?
checkpoint-status | fd29bb6c-5f1a-4716-ac88-2b8448651a35 |  | checkpoint | Hazard Register completed?
checkpoint-status | a0afec26-2bad-4870-8d79-437c29649052 |  | checkpoint | WorkSafe notified of Hazardous Work?
checkpoint-status | 9da23a07-5e28-4a1c-aa3c-ac15f79c3fda |  | checkpoint | Information Sign up?
checkpoint-status | 9fa9a643-ca28-4328-bf63-0ba5a9acd18f |  | checkpoint | Dump Site located and agreement with owner signed?
checkpoint-status | ec0d0b73-aed2-4105-8e38-d585235fe86f |  | checkpoint | Construction Drawings on Site?
checkpoint-status | 42d8ab1b-e3f7-4006-8d62-b2d552d56590 |  | checkpoint | Public Notifications done?
checkpoint-status | d781c6d4-6b63-4d94-87fc-e68a5d15c784 |  | checkpoint | Site Folder established and on Site?
checkpoint-group | 8d70792d-85f1-4e16-8ccc-15c50ff2517a |  | section | Health and Safety Implementation
checkpoint-status | 97e304ca-ab58-4e3b-aeef-01cce29277c7 |  | checkpoint | Is the Site Contract Management Plan available and on site?
checkpoint-status | 52e9fb06-76c2-4b41-991d-fa338138023f |  | checkpoint | Is the Risk Register on site?
checkpoint-status | 3106d5a4-691b-487c-9c1d-3092783b8b59 |  | checkpoint | Are Daily Safety Plan forms available?
checkpoint-status | 313411ee-508d-415e-ba8c-6ab8cfd1a057 |  | checkpoint | JSEA for work being undertaken effective and signed on
checkpoint-status | e70fcb64-b9a6-48fe-8a16-edbf3880e022 |  | checkpoint | Are there emergency procedures in place?
checkpoint-status | edad45a8-7572-43cb-8c6c-a9e36c4225ac |  | checkpoint | Are permits being used and controls followed
checkpoint-status | a5321baf-cb98-4209-8e21-ffb2083bd36d |  | checkpoint | Is there a record of toolbox and signed off
checkpoint-status | 2f560d2a-3ee7-4c0b-a112-b840d5d00d03 |  | checkpoint | Is there a hazard register board displayed?
checkpoint-status | 685cdced-5e60-4623-973c-9f9fe7ee7813 |  | checkpoint | Is it up to date and reviewed?
checkpoint-status | 9072fbc3-b1c9-4000-8319-eb0b51008a2c |  | checkpoint | Is there a qualified first aider available?
checkpoint-status | 26a0089a-2d71-402b-8853-c1f720837352 |  | checkpoint | Has a drill been carried out?
checkpoint-status | 0ce71818-8c7a-45ba-bdc1-be6d06778ca3 |  | checkpoint | Are there toilet facilities available?
checkpoint-status | 6c3726d5-08f0-4263-8bdd-fd02903d1952 |  | checkpoint | Is there means to clean hands and dirt from body?
checkpoint-status | 1cd87002-c77a-4dc1-8b17-b7381408198b |  | checkpoint | Is there a smoko room or similar area?
checkpoint-status | 81171fe3-8060-4162-8966-7e92e1d18b20 |  | checkpoint | For those working with sewer works have they been immunised?
checkpoint-status | 8d44b0cd-3d38-473f-a840-b9cb1282bfaf |  | checkpoint | Is there a designated smoking area on site
checkpoint-status | 8d7f6df1-70bd-4d53-b666-25ab4cf66691 |  | checkpoint | Are there hazardous goods stored correctly on site
checkpoint-status | 61c38b2a-a025-44a3-b98c-5c59e1acc7f8 |  | checkpoint | SDS file in place matching substances on site?
checkpoint-group | 6bf2409f-35ca-4acd-b8f6-cd1121266b54 |  | section | PPE
checkpoint-status | d5c01e0c-72a4-407a-a179-857c56f32a5f |  | checkpoint | Are all staff wearing correct PPE?
checkpoint-status | aba41d01-50ae-451c-a859-6cde0e8e65be |  | checkpoint | Is it tidy and in good repair?
checkpoint-status | b9d7fff8-8996-4206-8124-629984b0d591 |  | checkpoint | Are staff wearing seatbelts on trucks, rollers and loaders?
checkpoint-status | 802360b3-810f-4653-bc0c-d7ba2168034a |  | checkpoint | Are staff wearing hardhats where there are overhead hazards?
checkpoint-group | 55b06350-6923-43b3-8001-13685a8d44b7 |  | section | Staff Involvement in Safety
checkpoint-status | 5a715d5e-9588-495f-ad7b-d5fa066e0443 |  | checkpoint | Are there completed daily safety plans present?
checkpoint-status | 0ee9a106-2252-4718-8b74-ff0833664da9 |  | checkpoint | Are there completed plans for the last few working days? Pick 3
checkpoint-status | 41bc708e-1a3a-45dd-8553-deb73541adea |  | checkpoint | Is there a record of staff induction? Pick 3 staff, are they inducted?
checkpoint-status | ebe065d9-2f28-4988-9cce-90ab02e3c146 |  | checkpoint | Have they signed the Daily Safety Plan for the day?
checkpoint-status | f35a5c4f-2f4e-401b-b898-3a1e1d3a211a |  | checkpoint | Is there a site Covid 19 sign in register?
checkpoint-status | 16785966-a073-4cd5-ac81-1e2f320142c6 |  | checkpoint | Are the United Civil posters (including Life Saving Rules) displayed
checkpoint-status | 5c5200e3-5362-48e9-8b4b-53b1c75e6ccf |  | checkpoint | Site and facilities being cleaned?
checkpoint-group | ac0f48e2-ac3b-4432-8a79-1a0bf434373d |  | section | Equipment
checkpoint-status | da976bf0-3dc3-425b-91dc-cb0ff99b5cf6 |  | checkpoint | Are chains and other relevant equipment tested and tagged?
checkpoint-status | a8b39609-203d-4451-a3ad-b05b7c446af3 |  | checkpoint | Is electrical equipment tagged and in test?
checkpoint-status | bd48f48e-81a2-4dc8-adb8-a541d735c455 |  | checkpoint | Is there a first aid kit on site and is it complete?
checkpoint-status | 00b0e2a7-4685-4d71-a628-34e8e09940ce |  | checkpoint | Is there a fire extinguisher on site and is it charged and in test date?
checkpoint-status | 311b78ee-f714-491d-855d-75c90e3b9431 |  | checkpoint | Are diesel and petrol containers tagged?
checkpoint-group | 9e5acb46-45dd-41da-9ebd-146791002747 |  | section | Mobile Equipment
checkpoint-status | 6724b79a-03e2-4689-98d2-5f88c21972af |  | checkpoint | Are maintenance books present on applicable equipment?
checkpoint-status | 89e0bd4d-db52-48f3-819d-1d3181430614 |  | checkpoint | Are maintenance sheets up to date?
checkpoint-status | 4d6779e1-8c0b-439b-98aa-63813f3ab371 |  | checkpoint | Are defects being reported?
checkpoint-group | fd452c8d-e066-4edd-a271-b1b9b1db39ce |  | section | Calibration
checkpoint-status | 88807389-bb58-40d5-b539-a05356ebc5a3 |  | checkpoint | Is critical measuring equipment calibrated?
checkpoint-status | 96ef4e16-3119-430f-ad34-0f4fdf76aa41 |  | checkpoint | Is it named with United Civil Id?
checkpoint-status | 0550a043-ea94-4975-92a3-be55904ac274 |  | checkpoint | Is there a calibration tag and is it in date?
checkpoint-status | fb258972-c05f-4880-a7ac-78167233a31c |  | checkpoint | Is it on the Certification and Calibration Plant Register?
checkpoint-group | 42cdf586-398c-48d7-a6a2-5026455816bd |  | section | Subcontractors
checkpoint-status | 306f9994-9a62-48b0-ac78-3ae4c827e97e |  | checkpoint | Are high risk subcontractors (QHS or E) on the Approved Suppliers List in PIM?
checkpoint-status | aa9833d2-ac02-4426-a9c0-72c454d25986 |  | checkpoint | Have they provided the required Site documentation i.e. JSA, Task Analysis, etc?
checkpoint-status | 8935cb2d-cb13-4d57-b694-0731c0b3ebad |  | checkpoint | Are they wearing correct PPE?
checkpoint-status | 302b610f-fd6d-4240-99bd-8161ea6c849d |  | checkpoint | Are subcontractor employees inducted?
checkpoint-status | 47118131-a455-4f7d-be13-2024b0eae365 |  | checkpoint | Are their records for subcontractor VOC on site
checkpoint-status | 0ef9f39d-ad51-48f9-92ef-f3a283fffd1b |  | checkpoint | Responsibilities are defined & coordinated via contractual agreements/overlapping duties form
checkpoint-group | 198a9f82-a5cf-4f0e-9719-07b908aa1f14 |  | section | Purchasing
checkpoint-status | 16daaaf9-0811-4c9a-80db-e189fcb2f126 |  | checkpoint | Do Purchase orders specify specifically what is being ordered?
checkpoint-status | df6cbb4d-459f-4214-91bb-6dcb573fa520 |  | checkpoint | Is the purchase amount within the DOA policy?
checkpoint-status | f1120cd4-c6c2-4dda-8507-fb6f6df1736d |  | checkpoint | Is person signing PO authorised?
checkpoint-group | 06cdd13d-c094-404a-9873-8ae29851601d |  | section | Training
checkpoint-status | 5827bed1-36f5-4b93-993d-15265139e68a |  | checkpoint | Are staff licenced for the machinery they are operating?
checkpoint-status | 92da8f90-52b2-4ef9-8fd4-1fffc507cacb |  | checkpoint | Do staff have competency records for the equipment they are using?
checkpoint-status | 059e6a3b-3ac9-4412-b575-b1250b8dbfbc |  | checkpoint | Training plan developed, including orientation plan for new team members?
checkpoint-status | de8dcec7-3555-4a48-8fe3-ab536c54c1f5 |  | checkpoint | Have all required training requirements been met by the project team, i.e., Health, Safety & Environment, etc.?
checkpoint-group | 43620e7d-35c8-49aa-bf7d-b4603ede22e5 |  | section | Excavations
checkpoint-status | 23ed4843-9371-4bd3-aca0-9e5cd37ea055 |  | checkpoint | Are excavations 1.5m deep or greater battered, benched or shielded?
checkpoint-status | beae3437-5ea9-488c-913e-6891ec2e1b73 |  | checkpoint | Permit to Dig in place for all excavations?
checkpoint-status | 8ed4a17f-b610-4b24-a3bf-9be2a7f49d72 |  | checkpoint | Are excavations protected for after hours?
checkpoint-group | 03074202-13ca-4cd3-bd83-056a06c70829 |  | section | Heights and Overhead
checkpoint-status | bfc03a6f-6b2a-48d3-b561-132af82d500f |  | checkpoint | Are edges protected?
checkpoint-status | 09283ec8-9077-494a-8b01-0854173e0068 |  | checkpoint | If working with 4m of power line proximity permits in place?
checkpoint-group | f6410afa-df39-4f79-acdc-0fab6512fb9b |  | section | Vehicles
checkpoint-status | da0e58cf-68e5-479a-8fc4-7643fd46c8a5 |  | checkpoint | Are vehicles being driven on the road licensed?
checkpoint-status | fa14590a-9b9a-440b-adb7-5e0754f9f1bd |  | checkpoint | Do they have WOF/COF if applicable?
checkpoint-status | 577170df-a6a1-4797-8974-5921363b1886 |  | checkpoint | Housekeeping are vehicles tidy?
checkpoint-status | 4747720f-22db-4b0d-9a9c-de70968e54d5 |  | checkpoint | Do the Utes/lights truck have diesel spill emergency response card?
checkpoint-status | 7aafa5bc-8995-4769-a45c-0dedfbdef9e4 |  | checkpoint | Do the Utes/light trucks have a complete first aid kit?
checkpoint-status | 452b6e2e-43a4-400d-8576-04bc4184189e |  | checkpoint | TSL Tickets on Site and used as required?
checkpoint-group | 5650f387-a7f9-43cc-8061-f4d3cd782f18 |  | section | Fences
checkpoint-status | 8435b2d0-c127-47f6-85a8-4f10b2d9b97c |  | checkpoint | Are fences compliant?
checkpoint-status | 8d298690-f4ed-4fcb-b6fe-b66c098851ae |  | checkpoint | Are they in good repair?
checkpoint-status | 71700b6a-6e99-47a0-be90-c710519c5de8 |  | checkpoint | Are they stable and safe?
checkpoint-status | 62080de2-8333-4d32-bff7-db337a048881 |  | checkpoint | Would they prevent entry by a child?
checkpoint-group | e72f59a2-afaf-483c-a0a9-c2e1013f3eca |  | section | Confined Space
checkpoint-status | 34c59c35-3dec-40d4-bac6-0472dd0850eb |  | checkpoint | Are forms available for CSE?
checkpoint-status | dc3e8197-a1fe-4b48-ad7f-b3f0be9dee72 |  | checkpoint | Are there trained CSE people on site?
checkpoint-status | 0c9e7a06-31c2-47bd-aeea-0a777b71a7d6 |  | checkpoint | Are the forms filled out correctly?
checkpoint-group | 4f49b7da-155b-44de-ae0a-5a20915d0f5c |  | section | Environmental
checkpoint-status | b5e13628-53d0-42fe-a047-da540b6e1ba4 |  | checkpoint | Erosion and Sediment Control Plan in place?
checkpoint-status | 85e7bb1a-750b-4c6d-98cf-a7c64434d6bd |  | checkpoint | Are applicable Resources Consents present?
checkpoint-status | 82e6134c-4596-4e69-809c-53b57cab2fec |  | checkpoint | Are consents complete with applicable drawings?
checkpoint-status | 552d8572-4e31-4f38-be6c-7d06f9524a68 |  | checkpoint | Are environmental issue addressed in the Daily Safety Plan?
checkpoint-status | 7230aa7c-e138-4eb7-8e50-4d564d75deed |  | checkpoint | Is a Spill Kit available and complete?
checkpoint-status | 8365d915-e31b-4e04-8a2f-f2f88f07ecce |  | checkpoint | Has monitoring been or planned to be carried out for the day?
checkpoint-status | b825f47d-c71b-4b49-b222-273386bba2bf |  | checkpoint | Compliant controls in place?
checkpoint-group | a83fd4d8-a08d-492d-aa51-17533bf0d1c6 |  | section | Quality
checkpoint-status | fa90c921-3341-47f0-a4d5-9c370663bc99 |  | checkpoint | Are relevant Inspection sheets available as required by the ITP?
checkpoint-status | f40b4775-6a81-481e-b34c-70a22ec66785 |  | checkpoint | Have the relevant inspection sheets been completed to applicable stage in the contract?
checkpoint-status | b34f9978-a3fa-4677-9fc1-67d52cdd1966 |  | checkpoint | Are Hold Points being signed off by the Engineer?
checkpoint-status | faac7436-8282-4a25-9da0-9b492610091d |  | checkpoint | Are the correct status drawings on site?
checkpoint-status | dce2417d-4a03-4d7c-b251-e752b4c0d422 |  | checkpoint | Are Daily Work Reports being carried out?
checkpoint-status | d6ef2949-b7ac-4516-829b-241bbd19f91e |  | checkpoint | Is there an As Built file present that is up to date?
checkpoint-group | b7be2b2e-0b55-4222-9c89-570412cbd56d |  | section | Traffic
checkpoint-status | bff1ba22-0d82-4568-9798-a336352c95c2 |  | checkpoint | Is the Traffic Management Plan on site?
checkpoint-status | 639fd6ed-5d27-4a9c-9794-52f37885cee8 |  | checkpoint | Is the STMS on Site or back up STMS/TC?
checkpoint-status | 1b0af1a5-f04b-4859-9022-f32126a18e06 |  | checkpoint | Condition of signs OK?
checkpoint-status | 1c6a4076-8c6a-4599-867f-e9cf48477611 |  | checkpoint | Set out to plan or modified correctly?
checkpoint-status | 9445515c-58b0-4c8f-b875-fecaa6e033c6 |  | checkpoint | Has the set up been monitored as per COPTTM requirements?
checkpoint-group | 88881894-0098-4615-80ec-0e115f689b13 |  | section | Operations
checkpoint-status | 1cfb3339-5217-43dc-af52-23da6a5fa47a |  | checkpoint | Are storage areas, safe, accessible and don’t interfere with designated areas (people & plant)
checkpoint-status | bd387372-e1a4-4426-93e0-a66590212331 |  | checkpoint | Manual handling risk has been identified, assessed and managed using an established risk assessment tool
checkpoint-status | 0002858f-08bb-43f4-b907-d24fcc7f649b |  | checkpoint | Dust suppression techniques are effective at reducing dust generation to a minimum?
checkpoint-status | aec03bce-c8a2-42f9-a314-90d77b6c0d26 |  | checkpoint | Working hour restrictions are in place and being adhered to in residential areas?
checkpoint-status | d03fd0a8-7ded-405f-8de7-05d3834c546e |  | checkpoint | Flora and fauna controls are effective and followed
checkpoint-status | aecaa6c3-d9eb-4f1c-be57-a9439ed58059 |  | checkpoint | Cultural & Heritage controls are effective and followed
checkpoint-status | d0f176ec-b924-4b4a-bced-19d190d9e8e9 |  | checkpoint | Waste Management controls are effective and followed
checkpoint-group | 9f192bec-a418-44e0-9744-1c760520caed |  | section | Recommendations/Observations/Opportunity for Improvement/NCRs
checkpoint-status | af396842-691f-4602-8ed0-ba36ef968575 |  | checkpoint | Recommendations as per comments
checkpoint-status | 14715fc7-1c6d-4a11-b15e-ace9cd2742d3 |  | checkpoint | Observations as per comments
checkpoint-status | 4f392589-b565-49eb-8652-62639947521b |  | checkpoint | Opportunity for Improvement
checkpoint-status | 3f4d75a4-61d7-4b6c-865d-9674bc93bc04 |  | checkpoint | NCRs
text | 4b5dee0a-3532-51a9-ac01-716198be22cc |  | textbox | NCR number and description
checkpoint-group | da8bfa4d-2b61-4629-9800-895eebcd67ee |  | section | Sign off
checkpoint-status | 7d1ed12e-9728-495b-968f-af817138f11d |  | checkpoint | Name and signature of the author
text | 0cd2f3da-e020-5385-8dc6-13cf4d08003f |  | textbox | Name
text | eec05269-0ae1-5792-be37-f9952e364a91 |  | textbox | Date
holdpoint | 3d0f68a6-80cc-4ca2-b6ab-fc92b9b7dadd |  | signoff | Signature
checklist-sectioned | 1f428994-222c-4058-941f-4e91dbda1290 |  | checklist | Project Audit |  |  |  |  | Yes | Project Audit Checklist V2 | a2152fcf-7bbd-4e4a-afcc-27a610f505a4
checkpoint-group | 41978093-cd64-4acf-a254-83a8b79e5265 |  | section | Site Establishment (Start-up)
checkpoint-status | 749a0e65-7d6f-4ba0-b776-2016fc7dc771 |  | checkpoint | Contract with Client signed?
checkpoint-status | 11d3dbe1-73f0-4dc2-969d-e89515b31c45 |  | checkpoint | Subcontractor Agreements signed and on the PCF?
checkpoint-status | da47e5c5-d141-4413-9890-7bc22390731e |  | checkpoint | Council Informed of activity?
checkpoint-status | 9840e92a-27a9-464c-9bb5-63f71d20ce31 |  | checkpoint | TMPs approved?
checkpoint-status | cf9b8084-6746-4f7c-b0f5-e3a316836428 |  | checkpoint | Quality Plan completed?
checkpoint-status | c3554fdd-9584-4f52-9112-43cdfc226621 |  | checkpoint | Inspection and Test Plan completed?
checkpoint-status | 2b229115-e6b5-42a4-afe9-20d1c4ba7b2b |  | checkpoint | Safety Plan completed?
checkpoint-status | 93735915-c665-41b6-bf91-0e8385bbc61f |  | checkpoint | Hazard Register completed?
checkpoint-status | e98365c7-bc37-4b88-b57c-cbe26272f415 |  | checkpoint | WorkSafe notified of Hazardous Work?
checkpoint-status | ff7e0877-b2ab-4372-b726-e63b137f8177 |  | checkpoint | Information Sign up?
checkpoint-status | 1bfd2097-3c53-4715-9875-c91eefe6505c |  | checkpoint | Dump Site located and agreement with owner signed?
checkpoint-status | dc01dd69-79ee-456b-8290-e9d59972fc32 |  | checkpoint | Construction Drawings on Site?
checkpoint-status | 7611b3ec-d734-4215-9476-9371ea7fcfee |  | checkpoint | Public Notifications done?
checkpoint-status | 465e6902-e536-4da6-8ad3-a16e9a701a80 |  | checkpoint | Site Folder established and on Site?
checkpoint-group | ceaee69c-b7d7-4fef-808a-b97866533670 |  | section | Health and Safety Implementation
checkpoint-status | 3f747911-a89d-4bd1-ab23-6f1d561aad05 |  | checkpoint | Is the Site Specific Safety Plan available and on site?
checkpoint-status | a728484b-e040-4b39-9fcd-8b85b39a7ea4 |  | checkpoint | Is the hazard register on site?
checkpoint-status | f538bbcc-ecd2-4226-9ca9-da26ddc5188b |  | checkpoint | Are Daily Safety Plan forms available?
checkpoint-status | d28c462e-8fd8-4cf7-80c0-39dfdb0dd4b6 |  | checkpoint | JSEA for work being undertaken effective and signed on
checkpoint-status | 07955e0f-25f8-4aab-87e2-9b0d7423bccb |  | checkpoint | Are there emergency procedures in place?
checkpoint-status | e1ad37a7-292e-4a4e-a9fd-85290d5863ff |  | checkpoint | Are permits being used and controls followed
checkpoint-status | 70fddad0-417d-4ae8-9413-36ea4c95f07c |  | checkpoint | Is there a record of toolbox and signed off
checkpoint-status | 05392f26-9935-4591-b044-1d6aa5eb4fe6 |  | checkpoint | Is there a hazard register board displayed?
checkpoint-status | 4ff26bc6-5ea2-496b-bee3-d47309c6ab39 |  | checkpoint | Is it up to date and reviewed?
checkpoint-status | 215fe1c1-9c86-4fe3-a708-3409af80feb5 |  | checkpoint | Is there a qualified first aider available?
checkpoint-status | 17df32ec-80fb-4d5e-a9f7-e22a4519cf59 |  | checkpoint | Has a drill been carried out?
checkpoint-status | 28fda734-54fd-4095-9a94-e11084eb9dbf |  | checkpoint | Are there toilet facilities available?
checkpoint-status | 98f43b12-95af-4ecf-b9c3-e897fde143c4 |  | checkpoint | Is there means to clean hands and dirt from body?
checkpoint-status | a6a042b9-19c4-45a2-811c-00f3833c8e5b |  | checkpoint | Is there a smoko room or similar area?
checkpoint-status | fafb5c89-c167-4c57-949c-a7449dee90fe |  | checkpoint | For those working with sewer works have they been immunised?
checkpoint-status | 3a5b30c0-1a3a-4ddc-8c40-9a52bdd6b2f7 |  | checkpoint | Is there a designated smoking area on site
checkpoint-status | 5b8b76ec-1d9d-44a8-836d-8bde30944a69 |  | checkpoint | Are there hazardous goods stored correctly on site
checkpoint-status | f27790d1-6964-4892-9bb6-bc5ad4583648 |  | checkpoint | SDS file in place matching substances on site?
checkpoint-group | ddbb04fc-dfab-469c-a9fa-a6f6948f3f38 |  | section | PPE
checkpoint-status | be434607-8b40-440e-8883-11174885ae40 |  | checkpoint | Are all staff wearing correct PPE?
checkpoint-status | 7a43d984-7a57-4526-b123-b89d782fd378 |  | checkpoint | Is it tidy and in good repair?
checkpoint-status | 6d9d16af-3b27-4829-8f82-b4658360302e |  | checkpoint | Are staff wearing seatbelts on trucks, rollers and loaders?
checkpoint-status | f0be7590-a8fc-4af7-84ab-1e7ee9863835 |  | checkpoint | Are staff wearing hardhats where there are overhead hazards?
checkpoint-group | 4d857eb1-e385-4b45-89c1-305c668005cb |  | section | Staff Involvement in Safety
checkpoint-status | 07578ee2-42a8-462c-9bc5-9410aac89bd4 |  | checkpoint | Are there completed daily safety plans present?
checkpoint-status | 2f065f10-8072-4e0f-80ad-8b9628e0cc16 |  | checkpoint | Are there completed plans for the last few working days? Pick 3
checkpoint-status | 74f659cf-a382-4d88-8862-4bcb2aff9595 |  | checkpoint | Is there a record of staff induction? Pick 3 staff â€“ are they inducted?
checkpoint-status | 075004a2-b021-4180-b1e7-fd29b254dfe3 |  | checkpoint | Have they signed the Daily Safety Plan for the day?
checkpoint-status | d865c5fe-3a66-4c64-ae2f-f418ff1f22fe |  | checkpoint | Is there a site Covid 19 sign in register?
checkpoint-status | b0083f66-763f-41c2-b0e3-a2b1793ac45f |  | checkpoint | Do staff have Covid19 site diaries?
checkpoint-status | f84c1dbf-97e6-4f8c-92de-c9490404476c |  | checkpoint | Are the United Civil posters (including Life Saving Rules) displayed
checkpoint-status | 3ea082c4-92e4-4251-b4fb-e4f16bcbc052 |  | checkpoint | Site and facilities being cleaned?
checkpoint-group | 3de4069d-bb8f-43a1-83e7-b01d4c2af305 |  | section | Equipment
checkpoint-status | 59689e2b-c348-4915-854e-f4277936b44c |  | checkpoint | Are chains and other relevant equipment tested and tagged?
checkpoint-status | cbfa5978-ea6a-40c2-ac04-03786f2a8c0d |  | checkpoint | Is electrical equipment tagged and in test?
checkpoint-status | ea707a5f-b802-4f2b-a47b-f858b3b59347 |  | checkpoint | Is there a first aid kit on site and is it complete?
checkpoint-status | 99b8aadf-9299-4207-955c-034de7a8cddf |  | checkpoint | Is there a fire extinguisher on site and is it charged and in test date?
checkpoint-status | 18b1b4f1-e668-4616-9806-7f85d4131a11 |  | checkpoint | Are diesel and petrol containers tagged?
checkpoint-group | 9f732d66-e35e-4fd7-bb69-2239b0113955 |  | section | Mobile Equipment
checkpoint-status | 6b97b263-08af-43bc-acf3-02a64443a946 |  | checkpoint | Are maintenance books present on applicable equipment?
checkpoint-status | 8620923e-0d53-46dd-aa48-189dba559a8e |  | checkpoint | Are maintenance sheets up to date?
checkpoint-status | e64de438-a675-4012-809a-5c249fe94502 |  | checkpoint | Are defects being reported?
checkpoint-group | 2b57f159-849e-4b9a-9403-ffab119ea6ae |  | section | Calibration
checkpoint-status | ab5aed23-c510-4918-a134-a19bb24c3ed3 |  | checkpoint | Is critical measuring equipment calibrated?
checkpoint-status | b970fa93-bedd-4558-9e24-9a23d23f65fb |  | checkpoint | Is it named with United Civil Id?
checkpoint-status | 73fe57fa-1e85-44e1-9d8c-19058d10677a |  | checkpoint | Is there a calibration tag and is it in date?
checkpoint-status | f26fe397-f0c2-49e4-9b38-c6958058aac8 |  | checkpoint | Is it on the Certification and Calibration Plant Register?
checkpoint-group | b7d26bc2-ad0a-4cab-87d6-7a87a98dfbec |  | section | Subcontractors
checkpoint-status | 7c1f0150-c3d4-4e98-8fca-8082a014e075 |  | checkpoint | Are high risk subcontractors (QHS or E) on the Approved Suppliers List in PIM?
checkpoint-status | de2b8d43-de9d-4ff3-a11f-4f4ec20f4982 |  | checkpoint | Have they provided the required Site documentation i.e. JSA, Task Analysis, etc?
checkpoint-status | 90da61f7-2469-4544-acfa-d5333d54ab74 |  | checkpoint | Are they wearing correct PPE?
checkpoint-status | bbc01415-8353-4c0d-af6d-d258352642b7 |  | checkpoint | Are subcontractor employees inducted?
checkpoint-status | 994d0b22-4e16-4ea0-ba41-b2cc83f81f41 |  | checkpoint | Are their records for subcontractor VOC on site
checkpoint-status | 57a73b7f-ea4f-4abe-a3a1-2688c3327174 |  | checkpoint | Responsibilities are defined & coordinated via contractual agreements/overlapping duties form
checkpoint-group | c76bea99-512b-4907-8fe2-23323241d1a8 |  | section | Purchasing
checkpoint-status | 146be043-06f4-4f27-9a03-81eab7194639 |  | checkpoint | Do Purchase orders specify specifically what is being ordered?
checkpoint-status | 43108f4b-cea8-4f41-a741-a6545e2e4f39 |  | checkpoint | Is the purchase amount within the DOA policy?
checkpoint-status | 7aee2685-29a2-4ded-a918-257a602c0dba |  | checkpoint | Is person signing PO authorised?
checkpoint-group | 56cf5e37-3669-4cc6-bc98-1c9d9187b601 |  | section | Training
checkpoint-status | abb1e6e4-b989-4d25-bb38-a0a8895167be |  | checkpoint | Are staff licenced for the machinery they are operating?
checkpoint-status | 2fdae3be-0c61-44f5-9b1a-2342a875b7be |  | checkpoint | Do staff have competency records for the equipment they are using?
checkpoint-status | 666f63ce-9871-41f5-a1b7-9a1e49aed4b4 |  | checkpoint | Training plan developed, including orientation plan for new team members?
checkpoint-status | 3f362c5f-c4f4-4594-aa4a-cff9cea73f5f |  | checkpoint | Have all required training requirements been met by the project team, i.e., Health, Safety & Environment, etc.?
checkpoint-group | d65a1a1f-14fb-40cf-a79b-c2b23793b269 |  | section | Excavations
checkpoint-status | c4755078-1edf-46cf-8b27-aaf23c6f8b39 |  | checkpoint | Are excavations 1.5m deep or greater battered, benched or shielded?
checkpoint-status | 16ddba87-2c61-4e79-8075-b634f3ef9b6e |  | checkpoint | Is approved Code of Practice in place for excavation & trenches?
checkpoint-status | 1e68f9ba-9624-42cb-baf1-3c684ed50182 |  | checkpoint | Are excavations protected for after hours?
checkpoint-group | d3984ad6-b34e-40a5-a91c-bc73068b356e |  | section | Heights and Overhead
checkpoint-status | d0281570-7b8e-41ae-8c6c-1d7d4c5a79e6 |  | checkpoint | Are edges protected?
checkpoint-status | 52132901-0e4a-460b-a8d4-f462c9eb811a |  | checkpoint | If working with 4m of power line proximity permits in place?
checkpoint-group | f94c6d70-6c6c-45e8-b796-39a412ad58d0 |  | section | Vehicles
checkpoint-status | 17670c74-3c60-4ce5-a635-759670b2a3c0 |  | checkpoint | Are vehicles being driven on the road licensed?
checkpoint-status | 9f72554d-842d-4d0d-a3f2-40173cdbbcb8 |  | checkpoint | Do they have WOF/COF if applicable?
checkpoint-status | 23d47b82-1d4b-4f30-9f77-5d9d11e77737 |  | checkpoint | Housekeeping â€“ vehicles tidy?
checkpoint-status | e91186c8-42de-43ac-9992-a16e4806c11f |  | checkpoint | Do the Utes/lights truck have diesel spill emergency response card?
checkpoint-status | a3d37adf-a9b2-4203-93a4-0f17a0951f29 |  | checkpoint | Do the Utes/light trucks have a complete first aid kit?
checkpoint-status | 7afa1f06-2f42-4c25-a7db-c7622811f456 |  | checkpoint | TSL Tickets on Site and used as required?
checkpoint-group | 738e5975-05f7-47c9-a66d-3ee433492dc4 |  | section | Fences
checkpoint-status | 3ee3518f-4b12-4007-aa03-ee40e8fcc7f0 |  | checkpoint | Are fences compliant?
checkpoint-status | 72122548-d8de-4a5a-b9c0-acad0e13f660 |  | checkpoint | Are they in good repair?
checkpoint-status | 4c140d06-d509-43fa-94b3-a938b119da97 |  | checkpoint | Are they stable and safe?
checkpoint-status | 7bc491e4-4952-423e-a13d-e28af0a20c1c |  | checkpoint | Would they prevent entry by a child?
checkpoint-group | e5aaaabb-ed07-4574-af42-81f548ee0fac |  | section | Confined Space
checkpoint-status | 11bc523d-2a25-4fbc-a66c-38466af15a55 |  | checkpoint | Are forms available for CSE?
checkpoint-status | d7fd718b-8950-44d3-975f-5b79e30ccb92 |  | checkpoint | Are there trained CSE people on site?
checkpoint-status | 36837e76-9d69-4d3f-8b4b-bd5fd28c5afb |  | checkpoint | Are the forms filled out correctly?
checkpoint-group | 575e91c3-d004-48bb-9cab-a958df9272dd |  | section | Environmental
checkpoint-status | c60e5697-3914-4374-a790-2921a9a322d3 |  | checkpoint | Is the Environmental Management Plan on site?
checkpoint-status | bac97b4b-c757-4466-933a-50a07b425fea |  | checkpoint | Erosion and Sediment Control Plan in place?
checkpoint-status | 6ce9614e-f600-4bff-a410-a06f05bd2bd5 |  | checkpoint | Are applicable Resources Consents present?
checkpoint-status | 351d6298-4dfe-45eb-b71a-29b6c2821bf0 |  | checkpoint | Are consents complete with applicable drawings?
checkpoint-status | 93d02f75-10fb-4ce2-978b-15dbe3d777da |  | checkpoint | Are environmental issue addressed in the Daily Safety Plan?
checkpoint-status | f8ced12b-66c8-4934-a340-f2b5ff913a2d |  | checkpoint | Is a Spill Kit available and complete?
checkpoint-status | 54535587-55a5-4e92-b09f-6610113b2c4d |  | checkpoint | Has monitoring been or planned to be carried out for the day?
checkpoint-status | aeac2a96-4ec8-4e39-8c0a-a19ed88c0449 |  | checkpoint | Is there someone who is TP90/GD05 trained on site?
checkpoint-status | 18816c03-7244-453a-a0de-cab8972844ac |  | checkpoint | (Erosion & sediment control - ARC)
checkpoint-status | fd88993e-6797-486c-a839-c8159dc69548 |  | checkpoint | Compliant controls in place?
checkpoint-group | dc9ad24d-72b3-475b-b4a7-1e7109bdb4b8 |  | section | Quality
checkpoint-status | e0e5fa2b-8c5c-4b2c-b6ef-501949fbf400 |  | checkpoint | Is the Contract Quality Plan on site?
checkpoint-status | f98506e7-59ea-4a23-952f-d6931a7a642a |  | checkpoint | Are relevant Inspection sheets available as required by the ITP?
checkpoint-status | 594fb096-400e-4a52-8295-3eb11733336f |  | checkpoint | Have the relevant inspection sheets been completed to applicable stage in the contract?
checkpoint-status | af54ec31-50b5-42a9-aaa5-a0e4e65a5f25 |  | checkpoint | Are Hold Points being signed off by the Engineer?
checkpoint-status | b6e6d42d-30a7-4b75-8798-4d8df7ecfd4b |  | checkpoint | Are the correct status drawings on site?
checkpoint-status | 1a24073d-d14a-4a60-bf7e-13ac09f6f610 |  | checkpoint | Are Daily Work Reports being carried out?
checkpoint-status | 82086bb8-1d59-4a82-8acb-d6322a217a49 |  | checkpoint | Is there an As Built file present that is up to date?
checkpoint-group | f67e18be-5d22-428e-bdfb-38515c36e487 |  | section | Project Central File (PCF)
checkpoint-status | 23b492b6-ef81-433f-ba86-f7cfc4b70bca |  | checkpoint | Are documents uniquely identified and version controlled
checkpoint-status | 4a43d7ea-bd69-4543-95bc-52b262418c32 |  | checkpoint | Are documents being stored only on backed-up network drives?
checkpoint-status | 142f0653-8109-40cb-90f7-bdf54404ae1a |  | checkpoint | Is the electronic PCF the main file?
checkpoint-status | 6f21ffe2-0a2f-4841-8ee5-89b65c640868 |  | checkpoint | Are all project specific email files stored on Union Square?
checkpoint-status | c74972c2-0ef7-40e0-b031-cacbf3d6a7cc |  | checkpoint | Are both physical and electronic document files archived?
checkpoint-group | fbf79a8d-ade5-4d91-b505-f9e046bb8b3f |  | section | Project Management
checkpoint-status | 6bd43188-747c-4214-859d-9297be05a045 |  | checkpoint | Are variations documented and is there as file?
checkpoint-status | 17467ac7-b4a4-4732-acb0-8a6d956ed7fb |  | checkpoint | Has the CQP been duly updated to reflect any contract modification(s)?
checkpoint-status | 9b0276e1-3296-4858-8c7f-1ce5ed9534ef |  | checkpoint | Are payment claims on file and upto date?
checkpoint-status | c5cddf2a-679f-4c36-9ccd-be77eb38bedf |  | checkpoint | Are subcontractor progress claims on file and upto date?
checkpoint-status | 7d8db973-d22d-4f80-a0ac-04765d6b6c7c |  | checkpoint | Are payment schedules on file and upto date?
checkpoint-status | 5086f5e4-2a47-44c4-b722-03fe751ed349 |  | checkpoint | Are Site meeting minutes kept upto date?
checkpoint-status | 9a6338f2-5f47-4272-9244-40e4f439df01 |  | checkpoint | Are subcontractor payment schedules ok file and kept upto date?
checkpoint-status | aded5dd1-f685-45bd-bfab-97695e53360d |  | checkpoint | Is the financial forecasting in place and upto date?
checkpoint-group | a66db886-d6bf-4964-baad-9aaf445cb77c |  | section | Concerns, Corrective and Preventive Action
checkpoint-status | ed581b63-909b-4ecb-9544-bd46bda125c9 |  | checkpoint | Is there a concerns register be operated?
checkpoint-status | d670421e-9a4d-4370-87dc-7e3da88c037c |  | checkpoint | Is there a corrective action file and is being?
checkpoint-status | 94f1d344-1eff-4665-ac7e-f855657c67cd |  | checkpoint | Do Corrective Actions identify a root cause?
checkpoint-status | d9779810-a544-44cb-a3d5-adf4672697a0 |  | checkpoint | Are Corrective Actions verified to ensure they are effective?
checkpoint-status | 5220682f-c758-470b-9d77-bd21c580ccd6 |  | checkpoint | Is Customer Feedback being recorded?
checkpoint-group | c65316ba-4a0e-4fd2-ad75-ad79ef277bbf |  | section | Traffic
checkpoint-status | 8c9d06f0-199b-493e-8ba7-884dc9a5064f |  | checkpoint | Is the Traffic Management Plan on site?
checkpoint-status | 52bc7e6a-d18c-4090-b829-0900946a79c6 |  | checkpoint | Is the STMS on Site or back up STMS/TC?
checkpoint-status | c2161239-220a-4b64-a6f9-342a0861addc |  | checkpoint | Condition of signs OK?
checkpoint-status | d3a7db2d-d155-462c-8eae-adc09b60054e |  | checkpoint | Set out to plan or modified correctly?
checkpoint-status | 89379aac-9411-48e8-8c72-df332c8cd2dc |  | checkpoint | Has the set up been monitored as per COPTTM requirements?
checkpoint-group | 065e9390-2642-44db-8237-126f99fd4375 |  | section | Operations
checkpoint-status | c4b4c585-2bad-4431-90ea-fab4bd518218 |  | checkpoint | Are storage areas, safe, accessible and don’t interfere with designated areas (people & plant)
checkpoint-status | 45a5ff0e-dc6f-4d89-801c-8d35b48d44ae |  | checkpoint | Manual handling risk has been identified, assessed and managed using an established risk assessment tool
checkpoint-status | 2016c0e9-e5fd-47c9-be24-f8f8cbd7df76 |  | checkpoint | Dust suppression techniques are effective at reducing dust generation to a minimum?
checkpoint-status | f79d09e2-a92b-4683-8138-cfb4ded97d21 |  | checkpoint | Working hour restrictions are in place and being adhered to in residential areas?
checkpoint-status | cd6db50c-e0c4-4174-b24c-ee015c838134 |  | checkpoint | Flora and fauna controls are effective and followed
checkpoint-status | 426f032f-d5bb-470f-9359-ab8bbb982d63 |  | checkpoint | Cultural & Heritage controls are effective and followed
checkpoint-status | 69710a53-ce5a-4815-bc03-07c05401fca4 |  | checkpoint | Waste Management controls are effective and followed
checkpoint-group | eb8ea737-070c-4fcf-b5cd-7d206ea81dfe |  | section | Recommendations/Observations/NCRs
checkpoint-status | 5cd8abc7-ee46-46d7-bb3a-b0db262b7865 |  | checkpoint | Recommendations as per comments
checkpoint-status | da18d28d-58c3-460a-a398-31f483678492 |  | checkpoint | Observations as per comments
checkpoint-status | 59c4d626-77e5-480a-a6cc-45a0328515fc |  | checkpoint | NCRs
label | 6a0763fc-b3a2-54e7-9fd8-b9a3431dc793 |  | note | NCR number and description
checkpoint-group | cef89508-7dc5-4256-b43d-b9f87dd33cf4 |  | section | Sign off
checkpoint-status | 376cf223-bd78-4294-9245-0c54cc0d067e |  | checkpoint | Name and signature of the author
text | 1f04789a-f6dc-59b8-b07f-f4928fff10c7 |  | textbox | Name
text | 33174b6a-2729-53d6-9288-bf2bf9522812 |  | textbox | Date
holdpoint | 21a5d8ce-a262-4beb-b097-7a6b7a59a7cf |  | signoff | Signature
checklist-sectioned | 63008985-bcb1-4704-b376-346111c5ac04 |  | checklist | Periodic Project Audit |  |  |  |  | Yes | Periodic Project Audit | df055fba-1a89-43a2-b41c-c7d72b762960
checkpoint-group | d4f6b264-9c3b-4747-b8e5-ec50277e477b |  | section | Health and Safety Implementation
checkpoint-status | fdd701eb-e9a6-46b6-ac63-246ce0ca7ac2 |  | checkpoint | Is the Site Contract Management Plan signed and available on site?
checkpoint-status | 612e38db-52d2-48e3-b9b1-242828c17643 |  | checkpoint | Is the Risk Register on site?
checkpoint-status | de5c5320-81cb-4d26-8bbf-85e9783f4513 |  | checkpoint | Are Daily Safety Plan forms available?
checkpoint-status | e7759ed0-68de-4a58-b434-2c59e95aef69 |  | checkpoint | JSEA for work being undertaken effective and signed on
checkpoint-status | 5e2e9090-62ac-4537-a8e1-6f21427f1d6d |  | checkpoint | Are there emergency procedures in place?
checkpoint-status | 8b6b0342-8bb2-4304-9674-2440fa783a0c |  | checkpoint | Are permits being used and controls followed
checkpoint-status | 39ff2107-3756-41cb-b28b-0ccd73b734c4 |  | checkpoint | Is there a record of toolbox and signed off
checkpoint-status | 88a619a1-9dc4-4883-a4a1-f4d532a3b4f0 |  | checkpoint | Is there a hazard register board displayed?
checkpoint-status | d2dd4cbe-7fbe-4a23-b96b-f9e34b45f20e |  | checkpoint | Is it up to date and reviewed?
checkpoint-status | 7ff953c0-558f-4cd7-9727-0ecec416174a |  | checkpoint | Is there a qualified first aider available?
checkpoint-status | 2a845a46-3240-47b0-a49b-5dc4d1d0bcf2 |  | checkpoint | Has a drill been carried out?
checkpoint-status | 5fab097f-8585-46db-837d-2e18b35f2eb7 |  | checkpoint | Are there toilet facilities available?
checkpoint-status | 56f135b5-1057-4cf8-b5b9-33bc3a8eb807 |  | checkpoint | Is there means to clean hands and dirt from body?
checkpoint-status | d9060cd7-9728-41c9-942a-32203c181889 |  | checkpoint | Is there a smoko room or similar area?
checkpoint-status | 672106e3-f30f-4997-9777-e6912f3d4c66 |  | checkpoint | For those working with sewer works have they been immunised?
checkpoint-status | f3b2782c-6365-4921-924b-e11597cd522c |  | checkpoint | Is there a designated smoking area on site
checkpoint-status | 3d29a5aa-6133-4db6-951e-810fd9864f06 |  | checkpoint | Are there hazardous goods stored correctly on site
checkpoint-status | 9bfd4bff-0fc6-4f2f-b7bd-982060a307cc |  | checkpoint | SDS file in place matching substances on site?
checkpoint-group | faefc272-55a1-448d-bb08-f0a0a4f6de3e |  | section | PPE
checkpoint-status | e8206ad0-1869-42ab-a681-eca44c62869d |  | checkpoint | Are all staff wearing correct PPE?
checkpoint-status | c160ecf6-ea15-4800-86ec-6d4acd0a2776 |  | checkpoint | Is it tidy and in good repair?
checkpoint-status | 0b05b5aa-d6c3-4f37-a978-f708e8a786ae |  | checkpoint | Are staff wearing seatbelts on trucks, rollers and loaders?
checkpoint-status | 7e0b4f50-1fbf-444b-949b-bf4f13114dea |  | checkpoint | Are staff wearing hardhats where there are overhead hazards?
checkpoint-group | 46a1f23b-fafc-41ad-8497-e78e0b1501a6 |  | section | Staff Involvement in Safety
checkpoint-status | 1b65816d-8cd0-4219-a41d-85dbcb23eac3 |  | checkpoint | Are there completed daily safety plans present?
checkpoint-status | 23f3fab7-9027-4d8e-a60d-a561e21e73b5 |  | checkpoint | Are there completed plans for the last few working days? Pick 3
checkpoint-status | f08492af-2308-4370-ae1e-986f496abff1 |  | checkpoint | Is there a record of staff induction? Pick 3 staff, are they inducted?
checkpoint-status | 316bac2b-6ba6-4863-905e-888e43d77b82 |  | checkpoint | Have they signed the Daily Safety Plan for the day?
checkpoint-status | fe66bdc0-6b48-4c9f-84dd-70670c56fc97 |  | checkpoint | Is there a site Covid 19 sign in register?
checkpoint-status | 89de5fe6-29ad-4de4-a32f-5c9442fab441 |  | checkpoint | Are the United Civil posters (including Life Saving Rules) displayed
checkpoint-status | 838f5839-8c94-49d1-9300-17d83c7239e4 |  | checkpoint | Site and facilities being cleaned?
checkpoint-group | aef59589-50ac-4a1a-909d-1ff09825473f |  | section | Equipment
checkpoint-status | 2ef4211a-d6a9-4aa0-8e77-5235ca083654 |  | checkpoint | Are chains and other relevant equipment tested and tagged?
checkpoint-status | c518d2e1-03eb-4e52-ac58-5250215851f4 |  | checkpoint | Is electrical equipment tagged and in test?
checkpoint-status | 81142f1b-d285-4e9e-8174-0f92ebe4e303 |  | checkpoint | Is there a first aid kit on site and is it complete?
checkpoint-status | c05139f9-7cde-4e3b-aefd-736208edb688 |  | checkpoint | Is there a fire extinguisher on site and is it charged and in test date?
checkpoint-status | 33ca8a37-0790-424f-8beb-ff6a0b13a11d |  | checkpoint | Are diesel and petrol containers tagged?
checkpoint-group | 8abf1b99-c848-4ac7-954e-de901b3054ae |  | section | Mobile Equipment
checkpoint-status | 902ae796-aff1-4893-a21c-e536c186fc43 |  | checkpoint | Are maintenance books present on applicable equipment?
checkpoint-status | 2efa442c-bd3c-4cfe-8406-9b6ad67d96fc |  | checkpoint | Are maintenance sheets up to date?
checkpoint-status | e59a2974-9f46-47a8-8582-81875ee582a7 |  | checkpoint | Are defects being reported?
checkpoint-group | 6e2ec5d5-ff16-4981-abce-865fcb463a3b |  | section | Calibration
checkpoint-status | 432e1b13-7f48-4536-b502-a8614c1bd145 |  | checkpoint | Is critical measuring equipment calibrated?
checkpoint-status | 01fd2776-6a08-45d8-bdf4-d2c6a2ac0e07 |  | checkpoint | Is it named with United Civil Id?
checkpoint-status | 5a33dab6-f721-4fc2-be16-25d1c5819f54 |  | checkpoint | Is there a calibration tag and is it in date?
checkpoint-status | 932a1299-462f-45b8-9fe3-41ac3ca718cb |  | checkpoint | Is it on the Certification and Calibration Plant Register?
checkpoint-group | 0915f553-2019-497f-b9de-91872c038ded |  | section | Subcontractors
checkpoint-status | 6755de0b-63ae-4341-a82d-a28d202a795e |  | checkpoint | Are high risk subcontractors (QHS or E) on the Approved Suppliers List in PIM?
checkpoint-status | e1e17aa4-c848-4d0b-b172-193566e41fa0 |  | checkpoint | Have they provided the required Site documentation i.e. JSA, Task Analysis, etc?
checkpoint-status | b7e1118a-10fc-4b24-a384-9a3b1e37a49d |  | checkpoint | Are they wearing correct PPE?
checkpoint-status | 2ec8a5ec-05da-429c-8cab-899b764f2c9a |  | checkpoint | Are subcontractor employees inducted?
checkpoint-status | 4997c08a-7098-4a0b-bffd-9764a204a477 |  | checkpoint | Are their records for subcontractor VOC on site
checkpoint-status | ae76229f-202b-46ce-b276-bd4263853e9c |  | checkpoint | Responsibilities are defined & coordinated via contractual agreements/overlapping duties form
checkpoint-group | 2ff6220d-1ef4-4a8f-ac34-679e53293264 |  | section | Purchasing
checkpoint-status | 898d72f7-bf43-407a-addd-17cb61313f1f |  | checkpoint | Do Purchase orders specify specifically what is being ordered?
checkpoint-status | 7ccb7d26-ef64-449e-aff0-0a0bc2dcd600 |  | checkpoint | Is the purchase amount within the DOA policy?
checkpoint-status | d1d035eb-06a8-4f0e-a2dd-5abded88a725 |  | checkpoint | Is person signing PO authorised?
checkpoint-group | 1a3efd58-ba6f-49f8-9162-866b85a64193 |  | section | Training
checkpoint-status | 81b5823d-da6f-47dc-90c9-00eb333d872d |  | checkpoint | Are staff licenced for the machinery they are operating?
checkpoint-status | ee46023d-5d72-4f47-8771-bbfb8a70b4ef |  | checkpoint | Do staff have competency records for the equipment they are using?
checkpoint-status | e2662d9b-e11f-4776-ac05-2e9723a0ee5a |  | checkpoint | Training plan developed, including orientation plan for new team members?
checkpoint-status | 9a6252df-4a59-4d21-89fd-3d8da63c305a |  | checkpoint | Have all required training requirements been met by the project team, i.e., Health, Safety & Environment, etc.?
checkpoint-group | 3af75286-05fd-4c84-b494-97f1537390be |  | section | Excavations
checkpoint-status | b2f85806-3f89-427c-b8d9-12c30a2720bf |  | checkpoint | Are excavations 1.5m deep or greater battered, benched or shielded?
checkpoint-status | c315e35a-aecc-4d9e-942b-d9b9724b6f9b |  | checkpoint | Permit to Dig in place for all excavations?
checkpoint-status | 5c05764e-58a6-448b-a10a-b4e61dcce955 |  | checkpoint | Are excavations protected for after hours?
checkpoint-group | 9041ecd3-5b03-4fdd-8a51-fc712307aa36 |  | section | Heights and Overhead
checkpoint-status | e6c82476-7179-437f-aaec-3ae7957d9987 |  | checkpoint | Are edges protected?
checkpoint-status | 38c9dba3-e36f-461f-875d-96a21c1412f9 |  | checkpoint | If working with 4m of power line proximity permits in place?
checkpoint-group | c12ee305-402b-4e7b-9c8a-9623c81c825c |  | section | Vehicles
checkpoint-status | dc13dae2-c1ed-4340-a957-15aaf059599d |  | checkpoint | Are vehicles being driven on the road licensed?
checkpoint-status | c7a4b35a-bdd8-460d-949c-7a0689ba0095 |  | checkpoint | Do they have WOF/COF if applicable?
checkpoint-status | c9f1d79d-6596-4f36-9e38-5b1d39a5706f |  | checkpoint | Housekeeping are vehicles tidy?
checkpoint-status | 891e4c67-a502-4382-80a7-e4e814f5d906 |  | checkpoint | Do the Utes/lights truck have diesel spill emergency response card?
checkpoint-status | 2fd03956-2fb6-4c7e-a3d1-4d05cc78dbef |  | checkpoint | Do the Utes/light trucks have a complete first aid kit?
checkpoint-status | 192c6590-6e11-4d60-9c22-d656dcf9a917 |  | checkpoint | TSL Tickets on Site and used as required?
checkpoint-group | b5b32a35-3920-485a-93d8-8698bcb922fb |  | section | Fences
checkpoint-status | 26e840b4-63e0-46e5-bcd1-9fb83abc5b36 |  | checkpoint | Are fences compliant?
checkpoint-status | e0967ce2-b48d-4274-bfb8-fce34b77ad75 |  | checkpoint | Are they in good repair?
checkpoint-status | a8f323c8-6725-40df-a0d6-cec25d2a7f08 |  | checkpoint | Are they stable and safe?
checkpoint-status | 6f1cf41e-375a-4e6f-962a-64595db65172 |  | checkpoint | Would they prevent entry by a child?
checkpoint-group | b274d4d8-3539-4724-900b-219b12308f74 |  | section | Confined Space
checkpoint-status | 40a3c9af-b006-4413-966f-160cd99688c6 |  | checkpoint | Are forms available for CSE?
checkpoint-status | 87987ab6-a68a-4ffa-910e-555221b1223d |  | checkpoint | Are there trained CSE people on site?
checkpoint-status | cb2c4dcf-1c9a-45a9-85a0-a7ffdbc5c150 |  | checkpoint | Are the forms filled out correctly?
checkpoint-group | 96c8e93e-4459-4ac3-9e2b-081561bc9ec4 |  | section | Environmental
checkpoint-status | 137baee1-f160-4d3c-bc8f-159cd37e4b2f |  | checkpoint | Erosion and Sediment Control Plan in place?
checkpoint-status | 94eedf1f-c16f-40e4-8c89-9e9d5f96eac8 |  | checkpoint | Are applicable Resources Consents present?
checkpoint-status | feb8e397-0462-49e3-8257-9df560d9f252 |  | checkpoint | Are consents complete with applicable drawings?
checkpoint-status | 66ff4507-12ea-4364-8eea-369f90d65d6c |  | checkpoint | Are environmental issue addressed in the Daily Safety Plan?
checkpoint-status | c14983cf-d497-47ba-88e8-8db248105923 |  | checkpoint | Is a Spill Kit available and complete?
checkpoint-status | 80d55c6a-cc6b-4f4b-a71b-5b1c0fb1005a |  | checkpoint | Has monitoring been or planned to be carried out for the day?
checkpoint-status | 9a011152-8bf6-4f70-9cbb-7424f78a5832 |  | checkpoint | Compliant controls in place?
checkpoint-group | b564ef7d-57f6-4e6a-a84b-664369869fbf |  | section | Quality
checkpoint-status | a2405301-7968-4cf8-b77b-9be59ef1cde7 |  | checkpoint | Are relevant Inspection sheets available as required by the ITP?
checkpoint-status | 136650a8-42af-4709-892a-111814b6eb42 |  | checkpoint | Have the relevant inspection sheets been completed to applicable stage in the contract?
checkpoint-status | 57e3017b-5fff-4d96-9acf-ee418c094b08 |  | checkpoint | Are Hold Points being signed off by the Engineer?
checkpoint-status | 91486ad3-f688-4816-be4d-2bcc9c893c7b |  | checkpoint | Are the correct status drawings on site?
checkpoint-status | d42b25ca-5a1b-4fcc-82a3-112e94efd425 |  | checkpoint | Are Daily Work Reports being carried out?
checkpoint-status | 82a05480-5387-4170-868c-e7916f6c5050 |  | checkpoint | Is there an As Built file present that is up to date?
checkpoint-group | a47546c5-017f-4ca2-9cc5-a2b3ddf762f1 |  | section | Traffic
checkpoint-status | e0ad66c7-c2ab-498e-8bac-2a30d6d016b5 |  | checkpoint | Is the Traffic Management Plan on site?
checkpoint-status | ff4ad8c5-9d74-4c5a-bc39-9f2f114bee31 |  | checkpoint | Is the STMS on Site or back up STMS/TC?
checkpoint-status | 15edaa17-3d30-4d94-b330-71015275b504 |  | checkpoint | Condition of signs OK?
checkpoint-status | 304fbb56-8e98-4a00-a6ae-98e6f897ce63 |  | checkpoint | Set out to plan or modified correctly?
checkpoint-status | 0c173e04-ea97-4107-a4a5-3dc678385f48 |  | checkpoint | Has the set up been monitored as per COPTTM requirements?
checkpoint-group | 035e9cf5-f3f3-4add-ac55-c8299e342ecb |  | section | Operations
checkpoint-status | a7194f53-1354-4530-9776-7fa5724bc9a8 |  | checkpoint | Are storage areas, safe, accessible and don’t interfere with designated areas (people & plant)
checkpoint-status | 2a296afb-7743-4db3-a30b-5fb5609ad44f |  | checkpoint | Manual handling risk has been identified, assessed and managed using an established risk assessment tool
checkpoint-status | 30442d21-208f-452b-bc98-9cd5fdfcd240 |  | checkpoint | Dust suppression techniques are effective at reducing dust generation to a minimum?
checkpoint-status | a224f04c-1387-4369-b821-13573035a1f9 |  | checkpoint | Working hour restrictions are in place and being adhered to in residential areas?
checkpoint-status | 97d02155-e424-4a73-a1fb-e4caf6aaf47c |  | checkpoint | Flora and fauna controls are effective and followed
checkpoint-status | e560bc3e-4c37-4d20-88ef-cf16ef7e3c32 |  | checkpoint | Cultural & Heritage controls are effective and followed
checkpoint-status | 44b27a23-e339-4b36-aad7-87c301a2d8a6 |  | checkpoint | Waste Management controls are effective and followed
checkpoint-group | c182ba90-ab17-497d-bea1-852f4c9238e1 |  | section | Recommendations/Observations/Opportunity for Improvement/NCRs
checkpoint-status | f062f03c-9ddd-4fd8-8c7c-06752369ffdc |  | checkpoint | Recommendations as per comments
checkpoint-status | b7b080da-44c8-434b-9c20-ef0d7041898b |  | checkpoint | Observations as per comments
checkpoint-status | e0c9e66e-f42d-4a95-8f65-af6afead6476 |  | checkpoint | Opportunity for Improvement
checkpoint-status | fabfd92f-a878-44d3-b1fa-b814967551bb |  | checkpoint | NCRs
text | 5ca2d46a-cca3-5304-8fc9-f09a41eeb151 |  | textbox | NCR number and description
checkpoint-group | 8e6f6585-981b-4088-9489-5269c4f8e756 |  | section | Sign off
checkpoint-status | 044d21aa-c40b-4d1d-94b6-22f7dc242b48 |  | checkpoint | Name and signature of the author
text | 2dcf1720-107b-5a44-8ba1-b8de5e8e53bf |  | textbox | Name
text | c38a8a4b-4ca7-5446-bdfc-d0e36d448058 |  | textbox | Date
holdpoint | 2610d3ac-aa37-4955-bba7-00c8cb4392b1 |  | signoff | Signature