## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
Scope
Rows
|  | Site QA | dynamic | Belcanto - F&P SHED
Columns
|  | All holes are drilled & swarf cleaned up |  | All holes are drilled and swarf cleaned up
|  | Balustrade is installed plumb & level, meeting Belcanto's specified tolerances. |  | Balustrade is installed plumb and level, meeting Belcanto’s specified tolerances.
|  | All fixings are secure with no loose components or washers |  | All fixings are secure with no loose components or washers.
|  | Gaps within balustrade are compliant: no openings exceed 98mm, & gaps between tread/riser & bottom rail do not exceed 150mm in diameter |  | Gaps within the balustrade are compliant: no openings exceed 98mm, and gaps between the tread/riser and bottom rail do not exceed 150mm in diameter.
|  | Handrail height is within acceptable range of 900mm to 1000mm from nose of steps or finished floor level |  | Handrail height is within the acceptable range of 900mm to 1000mm from the nose of the steps or finished floor level.
|  | Installation aligns precisely with approved shop drawings |  | Installation aligns precisely with the approved shop drawings.
|  | Balustrades & handrails are shrink-wrapped & protected with tape on all corner posts & exposed sections |  | Balustrades and handrails are shrink-wrapped and protected with tape on all corner posts and exposed sections.
|  | All surfaces are free from scratches or have been professionally touched up as needed |  | All surfaces are free from scratches or have been professionally touched up as needed.
|  | Installation is complete & ready for client inspection & approval |  | Installation is complete and ready for client inspection and approval.
|  | All holes are drilled to specified depth, cleaned thoroughly & filled using correct epoxy. Work area is free of dust & debris |  | All holes are drilled to the specified depth, cleaned thoroughly, and filled using the correct epoxy. Work area is free of dust and debris.
|  | Pull testing has been conducted on 10% of rods, achieving required kN rating in accordance with PS1 specs. |  | Pull testing has been conducted on 10% of the rods, achieving the required kN rating in accordance with PS1 specifications.
|  | Handrail height is within acceptable range of 900mm to 1000mm from finished floor level |  | Handrail height is within the acceptable range of 900mm to 1000mm from the finished floor level.