## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Checklist: Stair Balustrade
section | Details
checkpoint | All holes are drilled and swarf cleaned up
checkpoint | Balustrade is installed plumb and level, meeting Belcanto’s specified tolerances.
checkpoint | All fixings are secure with no loose components or washers.
checkpoint | Gaps within the balustrade are compliant: no openings exceed 98mm, and gaps between the tread/riser and bottom rail do not exceed 150mm in diameter.
checkpoint | Handrail height is within the acceptable range of 900mm to 1000mm from the nose of the steps or finished floor level.
checkpoint | Installation aligns precisely with the approved shop drawings.
checkpoint | Balustrades and handrails are shrink-wrapped and protected with tape on all corner posts and exposed sections.
checkpoint | All surfaces are free from scratches or have been professionally touched up as needed.
checkpoint | Installation is complete and ready for client inspection and approval.
checklist | Checklist: Void Balustrade
section | Details
checkpoint | All holes are drilled to the specified depth, cleaned thoroughly, and filled using the correct epoxy. Work area is free of dust and debris.
checkpoint | Pull testing has been conducted on 10% of the rods, achieving the required kN rating in accordance with PS1 specifications.
checkpoint | Balustrade is installed plumb and level, meeting Belcanto’s specified tolerances.
checkpoint | All fixings are secure with no loose components or washers.
checkpoint | Gaps within the balustrade are compliant: no openings exceed 98mm, and gaps between the tread/riser and bottom rail do not exceed 150mm in diameter.
checkpoint | Handrail height is within the acceptable range of 900mm to 1000mm from the finished floor level.
checkpoint | Installation aligns precisely with the approved shop drawings.
checkpoint | Balustrades and handrails are shrink-wrapped and protected with tape on all corner posts and exposed sections.
checkpoint | All surfaces are free from scratches or have been professionally touched up as needed.
checkpoint | Installation is complete and ready for client inspection and approval.
checklist | Checklist: Main Stair
section | Details
checkpoint | All holes are drilled and swarf cleaned up
checkpoint | Balustrade is installed plumb and level, meeting Belcanto’s specified tolerances.
checkpoint | All fixings are secure with no loose components or washers.
checkpoint | Gaps within the balustrade are compliant: no openings exceed 98mm, and gaps between the tread/riser and bottom rail do not exceed 150mm in diameter.
checkpoint | Handrail height is within the acceptable range of 900mm to 1000mm from the nose of the steps or finished floor level.
checkpoint | Installation aligns precisely with the approved shop drawings.
checkpoint | Balustrades and handrails are shrink-wrapped and protected with tape on all corner posts and exposed sections.
checkpoint | All surfaces are free from scratches or have been professionally touched up as needed.
checkpoint | Installation is complete and ready for client inspection and approval.