## ITP Cover Page
Master Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: DN:1208 - 900 - Rev C
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | SH1/29 Intersection Upgrade |  |  |  |  | ITP Number: |  |  | 900
Project Number: |  |  | DN:1208 |  |  |  |  | ITP Status: |  |  | Draft
ITP Description: |  |  | Concrete and Structures Inspection and Test Plan |  |  |  |  | Revision: | 1000 |  | C
Contract Number: |  |  | 7991 |  |  |  |  | Drawing Sets:
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification:
Quality Specified: |  |  | Z8
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 2025-02-25 |  | Michael Randall |  | First Draft Hard Landscape ITP |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | 2025-03-18 |  | Michael Randall |  | Updated the description of the exposed aggregate to align with specific aggregate names. Removed sealer as it is no longer required by NZTA. Changed the verifying document for the set-out from the survey record to site photos |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | Draft for Approval | 2025-03-19 |  | Michael Randall |  | Incorporated comments from Stantec |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Master Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: DN:1208 - 900 - Rev C
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
1.01 | Materials
1.01.1 | 20 MPa Concrete | Concrete shall be certified 20Mpa plant mix and comply with NZS3109 | Drawing L105 | Mix Design | Prior to use |  | HP | ENG
1.01.2 | 20 MPa Exposed Aggregate Concrete: Grey, Black & Brown | 20MPa Uruti exposed aggregate. Allow 4KG/m3 black oxide | Drawing L105 | Mix Design | Prior to use |  | HP | ENG
1.01.3 | 20 MPa Exposed Aggregate Concrete: Black & Dark Grey | 20MPa Bulls exposed aggregate. Allow 8KG/m3 black oxide. | Drawing L105 | Mix Design | Prior to use |  | HP | ENG
1.01.4 | 20 MPa Exposed Aggregate Concrete: Brown | 20MPa Mangatangi exposed aggregate. Allow 8KG/m3 black oxide. | Drawing L105 | Mix Design | Prior to use |  | HP | ENG
1.01.5 | 1 MPa Mortar around Thriebeam barrier | Submit details of the product type and specification | Drawing L105 | Mix Design | Prior to use |  | HP | ENG
1.01.6 | Greywacke Stone | Submit details of the product type and specification | Drawing L105 | Datasheet | Prior to use |  | HP | ENG
1.01.7 | Hinuera Stone | Submit details of the product type and specification | Supplier | Datasheet | Prior to use |  | HP | ENG
1.01.8 | Penetrating Sealer | Submit details of the product type and specification | Supplier | Datasheet | Prior to use |  | HP | ENG |  |  |  | Sealer no longer required
1.01.9 | Thriebeam Barrier | Submit details of the product type and specification | Drawing L105 | Datasheet | Prior to use |  | HP | ENG
SECTION 2 – CONSTRUCTION ACTIVITY
2 | Setting out/Compaction
2.00.1 | Setting out | The Contractor shall be responsible for the correct setting out of all works, including set out of the various patterns and barrier | IFC drawing | Site photos | Each Pour |  | H | PE |  |  |  | Although construction of base below concrete is covered elsewhere, as a minimum this ITP should include double-checks to confirm the surface is ready (i.e. compaction/CBR & levels) if the prep work itself is not captured in this ITP. | Added line item 2.00.3
2.00.2 | Setout Approval | On completion of the set out of the hardlandscaping, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. | Survey records | Onsite inspection | Each Pour |  | H | PE
2.00.3 | Compaction of base | The base below the concrete shall be tested using a Clegg Hammer and must have a minimum CBR value of 10. The CBR value shall be taken as 0.07 (CIV)² | RITS Drawing 3-60: Roundabout Details. RITS:3.8.3.3 Clegg Hammer | Field Sheets | Before concrete construction |  | H | PE
2.01 | Construction
2.01.1 | Exposed Aggregate Concrete | All exposed aggregate concrete to be at a depth of 125mm. Saw cuts to be 1/3 the depth of the concrete and space no greater than 3M apart | Drawing L303 | Site photos | During construction |  | I | SE
2.01.2 | Greywacke Stone: Ø100-200mm | Placement & Embedment: Embed each stone at least ½ of its height into the concrete. Secure stones with their wider side set firmly in concrete. Spacing & Arrangement: Place stones closely together, ensuring gaps do not exceed 50mm. Surface Finish: Allow smoother or rounded sides to be exposed where possible. Protrusion Above Concrete Surface: Ensure stones protrude 25-50mm above the finished concrete level. | Drawing L303 | Site photos | During construction |  | I | SE
2.01.3 | Greywacke Stone: Ø50-100mm | Placement & Embedment: Embed each stone at least ½ of its height into the concrete. Secure stones with their wider side set firmly in concrete. Spacing & Arrangement: Place stones closely together, ensuring gaps do not exceed 50mm. Surface Finish: Allow rugged sides at the surface where possible. Protrusion Above Concrete Surface: Ensure stones protrude 25-50mm above the finished concrete level. | Drawing L303 | Site photos | During construction |  | I | SE
2.01.4 | Hinuera Stone | The Hinuera stone shall have a split face look (not a sawn look), laid in a mosaic interlocked pattern. The stones must be mortared in place and securely attached to the concrete plinth. Additionally, a penetrating sealer recommended by the Hinuera stone supplier shall be applied, with the product type and specification to be provided by the supplier. | Instruction from ER | Site photos | During construction |  | I | SE
2.01.5 | Thriebeam Barrier | The contractor shall submit a completed and signed installation check list | Ingal Civil Products | Check list | During construction |  | I | SE |  |  |  | No reference around the requirements for hard landscaping interfacing with the Thrie beam barrier posts, as specified in NTC-98 | Added line item 2.01.6 to cover this
2.01.6 | Asbuilt | All construction as per Drawing L105 |  | Survey report |  |  | H | PE
2.01.7 | Thriebeam Barrier - Posts | A minimum 400mm-wide ring of 1MPa mortar shall be placed around the RAB to fully encase the Thrie Beam posts within this material. A minimum clearance of 200mm shall be maintained between the post and the inner landscaping interface. | NTC-98 | Site photos | During construction |  | I | SE