## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
384e2b71-88ca-409a-b7ae-216b21ff32e6 | checklist | ITP - Hard Landscape - 900 - Rev C | itp | ITP - Hard Landscape - 900 - Rev C
178a0b55-0ada-4d05-9d86-3ab0a04ab272 | section | 1.01 - Materials
37d35481-b6a5-4fc8-8928-0917a357a9f8 | checkpoint | 1.01.1 - 20 MPa Concrete
bc25cf27-b835-547d-b500-f122e81cd8bd | note | Acceptance / Conformance Criteria - Concrete shall be certified 20Mpa plant mix and comply with NZS3109
d954e887-af91-5c80-934e-63652450f1ec | note | Standard / Specification - Drawing L105
a7bed055-4402-5989-aa1a-0f7d40f4f724 | note | Verifying Document - Mix Design
24da3b74-1d9f-5022-b530-1a078d54677e | note | Frequency - Prior to use
1ba2c494-0abb-5b80-8866-34c0e574a938 | note | Verification Activity: Activity - HP
7f835e94-c466-50a2-a038-8ddf5452e7d7 | note | Verification Activity: By - ENG
38540bb0-ff97-4288-8c34-2963f37cc770 | signoff | AUTHORITY HOLDPOINT
7f7b6484-5be5-4d6a-beed-a6c4ef6100e1 | checkpoint | 1.01.2 - 20 MPa Exposed Aggregate Concrete: Grey, Black & Brown
c11cfecb-0cb7-52a9-8588-25ad5e2367a8 | note | Acceptance / Conformance Criteria - 20MPa Uruti exposed aggregate. Allow 4KG/m3 black oxide
5fce7b0e-f32d-5989-b25e-ec44a639e50c | note | Standard / Specification - Drawing L105
1a322b48-8086-58f3-a939-11a882941161 | note | Verifying Document - Mix Design
c2313b5e-80bb-5833-b0cf-7403f533ebee | note | Frequency - Prior to use
bc57af34-e7e2-533f-8e14-e1d9285299d7 | note | Verification Activity: Activity - HP
25b696af-665b-57e4-9071-1438b95984fe | note | Verification Activity: By - ENG
33c53fda-328c-47dc-a794-15311c1a0e2c | signoff | AUTHORITY HOLDPOINT
4a9cd0dc-5399-4ca6-a5fe-3ee8352f1fec | checkpoint | 1.01.3 - 20 MPa Exposed Aggregate Concrete: Black & Dark Grey
4a8bec32-225b-5e9b-bee7-fe542a8affaa | note | Acceptance / Conformance Criteria - 20MPa Bulls exposed aggregate. Allow 8KG/m3 black oxide.
d027c3f6-ec0c-5a80-bdef-ea6b5b7457a8 | note | Standard / Specification - Drawing L105
d37d568c-92ab-5d1e-827f-dfa32ff1fc2d | note | Verifying Document - Mix Design
1ab36c39-4ae3-538d-8732-998b2de2813a | note | Frequency - Prior to use
f61da54a-5d44-5a7f-9035-104daa4756da | note | Verification Activity: Activity - HP
b00db705-3a00-573a-b128-341d4fc7f853 | note | Verification Activity: By - ENG
e7986890-4ee3-4fc6-82e3-dcccea986abc | signoff | AUTHORITY HOLDPOINT
d59e64bf-3793-4cae-88fc-45177b70594a | checkpoint | 1.01.4 - 20 MPa Exposed Aggregate Concrete: Brown
22ae24c8-2898-56fc-a7f8-35f277ab59aa | note | Acceptance / Conformance Criteria - 20MPa Mangatangi exposed aggregate. Allow 8KG/m3 black oxide.
d9338002-7164-592e-81ba-1c7d947af8e1 | note | Standard / Specification - Drawing L105
75715a90-2d4b-5e1f-b5fc-ce9d8d446b90 | note | Verifying Document - Mix Design
1b0f8f42-eaac-59fb-9848-7b8c1eae10ef | note | Frequency - Prior to use
0738a7d9-3fb5-5597-aee5-20ba652ec5df | note | Verification Activity: Activity - HP
119d0b3e-7823-52e2-82be-caedc1376e4f | note | Verification Activity: By - ENG
c70c73db-2c6e-4251-b81b-21daf50bbfac | signoff | AUTHORITY HOLDPOINT
5f4f504d-f2b5-4e63-ad85-bcc351238d3f | checkpoint | 1.01.5 - 1 MPa Mortar around Thriebeam barrier
b901a4dd-af28-5ced-881c-170310b5b54c | note | Acceptance / Conformance Criteria - Submit details of the product type and specification
ad32dcbc-0a4f-5f6c-8aac-8b1261b711ec | note | Standard / Specification - Drawing L105
aef487dc-b883-55cd-bab3-0f75422952c8 | note | Verifying Document - Mix Design
262ab0c7-6aa3-55b3-acf2-6cb1fbcfd1b2 | note | Frequency - Prior to use
740af957-1c67-5ea3-ac17-18ecc3362885 | note | Verification Activity: Activity - HP
43b62169-051e-51d3-a70c-ea5542fdfccb | note | Verification Activity: By - ENG
c2887cbe-1c22-4c61-bef4-111f6469bb46 | signoff | AUTHORITY HOLDPOINT
710d5a16-45b9-4cbc-bb2c-0dcb13f6c67c | checkpoint | 1.01.6 - Greywacke Stone
63ced2f7-24a9-5ec3-9b16-f045daa83f0e | note | Acceptance / Conformance Criteria - Submit details of the product type and specification
cd44de30-06b6-52b6-aad2-180e666c2a92 | note | Standard / Specification - Drawing L105
3013f559-41ee-51f5-b6f1-3032f6648e7b | note | Verifying Document - Datasheet
f88f9593-3654-5efd-a29d-4f66e37292c4 | note | Frequency - Prior to use
f3b4e2ba-5869-5bfe-96e6-7bf8ca3f2d1b | note | Verification Activity: Activity - HP
e0271be4-2773-5dee-b152-48744de37e5b | note | Verification Activity: By - ENG
68e4f59a-b02b-4e18-bd9e-c0e2b99268b5 | signoff | AUTHORITY HOLDPOINT
7188cde3-8499-4cac-80e6-970d41b30acc | checkpoint | 1.01.7 - Hinuera Stone
92f50983-21d3-5299-b84d-286f59b644d7 | note | Acceptance / Conformance Criteria - Submit details of the product type and specification
e3815557-729b-5a60-aef6-394d19da55f7 | note | Standard / Specification - Supplier
c884b77e-02fb-50d6-b1d2-dff7d2b50429 | note | Verifying Document - Datasheet
fcb98869-b79b-5411-8b2b-4c13200c2ef9 | note | Frequency - Prior to use
b5e91205-9c05-59df-9d76-9bf79b4536ee | note | Verification Activity: Activity - HP
a5144b18-6a1e-5d00-be50-57525362c13f | note | Verification Activity: By - ENG
6c84263d-6f52-4f3b-9024-e8ca6f47744b | signoff | AUTHORITY HOLDPOINT
6226619c-2c20-4f54-9a40-ce52b9d0286a | checkpoint | 1.01.9 - Thriebeam Barrier
9d4001fe-9dd0-5aff-be26-a0b7ac6a4b73 | note | Acceptance / Conformance Criteria - Submit details of the product type and specification
ed4c82f1-9e26-58fa-b0c0-dc8a2af6dc8c | note | Standard / Specification - Drawing L105
aa75b3b9-7a73-5ed1-b0fe-9c25020ae539 | note | Verifying Document - Datasheet
cd783fad-289e-5daf-ac51-6422f39a62fd | note | Frequency - Prior to use
3cee61e6-f417-507e-9dda-9b2576fdcfb5 | note | Verification Activity: Activity - HP
1648ee46-ad34-571d-825e-504dd906edaf | note | Verification Activity: By - ENG
701ff277-6676-4ec5-934b-886374cb71e3 | signoff | AUTHORITY HOLDPOINT
fedb869f-231f-40fa-aeb4-1fa3dff21a5a | section | 2.00 - Setting out
1188840c-3ef2-4568-9b41-86305386f4b3 | checkpoint | 2.00.1 - Setting out
674927ec-d53a-518e-bdc5-2b0d0782ecc3 | note | Acceptance / Conformance Criteria - The Contractor shall be responsible for the correct setting out of all works, including set out of the various patterns and barrier
cb5532dd-41a9-568c-b38e-613514b0970c | note | Standard / Specification - IFC drawing
c3d639f1-b558-59a1-8a60-268ce20d867b | note | Verifying Document - Site photos
9da7c9fa-45a2-59c3-9f54-fe57421209fc | note | Frequency - Each Pour
b3f4b5c6-5949-5e91-9e8d-e8bf2e5a3125 | note | Verification Activity: Activity - H
cf42b7a8-367b-5054-8def-83263f951987 | note | Verification Activity: By - PE
c16747f4-c986-4442-9a72-95216309669a | checkpoint | 2.00.2 - Setout Approval
f941d826-baad-50ca-8b9a-dddcd39f9edf | note | Acceptance / Conformance Criteria - On completion of the set out of the hardlandscaping, the Contractor shall immediately advise the Engineer for the purposes of checking the set out.
dd27d1a5-b97f-53f6-9de5-b03bd2614b0f | note | Standard / Specification - Survey records
793a66f9-68cf-52a3-b878-c4d441b7e577 | note | Verifying Document - Onsite inspection
bd358fea-a2b1-5122-8ca4-a37b9ad18e36 | note | Frequency - Each Pour
6fed05b6-5b47-545f-aded-34b0d5f9b3fe | note | Verification Activity: Activity - H
0dd52ff5-eb69-51bf-b712-4a0157dfc477 | note | Verification Activity: By - PE
| checkpoint | 2.00.3 - Compaction of base
| note | Acceptance / Conformance Criteria - The base below the concrete shall be tested using a Clegg Hammer and must have a minimum CBR value of 10. The CBR value shall be taken as 0.07 (CIV)²
| note | Standard / Specification - RITS Drawing 3-60: Roundabout Details. RITS:3.8.3.3 Clegg Hammer
| note | Verifying Document - Field Sheets
| note | Frequency - Before concrete construction
| note | Verification Activity: Activity - H
| note | Verification Activity: By - PE
7dfaeaff-79c6-4181-9eb3-52fd99129624 | section | 2.01 - Construction
fd13d42a-1ace-43e4-8345-8267ba5dddef | checkpoint | 2.01.1 - Exposed Aggregate Concrete
45b1511d-2cc9-51b8-ac1f-00c84e8cdda1 | note | Acceptance / Conformance Criteria - All exposed aggregate concrete to be at a depth of 125mm. Saw cuts to be 1/3 the depth of the concrete and space no greater than 3M apart
e6b7b779-18cb-58b1-8b26-fa773d312f6a | note | Standard / Specification - Drawing L303
5da52dd7-83b9-5486-ae93-6c9bd284b274 | note | Verifying Document - Site photos
c13b479d-3a83-5e67-b8f2-cba3baf759f8 | note | Frequency - During construction
bb1a54c0-aef0-5af3-bdfc-222392490b43 | note | Verification Activity: Activity - I
6c3c0bc7-1458-5c97-89ea-7d40c7a4784c | note | Verification Activity: By - SE
b44835c0-f0c5-400d-ab74-83b4e4e3a76e | checkpoint | 2.01.2 - Greywacke Stone: Ø100-200mm
405a7f0e-b220-5ba5-bf51-eac0800f6ec2 | note | Acceptance / Conformance Criteria - Placement & Embedment:
216d2949-110e-564c-a7b3-a98b787af2b6 | note | ○ Embed each stone at least ½ of its height into the concrete.
c4cb1924-3c60-565a-9830-4005dd3bca6c | note | ○ Secure stones with their wider side set firmly in concrete.
e6761a26-15c0-5216-a56d-6134273afeac | note | Spacing & Arrangement:
002e4d81-00fd-5ffb-8504-708c33c01652 | note | ○ Place stones closely together, ensuring gaps do not exceed 50mm.
da76370b-a1a9-57ac-8e4f-1784e9cfc004 | note | Surface Finish:
37a4c82f-1809-5927-b86b-bba3a6eae69b | note | ○ Allow smoother or rounded sides to be exposed where possible.
ec57a27e-dec1-58e9-bc39-14a24e57b942 | note | Protrusion Above Concrete Surface:
e28a75b0-a069-506e-a5aa-bda3fa60ac90 | note | ○ Ensure stones protrude 25-50mm above the finished concrete level.
eb532d54-f1ec-501d-86d0-315a76c2bb19 | note | Standard / Specification - Drawing L303
1e242bde-388b-553f-9aa4-34b92434acc7 | note | Verifying Document - Site photos
7a305bc2-5c0d-5d47-baf6-6facfa4428ce | note | Frequency - During construction
7cca6445-8393-5b28-adcf-8a12d68e81a0 | note | Verification Activity: Activity - I
a6fd9e5d-88b9-5c81-b8e0-0524d93fab81 | note | Verification Activity: By - SE
bc46e097-569b-4e8d-ae6f-24dc3743d16f | checkpoint | 2.01.3 - Greywacke Stone: Ø50-100mm
00ca6c17-366b-5c87-837a-811004d834f3 | note | Acceptance / Conformance Criteria - Placement & Embedment:
933449f9-0ef2-5733-9a1c-5f6ce3547a64 | note | ○ Embed each stone at least ½ of its height into the concrete.
5579029f-e674-5ed1-8167-48a83eb0bb49 | note | ○ Secure stones with their wider side set firmly in concrete.
248428ba-030f-57a6-b75a-4870c3555ad8 | note | Spacing & Arrangement:
544887fa-83fc-50d3-b6eb-29ecf985a73e | note | ○ Place stones closely together, ensuring gaps do not exceed 50mm.
d12ee93a-7735-57f9-ac60-3d5219af1180 | note | Surface Finish:
21ae4e87-b53a-5f19-a8c8-a931dec49c59 | note | ○ Allow rugged sides at the surface where possible.
11bf445a-31de-5256-a2ab-b9669388941b | note | Protrusion Above Concrete Surface:
9af772eb-5338-5418-88e4-895750279bcd | note | ○ Ensure stones protrude 25-50mm above the finished concrete level.
b4a8598a-b5ab-5013-a692-d7598d2aebb8 | note | Standard / Specification - Drawing L303
32fe1652-121c-5fa8-a13f-7796f821c90b | note | Verifying Document - Site photos
b5cfe1bd-7da8-5416-ae1b-8e357c9b1efd | note | Frequency - During construction
994475cd-fe71-58d9-8a65-0df4cfa264ee | note | Verification Activity: Activity - I
36bec739-46c5-5193-b610-2868cf92cf0a | note | Verification Activity: By - SE
a1f6430c-6d85-4afe-8aae-d4261cad34ba | checkpoint | 2.01.4 - Hinuera Stone
31cc1fc4-c99c-5b0f-9100-67f68f8f674b | note | Acceptance / Conformance Criteria - The Hinuera stone shall have a split face look (not a sawn look), laid in a mosaic interlocked pattern. The stones must be mortared in place and securely attached to the concrete plinth. Additionally, a penetrating sealer recommended by the Hinuera stone supplier shall be applied, with the product type and specification to be provided by the supplier.
a82aae3f-c08d-5296-976e-4840711e2101 | note | Standard / Specification - Instruction from ER
a8da6747-548e-5a9b-8a99-e3c722dd784d | note | Verifying Document - Site photos
0ed83d56-4b45-5bd5-b8cf-f9fe3582286a | note | Frequency - During construction
dfbfaeaf-45cc-55f2-a97e-93b31ba5b374 | note | Verification Activity: Activity - I
1d22c92d-6943-54bf-a822-30ad1e868ff1 | note | Verification Activity: By - SE
1cff72e4-ef5f-4f21-ad8f-7e5b19187d0b | checkpoint | 2.01.5 - Thriebeam Barrier
787831e2-a59b-5a64-86c1-9cc09ff79e12 | note | Acceptance / Conformance Criteria - The contractor shall submit a completed and signed installation check list
96cdbf15-47a3-5642-b31a-0248b0d9b4cf | note | Standard / Specification - Ingal Civil Products
d8c2fec7-08da-5b81-be28-ce551f1fb2ab | note | Verifying Document - Check list
0cc2f0a1-f274-5625-8c2d-2069f7cd971f | note | Frequency - During construction
b8a64217-7ba6-53d2-8341-80602581e1e1 | note | Verification Activity: Activity - I
859a71bf-c850-54d9-88ba-1ff15333378a | note | Verification Activity: By - SE
fba2d775-c227-4cc9-8bd9-5c2fc0bd4155 | checkpoint | 2.01.06 - Asbuilt
d1819db7-69fe-5cb0-b1b9-40a17842b250 | note | Acceptance / Conformance Criteria - All construction as per Drawing L105
d230cb1b-8036-56f6-b6b9-a9f1d59deae1 | note | Verifying Document - Survey report
8c91d0f6-8f39-55d9-bef3-5620efbf3be3 | note | Verification Activity: Activity - H
ad02f9e5-ce1a-5329-bfc9-aee63933e36c | note | Verification Activity: By - PE
| checkpoint | 2.01.07 - Thriebeam Barrier - Posts
| note | Acceptance / Conformance Criteria - A minimum 400mm-wide ring of 1MPa mortar shall be placed around the RAB to fully encase the Thrie Beam posts within this material. A minimum clearance of 200mm shall be maintained between the post and the inner landscaping interface.
| note | Standard / Specification - NTC-98
| note | Verifying Document - Site photos
| note | Frequency - During construction
| note | Verification Activity: Activity - I
| note | Verification Activity: By - SE
36d90e3b-4aef-4341-a68c-ba1518c3a16e | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
04fb8bfb-ae4d-579b-874a-06562abc962d | textbox | Contractor's Rep Name:
c63b4205-4ca9-5757-9208-7a9e75bab42c | textbox | Engineer's Rep. Name:
560ed30f-e455-5464-a09b-e91c2ca3560f | date | Date:
65cd46d3-fe7a-44f7-9beb-5d85c79e9751 | signoff | Add Signature