## Master List Templates
Id | Type | Name | Values | Prompting Name
c755ba6d-cc14-48b7-b857-ac5c6c2947c9 | checklist | Carpet Tiles Installation |  | QA Carpet Tile Installation :
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3e5897ea-15f3-46bf-b8f4-09ec59218523 | checkpoint | Carpet tile range and colour check and confirmed
ca7af71d-548d-4271-82d5-f91e1eb21437 | checkpoint | Area / Location to receive carpet tiles
0b919c41-9165-5e29-816f-07ff4a87f876 | textbox
3532ecac-75ae-4ea3-854d-dc05161964e5 | checkpoint | Floor prep required ?
91ba2909-8cb2-5a4b-aedb-b40d54d1bd25 | textbox
169e1a52-41ac-4c26-9a53-294cfc40585c | checkpoint | Installation direction confirmed ?
1d613fa5-4aa9-4b5d-92b7-441fd2b3f438 | checkpoint | Setting out lines square ?
02ce727b-a5dd-4c24-8eda-32c3a18156aa | checkpoint | Are all edges free from fraying ?
6192cd56-5fa2-495f-919d-a7d392832aa1 | checkpoint | Are all edges cut neat and straight?
7ae6fe07-6a0a-41ca-bec2-53b8e2010ba7 | checkpoint | Carpet tile adhesive used
7af8d0dc-ff0e-56dd-ba5a-1931b6cc8f31 | note | x1 Pictures
d2dae3fd-f1bc-4394-85d7-b6acded2717d | checkpoint | Completed Carpet Tile installation
9a74155b-f21a-5bf5-8025-8359e41031ef | note | x4 Pictures
c062a656-2501-4b33-9ade-fb586f853bfd | checkpoint | Check and clean any excess adhesive in joints, on wall, or skirting
139fcae5-bae5-43c3-bfca-24d9c03d6d2e | checkpoint | Transition between other floor covering level and flush
1606949e-9f0a-4713-83ac-d9e56454bdf1 | checkpoint | Phase completed with no damage ?
5608e008-a164-4b9c-acc1-422397f875d0 | signoff | Please signoff / request sign off
4745a1ad-b5d0-4104-90de-88989b613471 | checklist | Mercy Wall Vinyl remedial work |  | Mercy Wall Vinyl remedial work
27f401ef-9f28-4fb3-8a3d-3c4829ac926a | section | Details
fe75772b-3e4a-4edd-a973-4c59ada06f9d | checkpoint-no-value | Room details Details
2aca2292-a053-5319-b5ec-b7b2ca81650c | date | Date
f0deb28a-763c-4ad3-96d0-7e563b48068a | checkpoint | Take Pictures of Vinyl 2 images per wall before uplift
543c7016-7d1f-491c-8192-d368dec893eb | checkpoint | Take Pictures of wall after before uplift (2 per side)
04445d50-08df-43e2-b1f0-7427e44d5177 | checkpoint | Is new waterproodfing required? Yes / No
2dbd0e48-e1bc-429f-9549-fa05730eee73 | checkpoint | Apply mapeband and 1st coat of Aquadefense
ee3dc46f-221d-4f70-bda0-444524c17695 | checkpoint | Apply 2nd coat of Aquadefense
c114efbc-ff73-4506-8275-78564a61409d | checkpoint | Skim floor with Planiprep SC
c856b93e-c74b-42e8-ba27-167044585081 | checkpoint | Skim Wall with Planiprep SC
05ab753c-0093-44a2-82e3-9be9ec6885c3 | checkpoint | Disk floor and wall ready for Vinyl
40c41e6e-0df1-460b-bb00-d4f5b255d1e1 | checklist | NZ Living - Balcony |  | NZ Living - Balcony
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7ce3de8b-ebfb-49c8-abbf-cbf5607eec15 | checkpoint | Details
3b66c41c-5832-58af-b30d-aab645656b94 | textbox | Block Number
2a2c7c17-e211-5282-a8a1-1ddd9c192777 | textbox | Level Number
bb56e98e-7d19-5fa2-b1d5-e93cebdb9d01 | textbox | Unit Number
f097b912-f1dc-4300-b21b-1fef39f3ab3d | checkpoint | Clean Grind - 30 DISK
259c8eb9-6c3b-59c3-95e2-5979aaf689e5 | note | x 1 Picture
f90a54ae-fe66-44fe-ae1e-96c13ea700cc | checkpoint | Dremel tool in corners and below ranch slider
a81d49a5-c168-5aac-97be-6447ced9f159 | note | x 1 Picture
1fc5ca35-8d7c-4e24-8f0f-e82ebbb2e561 | checkpoint | Polish Grind - 80 DISK
28c00610-8bc0-580e-b15e-e12e33a12bbb | note | x 1 Picture
c213c337-a37e-4162-ac3f-a82e7c29b575 | checklist | NZ Living - Bathroom per unit |  | NZ Living - Bathroom per unit
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ab05fcbb-1748-47e3-90b8-663aced12aa0 | checkpoint | Details
62c4610d-546b-585f-8d64-9c81583e0754 | textbox | Block Number
17fe428e-02a3-53eb-847a-5cea3f9a665e | textbox | Level Number
67503979-e505-5611-b446-1f2a9fed8b97 | textbox | Unit Number
34f359bc-c678-4db5-a02b-7b820bb78df7 | checkpoint | Clean Grind
b71261fa-66d5-54cf-9442-b44abfbd6d43 | note | x 1 Picture
51f08809-5d6b-49bf-9e21-ac16205653f5 | checkpoint | MAPEI AQUA DEFENCE 1st Coat
17b9648e-ff44-547d-9549-0865cd103a94 | note | x 1 Picture
305989d0-a2d5-4cd6-af4c-c69fda218039 | checkpoint | MAPEI AQUA DEFENCE 2nd Coat
69dc96c5-49fe-5c3b-a659-db695343b86b | note | x 1 Picture
cc28aa46-f819-4e47-bc81-269b791d0d43 | checkpoint | Mapei band easi 400x400 waterproof membrane
68a86f11-03af-5084-b331-bd4339feeb46 | note | x 1 Picture
b82ed121-16e5-4a53-b617-45c5e238a3d2 | checkpoint | Apply Mapei Eco prim-T primer
17d3bc52-d6c4-5fd7-ba07-532d4eb532a4 | note | x 1 Picture
445969d4-6478-43e6-aac0-0856032789b0 | checkpoint | Apply smoothing screed compound
cfd1b85b-aacc-5b1e-8831-74929dc9ee9a | note | x 1 Picture
6465b791-ab83-42d4-9acf-0a8fcc011dc1 | checkpoint | 2mm Rubber underlay 1st floor and up only
ec704735-8bbf-4949-a04f-0e30f374a9b5 | checklist | NZ Living - Carpet |  | NZ Living - Carpet
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
22b8558b-d24b-4f87-96c0-1425124b0867 | checkpoint | Details
110fb50b-77c3-55a7-9a1b-a18168dbae8d | textbox | Block Number
713dd5e4-7298-511d-92d2-1821d2a70a59 | textbox | Level Number
1c9aa9ea-2105-5e9c-9d08-20139ba03453 | textbox | Unit Number
4303f131-278b-5ef8-89ee-87c46b2d719b | textbox | Range and colour fitted
57123ab1-6a6c-5633-bf40-30a3191ae492 | note | x 1 Picture
4e386b45-18dd-4fd3-bf69-e88705b7a254 | checkpoint | Underlay install
20fdefdb-12f3-599a-98aa-35acc713423c | note | x 1 Picture
964db42b-e47b-4f06-8a8a-e99a2391bb0e | checkpoint | Door transition trim between vinyl and carpet
80230ffc-8bb3-5fcf-b4a2-c764f8583e27 | note | x 1 Picture
9895d920-20e4-49fb-be08-3e384e5ff0b4 | checkpoint | Assure grippers are pushed down with bolster!
c39b79f5-3f49-5326-8e57-a27f3bf57b62 | note | x 1 Picture
07fa7299-d18b-49ec-8cb9-63da78649569 | checkpoint | Completed carpet install
e7c72250-d848-5b13-8fb4-2983b7e62fd3 | note | x 4 Pictures
a60ce3bb-924d-4201-a939-9ebc9fa553c8 | checklist | NZ Living - First floors and up units |  | NZ Living - First floors and up units
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3e7892ab-e67b-4652-811e-da7440c22f55 | checkpoint | Details
6fb61526-62f6-569c-af18-8ecc704d6c13 | textbox | Block Number
85365474-8916-57d4-bbad-b14755783f16 | textbox | Level Number
89bce13e-fbe1-51b6-a817-014fa2ba1ba2 | textbox | Unit Number
dac7de8b-001f-4b89-8983-12cc3e350f67 | checkpoint | Clean Grind subfloor
375b1547-2f5c-5cee-b550-9d3a96dd475c | note | x 1 Picture
004b2fbd-6ca3-4b5e-bc5d-5c8ebf28c3fe | checkpoint | Fine finish screed preparation
a3680f3e-520f-5687-9112-f8dcec0d5476 | note | x 1 Picture
a904a498-7457-405b-a9d7-de24b186d978 | checkpoint | Ramp at ranch sliders
d91a104c-d4dd-59e1-aca3-6c1273c90170 | note | x 1 Picture
ce60c6ac-c924-4c97-8bdd-8aa5b23844d2 | checkpoint | Polyvac prior vinyl
57421dfe-1a8b-53e7-a6d7-70e2eff4ba1c | note | x 1 Picture
b8b13317-cb27-48d7-a1fd-96dca8c94efb | checkpoint | Undercut bathroom door frame for LVT
1ede50d0-025b-5cf4-b87c-1021a017acb2 | note | x 1 Picture
9dd4dc33-0e44-4003-bd4e-704e8e1bbef9 | checkpoint | Bathroom vinyl adhesive 68T
355b04bd-89b2-5f1a-bb58-9d142e8abf03 | note | x 1 Picture
b7b93896-11c1-4462-9fac-5145f3977edd | checkpoint | Completed vinyl plank install to bathroom
9a8106ef-e130-5b7a-8088-dffb3bfab866 | note | x 1 Picture
981badb4-3c25-419b-9a4a-ea91179f88f4 | checkpoint | Fit regupol underlay prior vinyl with KE2000 (Sub supply)
bcefa41d-f009-5450-a543-98d530e380bf | note | x 1 Picture
03c528e1-5765-4972-9f42-31fcfa2a2c8d | checkpoint | LVT neatly but up against skirting
81f4f70f-0765-5fbf-8d99-824ae2cb5dec | note | x 1 Picture
5f6eec5c-80ea-4047-86b8-f693b2d79a65 | checkpoint | Vinyl plank completed installation pictures
029549b8-b3b0-51fd-ab16-831277f65782 | note | x 2 Pictures
64c32e05-f04b-4ef2-8b9e-8fee99c9fdc6 | checkpoint | Received and installed drain waste
ea2f1541-a238-56d7-8e5c-621fe3862031 | note | x 1 Picture
5ae53c51-f74c-4b0b-bc92-1bce42b0640d | checklist | NZ Living - Ground floor units |  | NZ Living - Ground floor units
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
48f8aec8-fc05-49c1-aba5-8187ebcb93da | checkpoint | Details
89f450d3-8cfd-58f5-ae7c-a7bf59fc51de | textbox | Block Number
4ef5ae9a-53db-529f-a5ed-d84b9f970025 | textbox | Level Number
7d60b79e-0042-5143-ac99-efacd5711d90 | textbox | Unit Number
2d1c327b-7d1d-4fc6-84bc-961cb24b96c5 | checkpoint | Moisture check
4f4621d1-d2b0-5a3b-a91f-daf29e0d07f1 | note | x 2 Pictures
42c0fdfd-d555-4289-8c32-697a29674910 | checkpoint | Clean Grind subfloor
4644957c-12a8-5d9f-9f08-ec6d2260e839 | note | x 1 Picture
237594b2-ede1-4b8d-b254-19bcc55fd3bb | checkpoint | Fine finish screed preparation
fa63d555-f08a-535e-b9c2-51bc42e8c212 | note | x 1 Picture
bb8e3122-a053-4485-bada-41fd0ab508a1 | checkpoint | Ramp at ranch sliders
b718fbd0-5099-5ff2-b478-6456e0a6b11b | note | x 1 Picture
be244f02-fe81-4634-8ffc-26e33c9db0b1 | checkpoint | Polyvac prior vinyl
857fa70e-f7b8-5818-b66f-f2d28cca5080 | note | x 1 Picture
3ad04569-0997-4a2c-971f-08e10230d495 | checkpoint | Undercut bathroom door frame for LVT
d4d94bd7-bc00-583a-8c69-65d68b7f0226 | note | x 1 Picture
2ff1608a-74f3-41d2-aeee-f08ba27b8596 | checkpoint | Bathroom vinyl adhesive 68T
f7915530-9b84-537f-a5a8-b087ac2c9f05 | note | x 1 Picture
c42dfadf-3415-4f3c-9fd5-e743552cd225 | checkpoint | Completed vinyl plank install to bathroom
c2852327-6e67-50c9-86ec-8f620e652d92 | note | x 1 Picture
d6936fa0-a258-48fd-95a4-e14dd1111984 | checkpoint | LVT neatly but up against skirting
19d42c2c-eed3-5879-bf12-3078158318bf | note | x 1 Picture
96b02104-2423-47d7-a1f4-59be0702e326 | checkpoint | Vinyl plank completed installation pictures
e9b94e1c-8b5e-5658-8d61-c0559aec995e | note | x 2 Pictures
6afc60a5-0458-4ee2-b41e-bba0ec3e6084 | checkpoint | Received and installed drain waste
b41842a1-dfe1-565e-bb88-88b4b6153e88 | note | x 1 Picture
86edd4f1-e8e6-4701-a026-2d827693e3f8 | checklist | NZ Living - Staircase |  | NZ Living - Staircase
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
12c171aa-a421-471f-aac9-6577a71a53d8 | checkpoint | Details
b8834cfd-0d0a-5c6f-9556-2009c224453b | textbox | Block Number
0555051f-e1e4-4ff2-bbda-2338d6ab98b6 | checkpoint | Staircase Number
151e9679-931b-4f70-9348-b67fa475bae4 | checkpoint | Sand and prep
c2fe2d1e-093a-4f7d-a5db-a1e37218f6de | checkpoint | Prep fill next to staircase on ground slab dirt trap
574a19d3-f5ef-546d-9f96-6f435f4dc65a | note | x 1 Picture
5a96285a-9d35-52f5-b411-eef97aeb6244 | textbox | Screed bag count
f5045963-8405-4eb2-ab45-31864c710a2f | signoff | Client Signature
49a990d7-e417-4f89-800e-dedef0796771 | checkpoint | Fit approved nosing and insert
ddbb2961-fa47-52d1-93d6-5349acec9a63 | note | x 4 Pictures
8ed85664-7dde-41c3-bb81-0d3669ef41ad | checkpoint | Fit vinyl sheeting adhesive 68T
d190fb1b-aa51-5a7f-af7a-987e9aa4619d | note | x 1 Picture
4fd48300-befa-4689-b672-46e3166722e4 | checkpoint | Completed vinyl installation
4c749be7-18f6-527e-9081-e8cfb65315aa | note | x 4 Pictures
c5ede8de-3f75-4fa9-a18b-c306de1966cd | checklist | Vehicle Incident Report |  | Vehicle Incident Report
075be75e-75ef-4bdf-9d1a-b12f53aac4f3 | section | Details
f3069888-c4a5-46c6-885d-91ce0a8c771f | checkpoint-no-value | Details
593f7b28-2133-5165-a1d0-88ff528ebccd | date | Date
26ec330d-9b77-5cc8-8f56-cebb7d407e02 | textbox | Time
5074bcf7-aa69-4744-a998-faaedbc55cad | checkpoint-no-value | Reported by
6f4f3be3-b381-54cd-abd6-b23616b584cc | textbox | Name and Surname
fd8b9f4e-4294-4eaa-ba5a-29133c0d42ad | checkpoint-no-value | Driver details
97ce5df5-dfec-525d-94db-31b7c00912bb | textbox | Name & Surname
b92437c0-067f-420f-b55b-f14e7060f213 | checkpoint-no-value | Vehicle Registration Number
2e2ebc72-e8b0-5a73-b899-b4712534e4bd | textbox
9e512bb8-318f-4e2d-aa49-a8125492c6f9 | checkpoint-no-value | Details of incident
82cc2686-53d9-5af2-94c0-308ed0fcfd3f | textbox | (Please describe)
007a324d-8f28-5667-b133-1d1f26d1748e | note | Add Pictures of vehicle and area
4af594f2-7790-4604-967f-ece48c0cfd17 | checkpoint-no-value | Was there a 3rd Party involved?
94684c25-ac1f-5388-9ada-6f19e748fe67 | textbox
f534aa82-4b8f-4109-989b-bf92c082c779 | checkpoint-no-value | 3rd party or Person involved
98f3fb85-6e53-50cb-aaaf-e4b22c19a6c2 | textbox | Name & Surname
2624cfc0-bb64-42eb-9e7e-a75bb496af80 | checkpoint-no-value | 3rd Party Contact details
32d36f71-3f38-5688-8fb4-8611ff5f3735 | textbox
f312343c-103e-5445-ac0b-ec64eabae77d | note | Take picture 3rd Party drivers Licence
ce6f3d8f-c0bf-5901-bc95-138167c53c85 | note | (Front and Back)
3840f5a0-97bc-5566-88ba-7248f6dc3bf7 | note | Pictures of 3rd party vehicle registration plate
286758a5-3c23-50f9-8804-8d11b009325e | note | Pictures of 3rd party vehicle rego details
140ca185-d8d2-4121-9a52-94601d7f7c5f | signoff | Review and signoff by Supervisor / Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
c187d08c-efc1-4184-900f-6a5344694c56 | checklist | Add Documentation |  | Documentation
6fd2b6be-74e5-404e-b395-b173523c7d59 | section | Details
09b732fc-d176-46c7-9952-96f00cdfd8b5 | checkpoint | Documentation
9f9dd812-f747-4172-b044-af1a77961e0c | checklist | Carpet Tile Installation |  | Carpet Tile Installation
89c0ecd3-57b5-4efa-82ef-8ab3be343b33 | section | Details
b89abdce-6b85-4da6-b4f6-d1fa3fe05e09 | checkpoint | Substrate clean and approved for installation?
dd096492-7c7e-4533-bbef-cab998b12b4a | checkpoint | Area clean and all rubbish / offcuts removed?
599bbc19-cd26-45d8-a3ce-9040c227ec66 | checkpoint | No damage to joinery, skirtings or walls?
5afe2412-a205-4cff-adeb-b78375267da8 | checkpoint | Has the floor been protected?
b1cc6b79-9233-4a8b-a16a-dbe034c4afaa | checkpoint | Installation complete with no damage?
43a168b5-a354-4386-83a2-7df3ad7f4d25 | signoff | Please signoff / request sign off by Site Manager
d48361ec-6249-4e57-a2c4-b284ebd4a61f | checklist | Concrete Moisture Test - On slab method |  | Concrete Moisture Test - On slab method
4ea7a164-2885-4856-934b-e560f10f1468 | section | Details
049b8f40-0b4c-4249-9bbb-530e9fb6b792 | checkpoint-no-value | General Details
1c783ebe-927a-5d86-a590-f6db03fd6b28 | note | According to the NZS AS 1884:2013, the acceptable level of concrete moisture content is less than 4.4%
c130146e-c842-5275-9f12-4addb709b02a | date | Date of test
8aaa8b02-ebaa-53d4-a278-d6f48d3afdfa | textbox | Project name
1e128705-cdbb-4044-92af-00aa3f14cde0 | checkpoint-no-value | Hygrometer device used for test
3d32f999-87a4-5a86-94c7-6c45b2955b42 | tickbox | Photo of Hygrometer device uploaded?
1694d8ad-dfff-405f-9d57-dcd5da6f715a | checkpoint-no-value | Test 1
8ccde11e-a55e-5e40-b5ec-00f46f8df520 | textbox | Area/Location of test and result
8da7a477-2337-507e-996c-05b2505b7480 | button | Result | PASS, FAIL
2a3ab77e-1ebe-40c1-a2ce-9ea310b6d980 | checkpoint-no-value | Test 2
d0233722-16c0-5da0-aac1-38eef5c2a1c0 | textbox | Area/Location of test and result
9f782e57-0730-5a52-9781-32957ed96f84 | button | Result | PASS, FAIL
53de483f-a48f-4612-9455-3a1db1399ff5 | checkpoint-no-value | Test 3
e2719cdc-c00d-5d1b-9bf2-4cd47525f2c7 | textbox | Area/Location of test and result
a0f19ccc-9c9d-5e06-86d3-9b36e0f5fdd7 | button | Result | PASS, FAIL
9f0ab392-270d-4cf1-a866-a5be00d0719f | checkpoint-no-value | Test 4
6f51729f-34c6-5f56-ac52-f7ed451e6cc4 | textbox | Area/Location of test and result
382cf7cd-3c7b-5c95-8a00-47632d27e071 | button | Result | PASS, FAIL
5726d34a-cb75-465e-b3a8-fb51f43d6b7c | checkpoint-no-value | Test 5
26cce781-72fa-5a9d-abe5-f98eb6174006 | textbox | Area/Location of test and result
8ab2edd9-60c9-5eec-83f9-ae17353e2784 | button | Result | PASS, FAIL
ca471d75-1f91-4744-884a-dfaa68051f23 | checkpoint-no-value | Test 6
203f4db6-d7b7-5ea1-87cf-de0547917584 | textbox | Area/Location of test and result
582c0280-d5e1-5071-9af2-18f8319d2579 | button | Result | PASS, FAIL
0f3f0c29-3fe7-415c-a629-4181f26c1990 | checkpoint-no-value | Test 7
b3c41250-8ca6-5479-ba06-43cda6f66e28 | textbox | Area/Location of test and result
00f7b600-949d-558e-9bd0-4a7b5f2b07da | button | Result | PASS, FAIL
ff4f06c5-f306-4fbc-b05a-919d456925da | checkpoint-no-value | Test 8
b09b3301-b1c5-53ab-be4b-da03bc70d7c4 | textbox | Area/Location of test and result
84a091fc-311b-52a2-a4ea-7a8582190cd8 | button | Result | PASS, FAIL
7d1c544f-fb1e-4729-be23-7f1c9f26d4ae | checkpoint-no-value | Test 9
5b2db635-e9d0-5dcf-abf1-a1ec1d984674 | textbox | Area/Location of test and result
6c6cad90-3c76-58f1-bcb3-d56fc984d73f | button | Result | PASS, FAIL
d876e515-c338-4d2f-9a01-de480372b2d2 | checkpoint-no-value | Test 10
d84d119c-3d8d-5c90-bff1-205cf4fbeaa9 | textbox | Area/Location of test and result
15a72e22-88e2-54f8-9116-b3de62694bee | button | Result | PASS, FAIL
bce75925-cec2-478f-9d4f-d5ab02aafaed | checkpoint-no-value | Remarks from examinee
fb1cebbb-f049-531e-b766-f658e805b520 | textbox | Remarks/conclusion
9f0a0fa2-f1a9-4cf8-80da-819f8f340d4a | signoff | Click here to signoff
4594d9fe-26ed-4df7-adc1-7b452cc58e9a | checklist | Entrance Mat |  | Entrance Mat
487958ed-2ff6-4f9b-9cf5-8e4716fd2861 | section | Details
c929f5e6-0eb2-4a05-b319-1df6d9ca84a8 | checkpoint | Substrate clean and approved for installation?
85f1fd5e-9896-40d1-9b1c-ce020e570017 | checkpoint | Area clean and all rubbish / offcuts removed?
b753918a-0bbc-4d9f-8e5d-ac0b67be4e4d | checkpoint | No damage to joinery, skirtings or walls?
e88c5409-7db5-4296-a81d-b101662c0c45 | checkpoint | Has the floor been protected?
39ada378-32d1-4064-8ecc-591667b61cac | checkpoint | Installation complete with no damage?
7d1b9153-3573-4dc2-a090-74e28e6c9701 | signoff | Please signoff / request sign off by Site Manager
fd5e024c-d49c-4684-8e01-88ec49df2d2f | checklist | Floor Prep |  | Floor Prep
571e180c-4095-44b6-95cc-893f81eae325 | section | Details
b0a9c1e6-72fa-4315-945e-cf43f43926ca | checkpoint-no-value | Date
de00522e-20d5-5ab7-9383-63fcc62648cb | date | Date:
fae9ddd4-26f2-4bda-8a3d-96bc7f7d1ce5 | checkpoint | Surveyed floor for flatness?
7cc5dc81-8fe7-43f6-808d-5431c68e3f19 | checkpoint | Moisture test done prior to installation?
16a57f9a-83e9-4e35-b4a6-8fb751252d53 | checkpoint | Clean Grind Subfloor
555436b6-44cd-4fa2-814f-2ffc18b082b4 | checkpoint | Apply First coat - Mapei Proof Primer North to South
87b8ddc6-22db-462b-9c3f-52eefa706008 | checkpoint | Apply Second coat - Mapei Proof Primer East to West
eb24b9cd-5dde-49b0-ba2d-75aee679b7ee | checkpoint | Skim coat applied / Disked ready for Vinyl
4d0a5a14-e503-412c-b885-76d6abfab2c6 | checkpoint | Disk ready for Vinyl
2fee69f9-08d1-4023-b7a7-f73449e46d0c | checklist | Floor Prep Screed |  | Floor Prep Screed
725e90c6-7c3e-4ebe-8380-2d1ad0364569 | section | Details
23da7e3c-53e2-4f61-9adf-ed5d99dc6def | checkpoint-no-value | Date
fa8a1341-0575-5058-8e0e-8424496f66b3 | date | Date:
e79c9ff1-d208-4226-83ac-95d59a55c4b4 | checkpoint | Surveyed floor for flatness?
27988768-604e-41b4-9723-e8c31536c148 | checkpoint | Moisture test done prior to installation?
71e683ee-c7ab-4e36-993f-851d2578177e | checkpoint | At-risk surfaces protected?
eb4fa0ee-1169-4afb-bfa6-dd0a3db2b74e | checkpoint | Clean Grind Subfloor
9cee5e47-026e-4fc7-aaa5-10b4af1ca0f2 | checkpoint | Apply First coat - Mapei Proof Primer North to South
3211fb5f-0565-465b-b9a1-630b93e3ef89 | checkpoint | Apply Second coat - Mapei Proof Primer East to West
31c8b678-a0ce-4c4b-ba3f-1dae31a9981e | checkpoint | Floor Levelling complete
869cfb70-9fad-4969-89f7-38e0c052e7e8 | checkpoint | Area clear of rubbish and debris?
53a744f8-e1ae-4d85-b3d0-e394d7c470bf | checkpoint | No damage to other surfaces?
afd70a94-bb04-4432-9a89-0e9023d17051 | checkpoint | Levels checked and ready for installation?
49c3e6ce-5312-42ce-ab30-25eb63962790 | signoff | Please signoff / request sign off
b92180f7-8ace-4fa2-97e4-cbf61eb66568 | checklist | Floor Prep Wet Room |  | Floor Prep Wet Room
e09c666e-b5c0-4ec2-bc24-c4b97cff7f63 | section | Details
ebf6ea39-9334-4702-88af-1366096b0d57 | checkpoint-no-value | Date
c0bb8c95-5ea4-4076-a860-043ab8f35612 | date | Date:
034eed07-06c8-5718-ac35-2c61e94a841e | checkpoint | Surveyed floor for flatness?
99e48597-dd72-40ca-88a5-0f146df84eac | checkpoint | Clean Grind Subfloor
c3ca90d7-67ef-468f-9b31-dfb5a2d2a72a | checkpoint | Apply First coat - 1 K Turbo moisture barrier North to South
f9c68a4b-75d7-4c4b-a3ef-f9854b1e43b5 | checkpoint | Apply Second coat - 1 K Turbo moisture barrier East to West
62a81286-8b36-4821-a0f6-efbbc38fa714 | checkpoint | Prime floor Eco Prim Grip Plus
8077f5ca-1770-4497-b54c-c289a64fd94d | checkpoint | Adjust falls with Novarapid if required and prime floor again with Eco prim Grip Plus
7f91dcfc-dc9e-40c1-be5e-1c13b7d2d575 | checkpoint | Prime wall with Eco prim T Plus
450cb22f-776e-4811-afce-f944c5997bdb | checkpoint | Apply 2nd coat of Aquadefense
5b8f2e45-79df-45a1-9948-9e87a4daebd5 | checkpoint | Apply mapeband and 1st coat of Aquadefense
ab5ac815-6ebf-4819-b26a-6681664da50b | checkpoint | Skim floor with Planiprep SC
5f6b5d1e-b737-4bbf-ac21-9cd24b202152 | checkpoint | Skim Wall with Planiprep SC
4419a990-5102-4fdc-8d38-0eab915aac21 | checkpoint | Disk floor and wall ready for Vinyl
558a9e31-057b-47a2-b8ed-4921b74e95eb | checklist | Floor Vinyl / LVT / Marmoleum |  | Floor Vinyl / LVT / Marmoleum
d599bd7b-c8e9-4851-aab0-8cd5bbd472e1 | section | Details
e80aaa18-7c45-439f-9b97-a2c944155559 | checkpoint | Substrate clean and approved for installation?
58564d24-79c3-45e5-91b6-709ccca9e852 | checkpoint | Moisture test done prior to installation?
81f7df97-86dc-4288-a7ad-6159231cbd1a | checkpoint | Specify glue to use e.g 68T, UZ2000 or Marmoleum glue.
3d3cd7b6-1dae-44d6-a6f2-99e8e9388e1b | checkpoint | Doors to be removed?
024179ae-080f-46d9-b767-91c95fbb0198 | checkpoint | All capping installed?
8f8ca50b-3e06-4e3e-a2cb-2bb7ff45468b | checkpoint | All butterfly corners done with templet, images required?
6e34ff40-b568-4041-ae40-db3c150bdbbd | checkpoint | Vinyl rolled during installation
9add3933-1d6d-4c80-a985-62813a72e10d | checkpoint | All areas complete and welded?
fdb836ee-94e6-4c83-8eef-24a7bac58652 | checkpoint | No excess glue on vinyl surface?
3cba53de-0523-47a6-ba60-4dcd3cb38cca | checkpoint | All transition trims installed?
d0fbffbf-4a6c-4701-becb-ce5e364af8f6 | checkpoint | Area dust free and all rubbish removed?
a97b7ea2-1f55-4ee8-93d4-500efdfb6032 | checkpoint | Has the floor been protected?
44d1778f-d601-4499-b52c-5e9401669bdb | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
d924d0be-52c3-4a60-9e31-57fb86f92018 | signoff | Please signoff / request sign off by Site Manager
45192593-9526-43be-bc3b-fbbf5d52b767 | checklist | GB Add Documentation |  | GB Add Documentation
06d39eb4-d638-4634-9703-20ec262374f4 | checkpoint | Please upload all documements and press PASS.
92b0afe4-3131-4d47-9869-eba38bb8aa53 | checklist | GB Carpet Installation |  | GB Carpet Installation
8f6cc434-87e7-455a-b4a7-eb764f097ba9 | checkpoint | Substrate clean and approved for installation?
371e782f-d046-5f61-a96f-0692b58a6c35 | note | x 2 Picture
90b29ee3-6656-4952-b222-f7672e4b8ee7 | checkpoint | Are sills, door frames & tiles flush with carpet?
b662be60-1004-5481-968f-9434d6402683 | note | x 2 Pictures min
c6e08f75-c089-444b-9ed8-7abb69d825a0 | checkpoint | Doors to be removed? Take pictures before and after (proof no damage)
455c1dad-c21c-53ab-a918-53d5d542a291 | note | x 2 Pictures min
251e47e8-bf74-43c8-9be2-c1fd81a224db | checkpoint | Confirm plan matches site and joins ok?
6f00b1d9-586d-459c-ad53-73c7f67272b1 | checkpoint | Review job sheet confirm all detail matches e.g. colour of carpet, underlay required?
226a2c3d-0cd4-46ad-adac-ea7b2cd19995 | checkpoint | Take photo of carpet joins?
0f025312-9e54-5d3b-b0e0-610e7fbff299 | note | x 2 Pictures min
46a8cdd4-c4c5-423b-8021-ce39d201f978 | checkpoint | No damage to skirtings or walls?
29044a8f-3cd1-5ba4-8f77-d0f9c57ba42f | note | x 4 Pictures min
eb5ef117-3fed-49a3-8fdb-3f43be4a9663 | checkpoint | Doors replaced and area left clean of offcuts and rubbish? Take pictures before and after (proof no damage)
65cf7435-02ac-558b-b6e5-8383f8cc3ee2 | note | x 2 Pictures min
447fd04e-e5c7-47ee-9f3f-0cdaf5be2ab1 | checkpoint | Walked all areas, pins tapped down, stairs tight, no carpet lifting, all ok?
e48a329c-410d-5fbc-bcc9-6de5349419d3 | note | x 2 Pictures min
53b36600-c4d3-4bb0-9764-a488b552e3ed | signoff | Please signoff / request sign off
0cbaa9a1-0a04-48b0-b02e-cf178581f74a | checklist | GB Laminate |  | GB Laminate
dd6f358a-6c6b-4cd1-98a6-8bdeaca960db | checkpoint | Area clear of rubbish and tradespeople?
53a3e993-bb12-5eec-a454-2c73a45dda73 | note | x1 Picture
e236c956-11d6-4fe1-917f-d1bee79587d5 | checkpoint | Survey floor, More than 3 bags and 3 hours grinding? If yes, notify the office with images & scope and wait for approval.
cc9c2231-1883-55d8-9d00-15ccdd2ad48e | note | x1 Picture
44670814-d443-42fc-835c-e9959c17c25e | checkpoint | Direction of planks shown on plan?
a376891b-c474-4a31-bcde-c5351e2b89e4 | checkpoint | Review job sheet confirm all detail matches e.g. colour of planks, underlay.
a1199e87-8af3-4fe7-be21-a84e3db8299f | checkpoint | At-risk surfaces protected?
976bae3f-0068-5275-9d69-0be06b737ab2 | note | x1 Picture
1cbd56c4-835f-4b32-abd4-005ec9ebb46e | checkpoint | Installation complete with no damage?
6a9a009a-e070-57fb-b743-3a66fc035fe0 | note | x4 Picture
1d753ef4-0bc3-45da-b98a-893f00ad0010 | checkpoint | Walked area and checked for gapping, bouncing, expansion etc?
0df2ddb4-ed17-4e43-8cc0-9a4fe9ca3fe7 | checkpoint | Opened boxes left on site and unopened returned?
f8df6dcc-ced1-4bbf-990b-1c5a3eab4045 | checklist | GB Timber Installation |  | GB Timber Installation
fcaeae62-8186-48b4-bae7-6619af4f58bd | checkpoint | Moisture test done prior to installation?
3d0236db-d5cd-57b9-a99d-01fe5ac37082 | note | x1 Picture
58acadeb-0328-4eb9-93ac-589841eaf89d | checkpoint | Floor prep assessed and deviation less than 3mm over 3m?
21af44b0-45b1-4655-9e4f-b716c0619336 | checkpoint | Review job sheet confirm all detail matches e.g. colour of timber etc
c27900de-45f1-444a-a7de-71d72638e8fd | checkpoint | Timber direction confirmed on plan?
305e277d-6209-43c7-9719-71795a210f18 | checkpoint | Bags and hours grinding signed off by Jay before starting?
ad8fc902-721c-4ac9-8a19-f339134afcc4 | checkpoint | Timber weighted down after installation?
c35d217e-7b21-5ad4-9155-eb47b3c07d92 | note | x 2 Picture
d193a39e-cfaf-4397-98a8-936933fb0a46 | checkpoint | All transition trims installed?
9929b223-9ed0-547b-996d-1e3a6def6c99 | note | x 1 Picture min
1c4608c5-0625-431f-963a-4a5b36ca9b7b | checkpoint | Area dust free and all rubbish removed?
53e4ae72-b0e4-558f-9373-ae88127c32a5 | note | x 2 Picture
6aa34fab-d439-4e34-90e5-02cd02971a70 | checkpoint | Installation complete with no damage?
b86aec30-28ee-5cf3-92d3-966ed60fcbc0 | note | x 2 Pictures min
1a479015-aa3f-42e8-bab0-c67bcd5521b1 | checkpoint | Walked area, all ok no gapping or damage?
dd5a44c3-61bc-58e2-877f-daf88c103493 | note | x 2 Pictures min
a82c0163-f1c9-4be9-81d8-2a3bb32be936 | checkpoint | Jay advised of all left over materials?
abe30dd4-e629-4653-b849-5c2a27ff7d45 | signoff | Please signoff / request sign off
eea7465b-3f47-467d-8199-28fc96685bb7 | checklist | GB Vinyl Plank |  | GB Vinyl Plank
8f09d853-f31c-4bcd-b7c5-1d12668b670f | checkpoint | Survey floor for flatness?
057f8aa6-6d9b-4ddf-8b56-d2ca1cfd87bc | checkpoint | Area clear of rubbish and debris?
f204fd14-0dc7-470b-9910-450ddee16469 | checkpoint | Planks have been on site and are acclimated?
08021a62-cd4e-4de3-bd84-44ad3da6db69 | checkpoint | Direction of planks shown on plan?
6e5e1bd3-4151-4eef-85d5-83cf02cc67fb | checkpoint | More than standard prep required? If yes, notify Jay with images and scope, wait for approval
6afc91e8-2e37-4a77-9ab7-a6a3a084a3c9 | checkpoint | Moisture test done prior to installation?
dd2259fa-f882-554b-95da-4ac575a2d9d2 | note | x 2 Picture
3ae204bd-3090-4a72-af39-37b857258a45 | checkpoint | Windows with direct sunlight blocked
cf00c9d6-07f3-55e5-96b7-4e1286275125 | note | x 2 Picture
a78453d5-9327-4d6c-b8a2-c4b84533ce7c | checkpoint | 68T used 1.5m from splashzone (sink etc)
96d3425b-177f-4f92-a227-359e11b797dc | checkpoint | At-risk surfaces protected?
67f70ef1-1e03-500c-8e54-269d984c73af | note | x 2 Picture
7c5dce30-9dd5-44b3-8d0a-c1feaa646595 | checkpoint | Installation complete with no damage?
584e00c2-e4e9-5294-8273-516aff9ea55c | note | x 2 Pictures min
1a9d6a89-e2cf-4738-a9a4-b2375685efa0 | checkpoint | Walked all areas, checked for gapping, lifting, excess glue on boards and skirtings and all ok?
31eb8503-ee40-4fe2-8fd8-515a6e9caaca | checkpoint | Opened boxes left on site and unopened returned?
f7fa9a52-5794-425e-a8f8-d9b619aea3e3 | checklist | Incident Report |  | Incident Report
08c8e588-b993-4cc6-88ad-0619e10bbfb6 | section | Details
03f584ab-cfb0-4dd0-93a0-08897493e3d7 | checkpoint-no-value | Project name or location
f71ba335-9972-58ff-bc39-86b8599f34a9 | textbox
9a6e353f-dafc-47d5-b982-70f4a4db4674 | checkpoint-no-value | Date & Time of Incident
354b496b-0bf1-5fab-b43c-0152fd23a043 | textbox | Date & Time
86e9cb36-1e90-4242-b00f-f0011ed65ae5 | checkpoint-no-value | Reported by
645b592a-a151-5220-b0a4-ac332d0dda57 | textbox | Name & Surname
827ae961-dd74-46d6-8981-7c2fa04fd57c | checkpoint-no-value | Reported to
4a5c810a-dea0-5112-8274-7022ec1a3b19 | textbox | Name & Surname
173f399f-815a-4bf0-84b2-e0391eb446a8 | checkpoint-no-value | Incident Type
9452c458-0c1d-5cc2-82e9-8386aedcc0d2 | textbox
b29001ad-3cc9-5bbc-b6c6-dc276ad50767 | note | Add Picture
78982c1e-cd99-469e-9cc9-d22c007bb04a | checkpoint-no-value | Details of incident (Injuries)
7a7da81e-bd1d-4a34-a3d8-037c31904c57 | checkpoint-no-value | Person involved
7dbd5b63-83e6-5af7-b4f5-423e66370519 | textbox | Name & Surname
08ebcfbd-abbb-5ab6-ad53-8c42313e1f1f | textbox | Contact details
af0f7a03-1c84-4762-b1dc-1483b3ccf3b5 | checkpoint-no-value | Details of witness
dbc5f7b6-9270-54e9-880f-2b7f20de0fb5 | textbox | Name & Surname
042f9a55-5684-5cdc-a05e-df64b55f3625 | textbox | Contact details
a1a96798-f3fe-4863-a413-9b80d14314af | checkpoint-no-value | Manager Remarks - Actions and Follow up
2584a8bd-c585-597c-ae0d-63b5157fd7cc | textbox
d61a46f8-b461-4c7c-8bc1-c0921ca7ed2e | signoff | Review and signoff by Supervisor / Manager
585b7b19-6122-48d3-9ca9-c52a9986d948 | checklist | Project Stock Control |  | Project Stock Control
0df76a2e-a8d6-4f6d-b672-9b1bd22450fc | section | Details
d6e05d94-3e35-4804-a07c-68fe5ce5a4b6 | checkpoint-no-value | General Details
034773a5-bde6-5ecb-b0ae-78ee086d0821 | textbox | Project name
0a1a2a68-f205-53e9-aa39-5af1ac8b75c7 | textbox | Job number
efe5c4eb-b741-58a4-ac88-999002ea7f8e | textbox | Product Manufacturer
1fc2ed27-d942-55d0-87f8-de97bdbfc449 | textbox | Product Range
6bdecaf1-1739-5a2a-a9c4-d7114be6df66 | textbox | Product colour(s)
1cb16bd8-d3e8-4b44-ba42-5101a2eb5f63 | checkpoint | Quantity Received from suppliers
587ddb13-18ce-5c99-9fb4-77bb39766eae | textbox | Boxes
a799de13-1dce-5df6-a25c-26e45bc5777e | textbox | Square Metre Per/Box
e2d30ee7-0f70-5758-b908-b9fbd28f533d | textbox | Square Metre Per/Roll
d63cac9d-4124-4d16-a2b3-7696de4426b0 | checkpoint-no-value | Stock issued out to installer - 1
c0e20704-c43d-5ac0-a136-69191fb129e3 | textbox | Colour/Range
5346cc21-ca0a-5c9f-8527-926554040587 | date | Date
1b7382d7-9b6d-5a7d-9a87-b33c3ce79c10 | textbox | Quantity
a0fb7eb4-adc0-5f2a-89e0-a4ae53852527 | textbox | Balance left
2e725ad9-2806-4876-8571-5a9c8388e05a | signoff | SIGN HERE
1f591d03-09b0-4973-b755-f1ae2a9da8cd | checkpoint-no-value | Stock issued out to installer - 2
6ca92818-883d-5b50-bb98-5f2c3c62d835 | textbox | Colour/Range
8a25220a-4cc9-5379-8ca7-faa3f51b2757 | date | Date
1c9e0cba-df46-5a39-8e0a-b30e0bc04e43 | textbox | Quantity
24f133f1-aa3a-5a8c-a40b-a1e0efa1b677 | textbox | Balance left
48208d5d-f35a-420f-aece-02b76e63d3e3 | signoff | SIGN HERE
33d8002f-919f-40bc-ad83-d373e4fcb8c0 | checkpoint-no-value | Stock issued out to installer - 3
39b2970c-9b6d-52d0-a08f-cb32e0dfd2b5 | textbox | Colour/Range
b3b5b2e0-1c72-5032-bfe3-f38cbb2def0e | date | Date
4fe9f599-09c7-52a3-a2bb-f5aef1a359e7 | textbox | Quantity
a6c2d037-9d6d-56d0-afea-0dfda3e5a2b2 | textbox | Balance left
cab09970-3a26-4abc-b048-cf459aa4f14e | signoff | SIGN HERE
ec3bc47a-7d3d-4a79-b0bc-da050ec5ab57 | checkpoint-no-value | Stock issued out to installer - 4
e22c4947-a424-50e4-a50b-911f3425dc6c | textbox | Colour/Range
e63fe33d-b384-5009-b043-470ac416c05b | date | Date
77c418cb-243b-5cf0-a3e3-c0fdf2384c88 | textbox | Quantity
56e0bbfb-5daa-5549-92e9-7efe5ebb18dc | textbox | Balance left
5a1674f8-73e4-4f0a-a7ed-ad2be6dcc7dd | signoff | SIGN HERE
5c7d0f6e-2242-4547-a2b7-2acf997a9f30 | checkpoint-no-value | Stock issued out to installer - 5
34de0c1f-e8ae-53e0-8035-f8449ba3e7c8 | textbox | Colour/Range
0397f60d-8b02-5d3c-8165-2cbf1ad504ce | date | Date
8e6d0541-61a4-5b9b-b81f-07da1d9d2676 | textbox | Quantity
f1f8d689-d94b-5ef5-a2fd-c67d2ff45248 | textbox | Balance left
0843ea5d-9bb2-498c-97c3-9ddb333a09f7 | signoff | SIGN HERE
1bd50b06-2e07-49f4-82ad-d57edc42f132 | checkpoint-no-value | Julius Remarks
65552aa3-19db-5198-8391-ed864a3eb93b | textbox | Remarks
77febfbd-9a2f-4739-8b39-198e1940e8df | checkpoint | Any material returned upon completion?
129587d6-90a2-5526-8bbf-09f2c2f1146e | textbox
a779306e-4790-45e6-9cfd-83f8efa01e90 | checkpoint | Signoff
9e9eccd1-1b2b-44ef-b1c2-9a4e0cf44993 | signoff | Review and signoff by Manager upon completion of project
e28eaaa0-c882-4d30-8a7c-d88cc2bd4340 | checklist | Toolbox Talk - Site-Specific |  | Toolbox Talk - Site-Specific
1867bfac-e5fc-4a75-a770-92a07574da79 | section | Details
fb471fc4-19d8-43ad-9aeb-6e4e73664cb9 | checkpoint-no-value | General Details
52f18fd6-b3b6-5eeb-92cd-6c643cccfb2f | textbox | Project name or location
9775011c-9a8a-51d1-b5b4-1af4030ca093 | date | Conducted on Date
8ac0533b-47df-5a4d-8069-a5cff56e119b | textbox | Who is running this meeting?
1c08929c-9f92-40f3-86c9-81e1c956eaa3 | checkpoint-no-value | Toolbox Topic
a82fe347-4b80-53b3-b6c4-6176f6edb622 | textbox | Description
3a81fa07-9e5e-5fbb-b28a-9c5e3ca63d56 | textbox | Actions
abbad9d4-1c82-428a-b5be-ae77b9052951 | checkpoint-no-value | Issues raised from site?
07053863-5e85-5478-8c5a-b344c9d9586d | textbox | Description
de9e851e-93a0-5416-bb26-d23593bba799 | textbox | Actions
a0d1c244-0291-48be-891c-6aa363ab693e | checkpoint-no-value | Employee raised issues?
5617fe10-7187-59bd-b615-d8bea4fd3611 | textbox | Description
4758440a-49df-554e-afef-5f3d2f5b88cf | textbox | Actions
60dc4ec2-db8a-468a-b731-09fa46e0e534 | checkpoint-no-value | Incident or Injuries
dcd09476-e502-5d5d-a356-986f1a3ae237 | button | Any Incident or Injuries to report | Yes, No
4f7daf9f-a81d-515b-bac1-160f1bb67d30 | textbox | Description
3178ce09-8695-5bd9-9c48-0c3684cf7929 | textbox | Actions
4088fcd5-e485-403f-8508-3decea1abd12 | checkpoint-no-value | Hazards
201ebdc2-8f7b-5fa7-a298-e7e0e8c8dff2 | button | Any Hazards to report (Dangerous activity or condition) | Yes, No
c493e5e0-e6a7-56a9-b3ef-13b2102df21f | textbox | Description
49261882-ef80-539b-bb24-12054708fca8 | textbox | Reported to
5b136608-f44c-4d25-8212-9fcf34df8e41 | checkpoint-no-value | Risks
5a555d5e-dc67-5261-bb83-347a34b43c5d | button | Any Risk to report (Possibility of something bad happening) | Yes, No
68235699-1036-5ea4-8b8a-76142667c420 | textbox | Description
230c222e-807b-53ce-bf5d-a72c6f1c0032 | textbox | Reported to
d99f8fdb-654f-4d84-9ff7-f28009ba1df2 | checkpoint | PPE - Personal Protective Equipment - Correct and in good condition ?
7bb94721-12a5-555c-8d9f-2c523bce4348 | tickbox | Inspected
dc53c900-5795-435b-96e4-538411e64bd1 | checkpoint | Positive safe-action observations
7e67ec13-7699-58d8-ad87-ac730486031c | textbox | Observations
95c2915b-bd94-4e72-968d-39f9e0abd39c | checkpoint | Attendance Record
9a766e8d-73a9-4a4a-84f9-07b620bc3dfe | signoff | Each attendee to click here to signoff
5ff9a824-180a-4037-92dc-b7cde9c6b4d9 | checkpoint | Supervisor / Manager remarks and signoff
6399ff62-936f-5e49-92fe-30be946781d1 | textbox | Manager's remarks
56589920-bf33-4b2a-97a2-0c83c9d4c56e | signoff | Review and signoff by Supervisor / Manager
6573cb25-bba6-468d-b8c1-78611d14934d | checklist | Wall Vinyl / Cove / Splashback |  | Wall Vinyl / Cove / Splashback
51022f2c-33f9-44f5-8e02-f9e39a65685a | section | Details
bf74ce56-097f-47a9-91d4-f94795d03813 | checkpoint | Substrate clean and approved for installation?
8fc7ba46-d257-4002-9e5b-362865eac5ab | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
2f13210c-a405-4f78-8a37-e89560c0ad3f | checkpoint | Cove height confirmed, and capping installed?
e62d3454-4a67-4792-a855-7ef2bd6e2237 | checkpoint | All areas welded?
d43b7397-31ea-41c4-bfc1-15f815d9c740 | checkpoint | No excess glue on vinyl surface?
53efef69-ac9b-4d9c-a3cd-2063cf42f588 | checkpoint | All transition trims installed?
7e6b2143-e2fa-4f0c-b78e-78328e6a0206 | checkpoint | Area dust free and all rubbish removed?
046d797c-d5c5-4398-b40c-5c7c49b2dd6b | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
3006b9d6-212b-4d09-bd0a-64399b5535f0 | signoff | Please signoff / request sign off by Site Manager