## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Approved JMF |  |  |  |  | Yes | Approved JMF | 023c1fe1-faec-4f3f-bcc8-cb8bff955a47
checkpoint-status |  |  | checkpoint | Approved JMF
checklist-sectioned |  |  | checklist | ITP - Resurfacing Physical Works |  |  |  |  | Yes | ITP - Resurfacing Physical Works | 11c501f3-3973-475e-9374-d873aa4ed1ba
checkpoint-group |  |  | section | 1.0 Pre-Works (Off Site)
checkpoint-status |  |  | checkpoint | Stakeholder Management Requirements met
label | 514feb31-9900-57d4-87a8-0493114086f0 |  | note | H
label | e1ae0b63-4067-56f9-8592-01007f84c8c0 |  | note | Reference or Specification: CSCMP
label | 382f6237-72ed-5217-a8e5-de23badbb6a1 |  | note | Method/Test required: Confirm requirements followed
label | b69db65a-72ae-5a9e-904f-353797cc31ba |  | note | How Often? Each site
label | 5daf83bd-fef7-51d0-b9fc-7a85bd370d47 |  | note | Records Required: Copy of stakeholder notification / Photographs of VMS Boards
label | 7781d3d6-3b86-5d3a-9ddc-bdbdcaf00bb0 |  | note | Responsibility: Project Manager / Renewals Manager
checkpoint-status |  |  | checkpoint | Confirm if any environmental protection is required
label | 4e81b85c-5e3b-522b-a4ad-a194f31abd3d |  | note | I
label | f8403762-7078-52f2-a338-02c98b9b934d |  | note | Reference or Specification: ESMP
label | 6763a998-4db1-5bf9-a8df-f90fd06fd686 |  | note | Method/Test required: Record decision
label | 11877c7f-21b3-5356-833f-e4a29538fb93 |  | note | How Often? Each site
label | 22e661b6-bb81-5f58-a9b4-61539753e690 |  | note | Records Required: Pre-seal Inspection Form
label | 958d24ac-4e9d-5a00-9aee-c5d76da70220 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
label | 1095741a-fab2-59d2-a352-3fafb4d244f7 |  | note | H
label | 05acbac3-9222-58c0-bffc-117d155a872b |  | note | Reference or Specification: QMP
label | c420a46d-b2fb-5b28-8898-c489c22c4b87 |  | note | Method/Test required: Brief all team members on day’s work plan
label | 280f4f63-5321-5d00-90e3-ff1a754bd580 |  | note | How Often? Each site
label | bcb28a12-08b9-5983-8fa1-bbbb13519978 |  | note | Records Required: Pre-seal Inspection Form
label | 29ac66cb-a92a-5343-bb2a-5f7cf543ebf4 |  | note | Responsibility: Project Manager
checkpoint-group |  |  | section | 2.0 Pre-Construction (On Site)
checkpoint-status |  |  | checkpoint | Job start, identify risks and controls, communicated to team
label | 372af9e1-6473-5edf-8993-a3ca0522718e |  | note | H
label | b4d0775b-9174-5a44-924b-22bce35a41db |  | note | Reference or Specification: HSMP
label | 1fea5a20-4f12-5bad-bc7f-e9f59974991b |  | note | Method/Test required: Record all risks and controls on Hazard ID following Team discussion
label | d30282bc-aa17-5ca8-8bb4-a58bfc02a918 |  | note | How Often? Each site
label | e96c6583-fbc6-5560-9895-0f9b06625919 |  | note | Records Required: Hazard ID form
label | 442f38a5-6273-5206-a47a-0c569f704a5f |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Establish traffic management to plan
label | 422df42b-d6af-5d8c-8c15-0aea2c1be5a7 |  | note | H
label | 57d28253-685e-5509-8f65-b36ed82b48b0 |  | note | Reference or Specification: TMP
label | c7d7ae90-64fc-5b23-b65b-fb475b7755db |  | note | Method/Test required: Site audit post set up
label | 9e42c8f9-4790-5262-b84c-ba02f020576a |  | note | How Often? Each site
label | a6290f6d-ac7c-5bc6-b233-aa5a15609803 |  | note | Records Required: TTM Diary
label | acdfa61b-dcd9-580e-8901-6d413786c036 |  | note | Responsibility: STMS
checkpoint-status |  |  | checkpoint | Confirm site is on approved programme
label | 486f5ace-fab7-5fc2-bbf9-1bd224e46bf7 |  | note | H
label | e72139d6-b145-5b6d-be28-73a90b05908e |  | note | Reference or Specification: Approved Programme
label | 98b95bca-e55c-5bf1-9b27-b1e54cc617bd |  | note | Method/Test required: Record as-built site dimensions
label | 2f995590-68d2-565f-be50-11469e8c276c |  | note | How Often? Each Site
label | aa11cf57-b7d5-5eef-96f2-9e37d066e304 |  | note | Records Required: Pre-seal Inspection Form
label | b3c5e478-6e76-538e-961e-e38a3723689c |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details
label | 8cd591a1-c0c0-51b8-9244-f1c3f4d20685 |  | note | H
label | 67a55671-9978-5eec-9b22-34e7166377c3 |  | note | Reference or Specification: Approved Programme
label | a08a323e-5552-5e44-ac67-8ad687ff9bf0 |  | note | Method/Test required: Record as-built site dimensions
label | b6396cf9-41a2-5d83-80aa-b2b2895278e6 |  | note | How Often? Each Site
label | d98f130a-ea48-54b1-bf06-8caf9c60fffa |  | note | Records Required: Pre-seal Inspection Form
label | c89e98b9-1c7c-5d33-889f-3736922a4ebd |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Stockpiled sealing chip is clean and suitable for sealing
label | be21e7cc-f14e-58c9-9b8c-a583fa6c4896 |  | note | H
label | e5e277e1-541c-5741-b13e-1d9a3cb0ab2e |  | note | Reference or Specification: QMP
label | ab06bef6-7758-5bf3-a31f-507b8d8b8639 |  | note | Method/Test required: Acceptable/Unacceptable
label | 37dc2fd1-f83a-501c-b67e-1d8a22157eb1 |  | note | How Often? Each Stockpile
label | 133fee51-a5ec-5d62-89d4-12be3bb3eb3a |  | note | Records Required: Pre-seal Inspection Form & Photograph
label | 5cf85885-ca9d-5a7c-b47a-6511cc686fe6 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design
label | db83ce0f-fbb5-53c4-899f-58e02af52cab |  | note | H
label | 7f93c9d5-e527-5ac7-9d7c-e82ab4e45b8f |  | note | Reference or Specification: QMP
label | d991459c-7f98-563f-ba0f-bb4597678f17 |  | note | Method/Test required: Acceptable/Unacceptable
label | 9cec3ef5-ca6e-514b-83f2-3f630037c3a2 |  | note | How Often? Each Stockpile
label | 2ab90d87-bab0-53f1-8235-6cfbbb41f379 |  | note | Records Required: Pre-seal Inspection Form
label | 4920f103-16a5-52e2-9ada-eced370809ca |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Record & photograph environmental protection measures installed
label | e08dfe05-2e41-581d-9fce-669f71a96348 |  | note | I
label | d3703491-18cd-514c-8411-c3e2f35f6eae |  | note | Reference or Specification: ESMP
label | 84e7fef5-422f-5af8-bc7b-9f0e954f433c |  | note | Method/Test required: Record temporary measures
label | dbb42a91-5d90-5a83-a4d2-eb44afb2c3e2 |  | note | How Often? Each site
label | 89866830-ef4a-53dd-8cb7-b1244aa975ee |  | note | Records Required: Pre-seal Inspection Form & Photograph
label | bb42efcf-3c7a-590f-ae65-622ef2c1e1d2 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Binder application rate
label | 31d6f7d3-af32-5cd4-ab4d-f68331d697c0 |  | note | T
label | 81331c41-745e-5785-8e9f-82a86f4d57ed |  | note | Reference or Specification: Seal Design / Spraying Instructions
label | 166f61ea-3cd0-5974-9bb8-037453bbbaba |  | note | Method/Test required: Confirm seal design requirements from programme
label | cddaf740-3904-5869-a75c-ea8303584c7d |  | note | How Often? Per site
label | 660a14c4-f391-5d97-91ed-02418fbcc564 |  | note | Records Required: Spray Sheet
label | bfc47693-07eb-5393-a9d2-dc0a42482839 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Pre-Sealing surface condition
label | 63825ca3-689b-5ae2-9df0-41126ae36d65 |  | note | I
label | 41a654cb-6c86-5b40-81a7-8c0506ca59b1 |  | note | Reference or Specification: QMP
label | 3803892d-6166-544e-bf39-818d0042ae50 |  | note | Method/Test required: Acceptable/Unacceptable
label | 2575e3f0-38f0-5a4e-8ac8-bc6aeabf285e |  | note | How Often? Per Site
label | 7a4bae46-7cc5-5551-8bc2-74ba80614f0f |  | note | Records Required: Pre-seal Inspection Form & Photograph
label | 4e3e70ef-6f5b-58cc-ad2a-2fdd696deb15 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-group |  |  | section | 3.0 Construction
checkpoint-status |  |  | checkpoint | Start spraying Temp >10°C
label | bb813cd5-bdfd-5d74-8467-d2c84d26aa61 |  | note | T
label | 3521d8eb-8049-5390-a8f2-662a8b2dc4af |  | note | Reference or Specification: NZTA P/17
label | 7757406c-ccc2-5815-8d77-8c63020f54c2 |  | note | Method/Test required: Start >10°C
label | efd27d66-b105-5c39-9b90-60da5aa76685 |  | note | How Often? Per site
label | d6116fac-c4e4-55c2-b0cb-7ed9eb57974a |  | note | Records Required: Spray Sheet
label | 9e9314f8-ea99-527b-ba11-76b88abf9e51 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Binder application variation
label | de88f092-56f7-5269-a824-b7f076452397 |  | note | T
label | d90fd9b7-fd1f-5a48-a5ed-a7af5f187577 |  | note | Reference or Specification: NZTA P/17
label | 4724bf5b-4707-5983-a58d-97a26df72e44 |  | note | Method/Test required: +/- 4% (spray rate) ; '+/- 50l (tank dip)
label | e28c2fbf-78bc-570d-972d-0eb2bf2c884d |  | note | How Often? Per site
label | f644c823-03cf-5f01-b057-6a5d30087335 |  | note | Records Required: Spray Sheet
label | 9c25bfa1-ef4a-50ed-b098-394ae898d915 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Sealing chip application
label | 58bf46f7-3631-56d2-a29d-05870321c645 |  | note | I
label | 1250e596-91da-5ace-b99c-8b0bb55d1e49 |  | note | Reference or Specification: NZTA P/17
label | 189e2f74-6682-549b-aa26-80b7fbffd361 |  | note | Method/Test required: Full and even coverage of sprayed area
label | d051d9f7-4d7d-560f-93f7-5f184de40863 |  | note | How Often? Per site
label | 0e615c88-4c58-5aa3-b869-aef574742a6f |  | note | Records Required: Post-seal Inspection Form
label | f63d8912-13ec-5aa0-9486-fc80edcc08d4 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | PTR Rolling pattern
label | 474bb046-0c4f-5352-9875-48b76fa17b10 |  | note | I
label | d87e1cca-d786-5557-8f84-5544d187a0e0 |  | note | Reference or Specification: NZTA P/17
label | 2a63f91e-e0bf-5ef7-8472-5e8d2aab3870 |  | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
label | c118b2aa-adc1-5e38-a54a-7b4d3afc7dac |  | note | How Often? Per Site
label | 6b1e32df-e7ae-50b2-b01b-26c2e8573bd0 |  | note | Records Required: Post-seal Inspection Form
label | ecc8f986-84bc-5183-bf3b-43c73333a33c |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Traffickating
label | 2f17eedd-1c14-5ee3-b2e6-520538cc6760 |  | note | I
label | bb0e2520-ef31-5140-a95d-f0521a291d76 |  | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
label | 4dfeb8f9-e497-56b7-912e-e86e4fb7ad73 |  | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
label | 220569d7-faa8-56d0-8ada-a728375065d4 |  | note | How Often? Per Site
label | a215a066-9bc5-507b-969e-1bc200718129 |  | note | Records Required: Post-seal Inspection Form
label | 251531fa-20ba-53fb-b02d-de284112e81f |  | note | Responsibility: Site Foreperson / STMS
checkpoint-status |  |  | checkpoint | Tagging for line marking
label | 705f2b9f-7dd4-5e9f-a7aa-83889051ea7d |  | note | I
label | c5f207a9-78f4-561b-8eab-945e7d7073c6 |  | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
label | 70e9aeb1-6c4e-58f0-9030-b1943e993e2c |  | note | Method/Test required: Pre-seal Visual check
label | fc9f0fac-2cb1-5014-bb03-acc01e400e05 |  | note | How Often? Per site
label | f501e1d9-f989-522a-bea6-23debfd7074a |  | note | Records Required: Post-seal Inspection Form
label | f4be5c95-bfbe-588c-ae20-d8e4be15dad9 |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Post-Sealing Surfacing Condition
label | ccc1d4a3-83ab-5b1f-bbf0-01897f6531d5 |  | note | I
label | 78ce75f5-5d14-5b0f-815b-e23210d2cedb |  | note | Reference or Specification: QMP
label | 8d7fb714-cd73-5bb6-a46c-5e6bf07c3246 |  | note | Method/Test required: Visual check
label | db82106c-2f07-5ab7-b520-44293891ca29 |  | note | How Often? Per site
label | d159eaab-cb01-535c-ad11-949196f03c3a |  | note | Records Required: Post-seal Inspection Form & Photograph
label | b6b1b3c4-cabc-5081-b309-1e91d676ce10 |  | note | Responsibility: Site Foreperson
checkpoint-group |  |  | section | 4.0 Post-Construction
checkpoint-status |  |  | checkpoint | Linemarking and RRPM Reinstated, Matches previous linemarking - within 48 hours of sealing
label | aca83171-09a4-5ca3-9353-e36731410e80 |  | note | H
label | 9f2d5f41-c7ec-5a4b-ac37-1059350cfbe7 |  | note | Reference or Specification: MOTSAM
label | a58910b8-0001-5425-b085-ea741d486c31 |  | note | Method/Test required: Visual check
label | 1f0576e2-78a3-58e6-81a0-e38799f46b95 |  | note | How Often? Per site
label | f7be1a21-ccea-54ea-a72d-53dfb53c1c74 |  | note | Records Required: Photograph
label | 78ae8dda-a490-5dfa-ac94-40752e6ed483 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Spray Sheet/s Checked & Supplied for Claiming
label | d6e109a0-a82d-58d7-bade-1185937c2937 |  | note | H
label | 12512d2d-31b6-570f-bfaf-5edadd2e5736 |  | note | Reference or Specification: QMP
label | 44de06ad-7231-52aa-a0df-31039a764fd6 |  | note | Method/Test required: Spray sheet data verified against design/programme
label | 7540dc3c-e6ca-526f-8175-1ac266e766fa |  | note | How Often? Per site
label | 45c11bd7-d87a-5f88-8dbb-69560eef0fad |  | note | Records Required: Spray Sheet/s
label | 61c78ccc-c35f-575d-b9fe-ac3c36099eb7 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Collect & Upload RAMM data
label | 9872be1e-2d6c-5fa1-8558-ad3e19dc8043 |  | note | H
label | de930a93-34b8-5d74-8cc7-1f71756fce73 |  | note | Reference or Specification: Comply with Waka Kotahi format
label | 5b9e4a8e-3668-5af8-b238-9f2bf2d814b5 |  | note | Method/Test required: Correct data supplied
label | 66c48a97-e042-59b4-8fa9-4ed3e13db94c |  | note | How Often? Per site
label | b590a342-1510-5d18-8a3c-717e39aa2069 |  | note | Records Required: Spray Sheet/s & Photographs
label | 40ee1d1f-0b7b-557c-b01b-10265ce39e8c |  | note | Responsibility: Renewals Manager
checkpoint-group |  |  | section | 5.0 Out Of Season Sealing
checkpoint-status |  |  | checkpoint | Out of Season Sealing
label | 606d6a13-e8e4-517f-855f-749cab707094 |  | note | H
label | 652df943-3eec-5744-b925-c984ae02af6d |  | note | Reference or Specification: Winter Surfacing Site Note
label | 7e2173e3-d1ef-530a-951a-58be16aae7d9 |  | note | Method/Test required: Waka Kotahi Approval
label | b1cbb982-60ef-538e-afcd-b8452eeae752 |  | note | How Often? Per Applicable Site
label | 2d3aa446-22f2-5835-9148-15df363ef8f3 |  | note | Records Required: Copy of Waka Kotahi Approval on-site
label | 4499ba86-069d-5732-91bf-9e9669835037 |  | note | Responsibility: Project Manager / Renewals Manager
checklist-flat |  |  | checklist | Verified Program |  |  |  |  | Yes | Verified Program | 2fe02575-2c1b-48ff-baa0-0dd27deca0fa
checkpoint-status |  |  | checkpoint | Verified Program
checklist-sectioned |  |  | checklist | ITP - Resurfacing |  |  |  |  | Yes | ITP - Resurfacing | 5c426b84-eb5f-4995-a622-d9ebaf03f148
checkpoint-group |  |  | section | 1.0 Pre-Work
checkpoint-status |  |  | checkpoint | Approved JMF for Strengthening Repairs Mix (if required)
label | 614627f2-b74d-572a-93c2-1206b9d70a36 |  | note | H
label | a4599147-a955-5e59-afb7-8a072cabeb4e |  | note | Reference or Specification - Design Report
label | f25a13da-a035-5d65-87fb-406cfbae7e6d |  | note | Method/Test Required - Confirm approved JMF dates in Design Report
label | b36050ca-3467-5d12-ab7d-3a08e898d891 |  | note | How Often? Each site
label | 73b3c01e-ddde-5626-b1ac-c8d5b1ebd76a |  | note | Records Required - Copy of Approved Design Report
label | c376fcaf-eb4c-5879-92b3-364fa475b5e2 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Approved JMF for Pre-Level Mix (if required)
label | d813c995-78b9-5365-9e89-8f7a71674d45 |  | note | H
label | b0633d86-1045-567d-bae6-da3566d8afeb |  | note | Reference or Specification - Design Report
label | 670c37fa-920d-5fd5-aed0-6e13c22d1d24 |  | note | Method/Test Required - Confirm approved JMF dates in Design Report
label | 04d5ee12-4df0-527e-93c3-81c1063bbc17 |  | note | How Often? Each site
label | a67a0c72-bbcb-5327-9e26-73eb23ff9bb7 |  | note | Records Required - Copy of Approved Design Report
label | c9cc4d17-5dea-51ef-bec0-c7e5e69d51c3 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Approved JMF for Wearing Course Mix
label | 23f34bbb-d9a1-5f1e-b6e5-754fffbf8417 |  | note | H
label | 176691ad-808e-595f-a8ce-f78a009425ec |  | note | Reference or Specification - Design Report
label | a812eef0-95d1-5f5d-9e8a-de1731637260 |  | note | Method/Test Required - Confirm approved JMF dates in Design Report
label | 0f3c22bf-8763-54b1-89b3-55bf457a7613 |  | note | How Often? Each site
label | 50161ef5-97a8-587c-8999-54ed96ed13dc |  | note | Records Required - Copy of Approved Design Report
label | d8dce541-23bb-5520-921d-571da2d5456b |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Approved Design Report
label | 638614c2-e5e1-5620-8064-19752bbc689c |  | note | H
label | 487064df-d9a1-5d3b-9c89-e9c279384360 |  | note | Reference or Specification - Design Report
label | 21fbd821-af9c-58fe-b7b2-7678d6adeff5 |  | note | Method/Test Required - Confirm document on-site
label | a9683f08-17db-58d1-9003-d7f9a894bbfd |  | note | How Often? Each site
label | e41c3d6e-014f-5dc8-8fc3-959fb316e386 |  | note | Records Required - Copy of Approved Design Report
label | 338722f8-ad38-5c3c-a45e-fb634921d99e |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Treatment of affected Service Covers (to be raised or protected)
label | b626627d-f299-5a46-a85a-4e8672fa2137 |  | note | H
label | 00a3c5a6-b7da-5e74-9740-398d86296fac |  | note | Reference or Specification - Job sheet
label | b5d2e7bc-9980-5180-a769-3c81b2752ce4 |  | note | Method/Test Required - Confirm plan in place
label | 7e953416-76c4-598b-a310-917a254412c5 |  | note | How Often? Each site
label | 60079e14-430e-5914-82ec-e83b42a7d074 |  | note | Records Required - Job Sheet record
label | 227a205e-7f87-552d-98f8-dec815c5b7e4 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Stakeholder Management Requirements met
label | 2d349e5e-e7e4-5bea-938a-a3e1c06ea3b4 |  | note | H
label | 57014eea-2650-5122-a56a-a246f267e1b0 |  | note | Reference or Specification - CSCMP
label | d43ad804-14e0-5be8-a08c-6a47fbb0f124 |  | note | Method/Test Required - Confirm requirements followed
label | ac8e2abe-702f-5768-bdc1-276a2d263151 |  | note | How Often? Each site
label | 9d4b6897-cfd7-5e6c-af50-ec2809570fe0 |  | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
label | 25028f5e-0e68-5100-a8a9-a8c3df0fd833 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
label | 408e6f58-2477-5ffd-b344-ce665f954cd5 |  | note | H
label | 8612560e-25a2-585d-9ba2-8cd258ae28e6 |  | note | Reference or Specification - QMP
label | e1209e46-8acc-5e69-8cd5-be5c1481535b |  | note | Method/Test Required - Brief all team members on day’s work plan
label | a1e6276a-6c57-54a3-8b52-200203208e8b |  | note | How Often? Each site
label | 295d5654-1d54-5c96-9075-c70d2c8e9e71 |  | note | Records Required - Daily diary
label | 02e7d41e-68d9-5f50-9c4a-4cdaaf5f23a1 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Confirm if any environmental protection is required
label | 943e1b8f-1fab-57ec-8e14-62a5cafc962b |  | note | H
label | 887612ab-7ea4-50a5-93f5-4b74f875f9f3 |  | note | Reference or Specification - ESMP
label | 191c1918-08bf-5423-bb34-f27a92eb8787 |  | note | Method/Test Required - Record decision
label | 2f3ac495-f88c-5f09-908f-7cc5723eeb64 |  | note | How Often? Each site
label | 014fd651-995c-5a87-a03c-c534463fb482 |  | note | Records Required - Job Sheet record
label | bbf6b828-0f7f-5282-9297-ded97af60776 |  | note | Responsibility - Project Manager
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | Ambient Conditions - Pavement Surface Temp ≥ 5ºC (Intermediate or structural layers) and ≥ 10ºC (wearing course) and forecast to rise
label | bea5a76f-e571-5b48-8afe-64e1233565b4 |  | note | H
label | 078e3f1f-429b-5f77-9791-4f39d50400c4 |  | note | Reference or Specification - NZTA M10: 2020 9.5.2
label | fb0c6aa1-4429-542e-8a56-7aeccb9aab5a |  | note | Method/Test Required - Temperature Gun Check
label | d6619223-8d12-5d1e-95d1-9adf03ec1117 |  | note | How Often? Each site
label | 2b7b46b8-7ea2-5f00-b057-ccc59cb68aa8 |  | note | Records Required - Job Sheet record
label | 3571fcc7-4440-5ef9-a337-a29ccc846412 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Job start, identify risks and controls, communicated to team
label | f8e86750-39df-527c-83cb-e0b2513eddf7 |  | note | H
label | ffd7d8c6-18fd-543f-944c-6f1eaade95c7 |  | note | Reference or Specification - HSMP
label | cad2d865-8ba6-5f27-bc7a-6da709a04be0 |  | note | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
label | 359f8519-f970-54e2-ab58-2a470d78cb58 |  | note | How Often? Each site
label | ede2b1ef-0f23-56c6-a7e9-9f7239597eb2 |  | note | Records Required - Hazard ID form
label | 44be61e7-6356-5654-ba3d-f4f2e57207e9 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Establish traffic management to plan
label | bf779cbf-9fe6-59a8-a815-4de28db97bbf |  | note | H
label | 84d0fae2-17f0-5c1a-8612-1209f0ae2d2b |  | note | Reference or Specification - TMP
label | 40c8e5c3-5e8a-5cb2-8ba3-85909f681777 |  | note | Method/Test Required - Site audit post set up
label | 9dfcbd02-e48b-50f9-b525-8f80e1846e19 |  | note | How Often? Each site
label | 54922c69-ddeb-54d7-9088-e9dc4f9894ab |  | note | Records Required - TTM diary
label | 7c4ecd00-9090-53e7-bdec-d1cc3fda8456 |  | note | Responsibility - STMS
checkpoint-status |  |  | checkpoint | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | 2f0cd4b4-2f61-5498-9bb5-d269a2dda676 |  | note | H
label | 603c8afb-1a2e-56ca-bcb7-1b2a864429cb |  | note | Reference or Specification - Design Report
label | 07c4dd0b-2113-53e6-b2ee-28f1f2cc6161 |  | note | Method/Test Required - Record as-built site dimensions
label | 355ffec6-e4b7-527a-87e7-70f161f02f74 |  | note | How Often? Each site
label | 6387ef6d-e132-5540-8a3e-a3db8ebc14ea |  | note | Records Required - Job Sheet record
label | cdb28a15-4b23-5218-bded-2797f173666c |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Identification of Services; Service Plans on Site; Shallow Services Marked
label | 7a3ff944-de0d-5e9d-8c8d-b0fd0ec46291 |  | note | H
label | d8fd0243-e8e7-5172-b709-668789f58d38 |  | note | Reference or Specification - SOP
label | ab35c67b-2c2a-53ef-955b-a570fabcc3f2 |  | note | Method/Test Required - Confirm document on-site / Visual check
label | 83f633a6-3a40-5073-b21f-2f796effbf6a |  | note | How Often? Each site
label | bc8bf08a-b50f-5ede-ac73-8b64d931507f |  | note | Records Required - Job Sheet record
label | be544faf-513a-513e-a016-e8790600e63e |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Record & photograph environmental protection measures installed
label | 814ac63c-b716-552b-85bc-54ba6e60274b |  | note | I
label | b25fdae7-2fa1-5bde-aec7-f72786775548 |  | note | Reference or Specification - ESMP
label | 7e0ec370-bc41-5eb4-8fb7-87046bbbc531 |  | note | Method/Test Required - Record temporary measures
label | 5f658e7c-84f2-5b88-8020-f07c9bd55f97 |  | note | How Often? Each site
label | 2a8d9a7d-3847-50aa-b052-20c2ab7caf11 |  | note | Records Required - Job Sheet record & photograph
label | 1ad6eabd-76ef-5f7e-9cc7-7f4855d376d1 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 3.0 Milling (If Required)
checkpoint-status |  |  | checkpoint | Milling undertaken to correct depth - +/- 5mm nominal thickness
label | 8a8e9c8a-3759-5e84-be41-117191ba5ce0 |  | note | I
label | be2b601a-be94-516f-974c-6dfdad45ee46 |  | note | Reference or Specification - Design Report
label | 25e2ce9f-922e-554e-920d-27c9f29fe3fb |  | note | Method/Test Required - Dip checks
label | 7588ed96-5774-51c6-a3ae-9218a07a4bad |  | note | How Often? Per site
label | 777f14c7-7213-51db-b298-8c679b85ca5d |  | note | Records Required - Job Sheet record
label | e112f572-b4a5-5d5b-97b8-4a47eefd5d25 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Exposed Basecourse waterproofed / levelled
label | adf5023d-bb89-5359-a278-e0488036bb4b |  | note | I
label | a0bf61f9-2359-5da6-98d6-dcccf99d1731 |  | note | Reference or Specification - QMP
label | 972be135-70f3-5b68-8093-d7f3e4cfbfbb |  | note | Method/Test Required - Acceptable / Unacceptable
label | e5731728-63d5-5fe7-b1f7-28336c7586af |  | note | How Often? Per site
label | b52fe598-19eb-5014-8fbf-bf13d3d52be5 |  | note | Records Required - Job Sheet record
label | c5d177d8-8990-553a-b4b0-4221462ce6eb |  | note | Responsibility - Site Supervisor
checkpoint-group |  |  | section | 4.0 Membrane (If Required)
checkpoint-status |  |  | checkpoint | Application as per Design Requirements (Chip size / binder application rate)
label | 583c15fc-df7f-5e3e-a4a3-39577649a44e |  | note | I
label | 067a3eaa-3c59-54e7-9137-4d5771d93ed8 |  | note | Reference or Specification - Design Report
label | e56b41b7-6556-5970-8974-9b5068c60b82 |  | note | Method/Test Required - Spray Sheet/s
label | 16195792-9dec-508b-8d1d-3e5f6f2e8df6 |  | note | How Often? Per site
label | 3577ef15-03f8-5850-a79c-9347cd0975c5 |  | note | Records Required - Job Sheet record
label | b9d75f4a-8323-551d-896e-834ed132d543 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 5.0 Strengthening Repairs (If Required)
checkpoint-status |  |  | checkpoint | Delivery temperature - +/- 30 degrees from recommended mixing temperature
label | 351d5799-fe31-517f-af5a-f5c0d8f178b2 |  | note | T
label | 4eeb35bf-4556-5dde-aa5d-5a30e2a0d5e4 |  | note | Reference or Specification - NZTA M10: 2020 Notes
label | 3327c1a7-31d9-5945-81b7-58a87a7fa770 |  | note | Method/Test Required - Temperature Gun Check - Acceptable/Unacceptable
label | 4e796713-5a1d-5d66-b6de-29977f24f5de |  | note | How Often? Per load
label | 910e079a-de35-5a57-bc1d-61253781f6ed |  | note | Records Required - Job Sheet record
label | ab762ed2-df41-59af-8e21-257f61891c48 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Structural Asphalt Layer Thickness - Each Layer >55mm with ±10mm nominal thickness
label | 926223c7-1d7f-55b5-a07b-b99528d3b2c4 |  | note | T
label | dc98884d-724b-5c6a-9a0c-637b6d18bdc9 |  | note | Reference or Specification - NZTA M10 2020 10.1 & Table 3.1
label | 9fd39cdc-d8ec-5ce3-8270-774d6559c085 |  | note | Method/Test Required - Dip checks during paving process / Cores
label | a4153b81-50a5-5316-be12-53398e74a21d |  | note | How Often? One test per patch & / or One test per 300m2
label | c0991e61-0342-5de4-a888-cc2185e22e5a |  | note | Records Required - Job Sheet record & photograph
label | 7a08ab87-ea9e-5009-966c-887074750793 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Compaction and Air Voids
label | a3fcbc42-cf2a-55fb-b8ae-9d06904f39d3 |  | note | T
label | 9914f104-b957-5f60-89ea-eab837d0d2bd |  | note | Reference or Specification - Paving SOP
label | 2a1b2772-9bc6-599c-bbc4-cbd5f6773dc1 |  | note | Method/Test Required - NDM for Quality Control Only
label | 40f8216d-4cc8-5f51-b063-ac2fb005d26a |  | note | How Often? One test per patch & / or One test per 50m2
label | 6303ac61-a073-55dc-be7b-54b4a63c040d |  | note | Records Required - Job Sheet record & photograph
label | b679ec4a-fbf9-5830-ab6b-e7358eb3a886 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 6.0 Pre-Levelling (If Required)
checkpoint-status |  |  | checkpoint | Delivery Temperature - +10 / -30 degrees from recommended mixing temperature
label | 131994ed-a516-55a1-b26d-dcf61235ab63 |  | note | T
label | 8e14229a-8897-565e-9074-08c1e6890f3f |  | note | Reference or Specification - NZTA M10: 2020 Notes
label | f2113701-9ba2-5d3f-8b64-7f6a1b56e3df |  | note | Method/Test Required - Temperature Gun Check
label | a5d5ffab-a640-5143-996e-1008cfcf2875 |  | note | How Often? Per load
label | 7cc30d20-2262-5892-80a5-cdd2d4271dad |  | note | Records Required - Job Sheet record
label | 0aebda4f-e367-5216-8454-8791e13c5082 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | -5mm / +5mm below bottom of the nominal thickness of wearing course specified in Design Report
label | 9b6a647a-bc3a-5235-bed6-8845f7932277 |  | note | T
label | 49dbea31-65d4-5751-8ed5-8736662c591b |  | note | Reference or Specification - Design Report
label | f053f8dc-1306-5081-86f5-1886d9dfdde7 |  | note | Method/Test Required - Dip checks during paving process / Cores
label | 5452f2c8-ca44-5228-9f78-8c425ce48f30 |  | note | How Often? Every 15m
label | 629d8f64-3488-5350-9c63-c96621c639d4 |  | note | Records Required - Stringline Sheet record & photograph
label | 3b38bfa3-8230-5208-80b3-ec52c6f0f8a5 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 7.0 Wearing Course
checkpoint-status |  |  | checkpoint | Delivery temperature - +10 / -30 degrees from recommended mixing temperature
label | 6f872f9c-af36-5256-bacc-d3767cd15e2c |  | note | T
label | c74fe05e-07a3-58eb-b686-c4b1667335be |  | note | Reference or Specification - NZTA M10: 2020 Notes
label | 5e7ef251-6857-5746-96e6-aa57c9ded494 |  | note | Method/Test Required - Temperature Gun Check
label | 0ddd6702-dd61-5631-8a7f-68b7adc5eb6d |  | note | How Often? Per load
label | 468e8150-0322-58a4-8cf5-7c64e48ad9e7 |  | note | Records Required - Job Sheet record
label | faff4c48-47a2-567d-8032-b5445f0cf171 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | -5mm / +10mm nominal thickness specified in Design Report; If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report
label | 5ec1ca8d-e237-52fb-a727-2ca4397ea596 |  | note | T
label | 6dbe44e5-01e3-5af4-b574-8cdba769be91 |  | note | Reference or Specification - NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4 or NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1
label | f6e408a7-84f9-585f-b340-8a8266274440 |  | note | Method/Test Required - Dip checks during paving process / Stringline Sheet
label | f71a61d8-252b-5214-a29b-65149cf1402b |  | note | How Often? Every 15m
label | 16b3497e-142b-5f92-9c3f-4f6aa3d55959 |  | note | Records Required - Stringline Sheet record & photograph
label | 804441f2-0ff3-576a-ad1b-2e8184c9e280 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Compaction and Air Voids (1)
label | 2fab9f12-6bf1-57f8-a333-469d1c975ccc |  | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset (1)
label | e7c3233d-5582-52e7-995b-4e45ff99a59b |  | note | T
label | 1bf0bc7f-c182-5cd0-833a-b2848c0bde94 |  | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
label | b1d6d6ff-72e3-5939-8ea1-f638a90c4865 |  | note | Method/Test Required - 150mm Diameter Cores where: 1. >30 tonnes 2. >=35mm lift thickness
label | 63fc0fce-ac00-5229-a290-3acde03d8959 |  | note | 100mm Diameter Cores where: 1. >30 tonnes, 2. >=35mm and <40mm lift thickness
label | 0937fa2a-d600-5bc1-8379-b959701219d8 |  | note | NDM (only where accepted by the Engineer in writing along with the testing plan.)
label | 2c4db492-f7d2-5691-aeb2-8ed080deb389 |  | note | How Often? Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
label | f0dfb116-8d9a-5714-a325-6e9872a1a2c3 |  | note | Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
label | 2f2b76d0-4c58-52f9-a1fc-a9a96365e04d |  | note | NDM (only where accepted by then Engineer as per agreed testing plan.)
label | 3c62b41d-ee55-5de1-bc12-208fe596e8dd |  | note | Records Required - IANZ Accredited Laboratory
label | 299f1949-874f-5f57-8073-f0a34bbfa9d5 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Compaction and Air Voids
label | f5f32eab-ea3d-5a33-945d-ecea0e4cb47c |  | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset
label | 9c1b31a5-28ae-5fd6-923c-9c215c3a15d2 |  | note | T
label | 0e5d3342-e9f3-5e41-9702-a6a1d3e25023 |  | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
label | 42fee68a-dbdf-5155-84be-61c41078dc02 |  | note | Method/Test Required - NDM for Quality Control Only
label | e7349063-4673-5c10-9ebd-806ecfee237d |  | note | How Often? Every 20m alternating wheel tracks
label | 19d04f1c-0d62-505f-8d47-41fdc8d7cd5f |  | note | Records Required - Job sheet Record
label | a787d75b-d3f7-52b3-ad49-a18b41370b90 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Post construction surface condition
label | f7fc67db-13c8-5e79-8607-b7db6dee8916 |  | note | I
label | 1fcea953-933b-5002-b881-dbe814b1dc2f |  | note | Reference or Specification - Design
label | eaea649d-c0e7-5071-ad45-63bf7d5c6cb4 |  | note | Method/Test Required - Acceptable / Unacceptable
label | 1b9276a6-ab08-5fb7-b219-6a31b0070319 |  | note | How Often? Per site
label | 3c278b74-c546-5a2e-9c35-c10e9ec96a66 |  | note | Records Required - Job Sheet record
label | 96ae3576-2e7d-5e2d-a861-af6ad4062c42 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Supervisor to provide an update regarding site completion per shift
label | 4c216096-0e87-53e1-9231-d53b76a89bf2 |  | note | H
label | 309c288d-8e91-5a79-a3e8-2380dfd09c8d |  | note | Reference or Specification - Design
label | 076ff0dd-5d92-5918-8cd1-cfb298b7f288 |  | note | Method/Test Required - Acceptable / Unacceptable
label | 22c565ee-8a3f-5ab2-aab2-b15713491eb8 |  | note | How Often? Per site
label | ab8d98cf-ba0f-531b-9941-130b6893da44 |  | note | Records Required - Email
label | 8adbdc45-e40c-5e7e-925e-b528096857ab |  | note | Responsibility - Site Supervisor
checkpoint-group |  |  | section | 8.0 Post-Construction
checkpoint-status |  |  | checkpoint | Linemarking and RRPM Reinstated - Matches previous linemarking - within 48 hours of sealing
label | 26f66010-2c1f-5193-b755-7da2b6586d7d |  | note | H
label | 196858d7-ae78-560d-b3bf-3f6d9df8571a |  | note | Reference or Specification - MOTSAM
label | 4746cf38-c61b-52c9-8829-f5194575146a |  | note | Method/Test Required - Visual check
label | fada7c38-fa31-595b-b43f-2084ddf32e12 |  | note | How Often? Per site
label | 8dccb2b8-51ab-5c96-b30e-3ff055b833a6 |  | note | Records Required - Job Sheet record & photograph
label | fa5faa76-b439-5be8-887f-c63eb13001e2 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | As-Built records – structural patches
label | 935ea45b-6584-5e50-ae21-93d34b2e5bc7 |  | note | H
label | 7c9daba6-8ddc-5baa-854b-61ab7ac3c326 |  | note | Reference or Specification - Design
label | 7a408df1-1295-5e5a-bea5-1b714605afaa |  | note | Method/Test Required - Record as-built patch dimensions & RPs
label | 64d2438a-6742-5828-b5d3-1b956e19060b |  | note | How Often? Per site
label | 38b0a551-11c9-5b1c-bb4c-89997dedd85f |  | note | Records Required - Job Sheet record & photograph
label | 153935c2-7dad-586e-aa78-c9b070321325 |  | note | Responsibility - Project Manager / Site QA
checkpoint-status |  |  | checkpoint | Collect RAMM data
label | bcf21609-1837-59a6-a588-a53202a2ee4d |  | note | H
label | 058a5f7c-01a1-538e-9bfd-2796241cc6ae |  | note | Reference or Specification - Comply with Waka Kotahi format
label | a4a38c8b-0b1a-582e-9f03-014b890ff567 |  | note | Method/Test Required - Correct data supplied
label | eaa3f37d-fec4-583c-982a-ce38bdbbba20 |  | note | How Often? Per site
label | e8fa2c04-0f73-5027-9ab4-14b6f656ee49 |  | note | Records Required - Job Sheet record + As-Builts + photographs
label | ffcc6258-3347-5679-a400-60de354c79ff |  | note | Responsibility - Project Manager / Site QA
checkpoint-status |  |  | checkpoint | Compaction as per sample test results
label | faa49363-a106-5600-b37a-4d8c74a3a9fd |  | note | H
label | 716b00bc-877a-5b27-ada2-9c9a6851ffc5 |  | note | Reference or Specification - JMF Design Compaction
label | d3652934-d117-53ea-802b-816a68ebf02b |  | note | Method/Test Required - Mean ≥95% ; Minimum ≥92%
label | 58f44573-616f-5a80-a390-b0082d3c6a22 |  | note | How Often? Every 20m alternating wheel tracks
label | 68fe9569-1e89-56eb-97e0-0fdad5deafed |  | note | Records Required - Post-Verification Testing and Report from IANZ Accredited Lab
label | 6c555cc4-c940-5da6-8131-19beef47ab9a |  | note | Responsibility - Project Manager
checkpoint-group |  |  | section | 9.0 Out Of Season Paving
checkpoint-status |  |  | checkpoint | Out of Season Paving
label | df1092ba-0d46-5c88-90a2-d32a548a930d |  | note | H
label | f840efb0-c8b3-586f-a6bd-b99f174e14a9 |  | note | Reference or Specification - Winter Surfacing Site Note
label | 9eca0f66-d4d1-5edd-bfe6-293d09ada857 |  | note | Method/Test Required - Waka Kotahi Approval
label | 21c0c8d3-1928-536b-afd7-547f18100d23 |  | note | How Often? Per Applicable Site
label | 55a74489-fd47-5c73-b10c-6c202215f413 |  | note | Records Required - Copy of Waka Kotahi Approval on-site
label | 0344772a-0682-551a-8258-d792fd478326 |  | note | Responsibility - Project Manager / Site Supervisor
checkpoint-status |  |  | checkpoint | Dispatching Temperature compliance
label | 1bbbc46b-f35a-505e-b460-56f41d780c60 |  | note | T
label | 1abe0390-e45c-53a2-a8d0-90cec27f8fdc |  | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
label | 313dbd80-484a-53f5-8b73-d8f816153fd9 |  | note | Method/Test Required - As per Table N4.1: NZTA M/10: 2014
label | 37b25f77-34b7-5180-b98b-29229a33b0ff |  | note | How Often? Per Load
label | 4f66d4d7-c688-5365-a3c0-c6b0ece7b59e |  | note | Records Required - Job Sheet record
label | 27f1a569-90dd-5440-885e-2616f5007321 |  | note | Responsibility - Asphalt Plant Manager
checkpoint-status |  |  | checkpoint | Arrival and Compaction Temperature: 110-170°C - To be recorded when mix is tipped into the paver.
label | b8fb8fe1-9d51-56f2-9575-5dfd7d6009c1 |  | note | Manager to be notified if temperature falls below:
label | 854e129f-6e98-5b97-a877-014a49cde3ea |  | note | SMA9.5 134°C
label | 49f81d3f-ef5d-505e-9141-dd7aea3c2b5d |  | note | SMA12.5 134°C
label | 0999946b-ce68-55c4-a1e7-14acfd8ae309 |  | note | SMA11 134°C
label | a9eb564e-6f7e-56d3-be86-9dce12defd12 |  | note | AC20 145°C
label | 9098d435-3a02-5f35-b613-3d814d4596cf |  | note | AC14 142°C
label | c86b7995-f621-5d72-94b4-b4c6df8a2f34 |  | note | If temperature falls below 110°C mix will not be used
label | a0eccb67-6042-5fe4-a147-777eebe467b9 |  | note | T
label | 97189927-6a15-5003-be91-6e0b3f582688 |  | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
label | b983561a-8520-542b-b6d4-9031654396a3 |  | note | Method/Test Required - Temperature Gun, Acceptable / Unacceptable
label | 7125037d-25df-52b4-bbf0-82ebe595ad26 |  | note | How Often? Per Load
label | c26dc2c5-fcb5-5fe6-8701-dfa0d738e6d8 |  | note | Records Required - Job Sheet record
label | 26fcfe2a-b929-5dac-8678-3955a2731d8e |  | note | Responsibility - Site Supervisor / Site QA
checklist-flat |  |  | checklist | QMP |  |  |  |  | Yes | QMP | 6161efe9-f0a4-47ed-973e-fe443cd024f1
checkpoint-status |  |  | checkpoint | QMP
checklist-sectioned |  |  | checklist | ITP - Granular Rehab |  |  |  |  | Yes | ITP - Granular Rehab | c15272b8-6989-46f0-b7c3-7f4fc6dcbdaf
checkpoint-group |  |  | section | 1.0 AP 40 M4 – Raw Aggregate Testing
checkpoint-status |  |  | checkpoint | Sand equivalent, or
label | 4d2cf821-6520-517d-89e2-f157321da96e |  | note | T
label | 40e57aaa-d5d9-5315-897a-14636bbc276c |  | note | Reference or Specification: Design
label | f9e7a357-cd45-5c73-ac52-251436925c1d |  | note | Method/Test required: ≥35 Unit of measure?
label | db1f0675-d026-5ed4-98b7-643dffe70408 |  | note | How Often? 1 sample per 500m3
label | 5e2b0a56-1333-5089-9d5a-e6dcdac1df8a |  | note | Records Required: Test Report
label | 7151d52a-76d7-5d08-9811-7a7b07fd45ee |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Clay Index (passing 0.075 mm), or
label | adc13250-18dd-5721-b72a-7774db43d903 |  | note | T
label | d70f3f03-e8d4-530f-b074-b01ecefaff13 |  | note | Reference or Specification: Design
label | 22eade97-91c1-57fc-a849-ca23b243417e |  | note | Method/Test required: <=3 Unit of measure?
label | ecbbd81f-a8f4-537d-ac1d-6fd46b75c8b5 |  | note | How Often? 1 sample per 500m3
label | e62f4a84-0e2e-59db-b079-85393c299beb |  | note | Records Required: Test Report
label | e5a3d3e1-49e4-5bae-8ba1-64810a107d1e |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Plasticity Index
label | 6466c61d-56b8-56eb-8ad4-3aed70989037 |  | note | T
label | 1dcf757e-8a2c-57e8-acc1-f5271302fd94 |  | note | Reference or Specification: Design
label | cddd3fdf-0ce8-5530-bd55-75b7cf384967 |  | note | Method/Test required: <=3 Unit of measure?
label | 9033373f-a8a8-5aef-9d75-54519f75b383 |  | note | How Often? 1 sample per 500m3
label | af29a198-296c-559c-9363-8023aef1e7fe |  | note | Records Required: Test Report
label | 48b18bfd-1c2f-5dee-b9e3-9b44269e6a9e |  | note | Responsibility: Project Manager
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | Particle size distribution
label | f8660252-3d97-50e1-9b24-e4bee69c630b |  | note | T
label | a92b4e01-de56-58e7-8468-17e86b81f1e7 |  | note | Reference or Specification: Design
label | 6ee26eda-ad2c-5938-b0b9-a46df3641603 |  | note | Method/Test required:
label | 4d6cc165-6e00-5a49-88ef-ca9f61066dbb |  | note | • 100% passing 63mm
label | f96f54c6-e9c2-5dd7-a82a-50f8ec198d76 |  | note | • 40% ≥ 65%passing 19mm
label | e364518e-2cee-5f83-989e-1768970372ca |  | note | • ≤ 10% passing 0.425mm425µm
label | 55bbfdb8-4249-56ff-83ab-f9a935b86299 |  | note | How Often? 1 sample per 250m3
label | eb926334-f237-53f2-9f2c-6c7e3c8dea65 |  | note | Records Required: Test Report
label | 8e7e8f87-a9ac-5d91-a70e-4492baefeac7 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Solid Density
label | 0f673e4e-1ef0-5c31-a4ad-e69efcf9260d |  | note | T
label | bfac5a10-9847-519d-9db6-6d0ac78bf455 |  | note | Reference or Specification: NZTA B/2 7.5
label | 4d13ad2d-f21d-5720-a7cf-d0b356458ea3 |  | note | Method/Test required:
label | 836e9828-fbc1-583f-a8b4-2d4ebb108583 |  | note | • Unit of measure?
label | 387bcbfd-864b-56e8-bfcd-175c9561d9b2 |  | note | • Tolerance?
label | cbe032be-b7aa-56cc-a842-a20bbf0ff17a |  | note | How Often? 1 test
label | 8addba43-addf-58a2-a024-70cff39f2116 |  | note | Records Required: Test Report
label | 2c35083f-121b-5324-ac11-d2586adfa957 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Determination of MDD & OWC
label | c382fc98-a0ab-5dd0-8c77-cf29859a8d6f |  | note | T
label | dc640a7b-e1fd-59ab-8ac9-e414d5066e97 |  | note | Reference or Specification: NZTA B/2 7.5
label | 63be52d9-6fc1-57cd-a779-e852616774d3 |  | note | Method/Test required:
label | 70296419-1b13-5031-b7d1-70b63def0d2e |  | note | • Unit of measure?
label | f6b13779-58ac-54e6-9338-6fed223a2a51 |  | note | • Tolerance?
label | b05a6c03-f72b-5a6d-85d7-9b10a4d15a89 |  | note | How Often? 1 test
label | 4d7f1c4c-73d9-5856-b1bd-fcfbe760d0bc |  | note | Records Required: Test Report
label | 5973aa65-b64a-57ca-b404-ec4b02517ebf |  | note | Responsibility: Project Manager
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | Stakeholder notifications undertaken
label | d9bb7c78-03d0-55c2-a148-29ef131f9971 |  | note | H
label | 4e1108c7-d070-5281-aae0-a4edba97d28f |  | note | Reference or Specification: CSCMP
label | 1134cb07-3254-5cca-b4fc-71e3361a6b15 |  | note | Method/Test required: Stakeholder notification emails and letter drops
label | 7dae037c-0971-54bf-bb92-8e40ca6b504b |  | note | How Often? Each site
label | db85e112-63cb-5d1f-9e9b-4dcee681e086 |  | note | Records Required: Evidence of notifications
label | e3285768-0dbf-5523-83be-4b8ae7f06811 |  | note | Responsibility: Network Manager
checkpoint-status |  |  | checkpoint | Mark-out of services and Permits in place
label | a2a5a143-068e-5f6c-92b3-0ad9fff01d88 |  | note | H
label | cf2baabb-d5c5-5856-8775-6586e90948a4 |  | note | Reference or Specification: HSMP
label | 2534efed-950d-526f-bec9-70faaf2b77b4 |  | note | Method/Test required: Physical mark-out of all services and signed permits
label | 4b21e569-ceb8-5e6e-b5ee-9d7917fe5d1f |  | note | How Often? Each site
label | ded77b56-cc00-5ca3-994a-56cd4885004e |  | note | Records Required: Signed permit
label | 3e328bd6-6d95-53a1-a748-53e41b51a13d |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Job start, identify risks and mitigations, communicate to team
label | 9d41bbee-bae7-506c-912c-8f23441d7caf |  | note | H
label | d2b5883a-7e96-576d-bd7a-e54b0259806d |  | note | Reference or Specification: HSMP
label | af869c72-4c95-5d1a-baef-8f49b59aab16 |  | note | Method/Test required: Record all hazards on JSEA and brief team
label | 0b5f397d-033a-5e10-8d7f-419ebf2eb0b8 |  | note | How Often? Each morning
label | c0bd7f07-f60c-53be-b7b7-3b393598aba3 |  | note | Records Required: Job start form
label | 22598b30-f560-504e-90c7-b6b50a57a113 |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | Set up traffic management to plan
label | c9b1a23f-3309-562f-89d8-48cf666e0d6c |  | note | T
label | 1d35345c-d03e-5217-b8d0-ccc0d12ff55c |  | note | Reference or Specification: TMP
label | 5d4b4c16-57cc-5710-9e5e-9e3fa8812125 |  | note | Method/Test required: Perform Site audit post-set up
label | 488be8df-3d9f-5f9e-96cc-2b83aa333e98 |  | note | How Often? Each site
label | 2566039b-c037-592b-80d3-1f85cbf63801 |  | note | Records Required: Daily Diary
label | f765b09d-b5d3-54c1-ac53-585df13d4594 |  | note | Responsibility: STMS
checkpoint-status |  |  | checkpoint | Assess environmental requirements of site and install sediment and erosion control measures if required
label | e12d909d-29d6-5d37-a6be-f61843cc8547 |  | note | I
label | d3e3992f-aedc-5207-85f1-702836ccc3b1 |  | note | Reference or Specification: ESMP
label | 0de59572-3914-5a6d-838a-ca46591ec597 |  | note | Method/Test required: Identify areas at risk and install control measures
label | 465caefb-1ec9-52b3-a0de-ff04acb14990 |  | note | How Often? Each site
label | 36555d0c-03dc-59ae-b411-c913c6150166 |  | note | Records Required: Daily diary
label | 5718283e-b05f-5c89-9e3a-b66e2580274f |  | note | Responsibility: Supervisor
checkpoint-group |  |  | section | 3.0 Basecourse Inlay
checkpoint-status |  |  | checkpoint | Cement Spread Rate
label | bf16d9bc-8f5b-57da-b829-708a2352dc6d |  | note | H
label | 9b811293-1d83-5b75-bede-ae4a2d58125c |  | note | Reference or Specification: NZTA B/5
label | 6a68f046-b2ef-5585-8b1c-4f6a51fa212c |  | note | Method/Test required:
label | 68ba3c08-d4f6-5b77-905f-032501337e49 |  | note | • ±0.5kg/m2
label | b096e5a4-7f4c-51fc-813a-f7e648555d54 |  | note | • Weigh mat: Every 400m²
label | fdfdce63-d212-5d51-b3f0-992c4c5cbe96 |  | note | • Average usage test: Within ±2.5% of the specified rate
label | 0f31b1cb-f744-53f0-8f46-4f19a5ed7793 |  | note | How Often? Upon emptying the spreader and bulk tanker
label | 33d8dd3a-78d5-56d6-a05d-c4a1a40553ee |  | note | Records Required: Cement Sheet
label | 83d56b0c-36af-5060-92f3-87ff7d6fb1b4 |  | note | Responsibility: Stabilizing Supervisor
checkpoint-status |  |  | checkpoint | Hoe and stabilise to design depth
label | eb0660a5-38db-5cfe-ba49-72c8d345588a |  | note | I
label | 31721692-6633-5822-9ed3-3a44e076a990 |  | note | Reference or Specification: NZTA B/5
label | 7a02c458-b75f-5079-b05e-556484f8aa3d |  | note | Method/Test required: -0mm / +20mm
label | bfb09783-69da-5fc6-9acd-1e8dd0f9c9ec |  | note | How Often? Per run
label | b3adb155-f7f8-5955-9f19-51f210abe61c |  | note | Records Required: Cement Sheet
label | e9e6ea49-5b10-5319-8aa3-337a1137c7a8 |  | note | Responsibility: Stabilizing Supervisor
checkpoint-status |  |  | checkpoint | Overlap longitudinal joints
label | afd0e67c-9fb1-584c-9a3b-8cad3b1d8be2 |  | note | I
label | 65d97dcf-ddca-52e9-8820-460a1ca5a591 |  | note | Reference or Specification: NZTA B/5
label | bed21a60-bda6-5bfc-948c-f42b870e3634 |  | note | Method/Test required: Record hoe-depth setting
label | f6e7f3ef-fd88-5667-b22b-294a4bb6c22e |  | note | How Often? Per run
label | f450dba8-c609-5982-8777-d61a1dcc4823 |  | note | Records Required: Stringline Sheet
label | 6c731e93-ccb3-5e25-93f0-df4bc702727d |  | note | Responsibility: Stabilizing Supervisor
checkpoint-status |  |  | checkpoint | Plateau density test
label | 78480592-72c1-519f-b144-de3712c26bff |  | note | T
label | dbff464a-b31c-5bfd-8102-cce2e86103cc |  | note | Reference or Specification: NZTA B/5
label | 9f233171-54fd-558c-8c71-ac6cc9404c91 |  | note | Method/Test required: 200mm overlap
label | d7c82225-022c-5a9f-a546-f40df3535128 |  | note | How Often? 20m centres each side
label | 10f235f4-9621-5b60-819b-866d3af32c40 |  | note | Records Required: Plateau Density Sheet
label | 8b1b533a-93f3-5dbc-a8fc-cdda2ca57ae3 |  | note | Responsibility: Quality Engineer
checkpoint-status |  |  | checkpoint | Confirm layer thickness
label | 1a8f87b1-8dd7-5a8e-bcca-a076b199753c |  | note | T
label | 9eca8c52-f26f-5eef-8e29-aa76d2e2db6b |  | note | Reference or Specification: NZTA B/5
label | 263e5fc8-9055-563b-9aa3-9cba9778a158 |  | note | Method/Test required: Nuclear Densometer
label | 28e3d9ae-7477-568e-aae6-2dcee381ad7f |  | note | How Often? 20m alternating wheel tracks
label | 78e33726-b2ca-5422-a15f-bc3e87c28e88 |  | note | Records Required: Plateau Density Sheet
label | c1345231-9ddf-58cf-b40d-0df8a9dfdbd4 |  | note | Responsibility: Quality Engineer
checkpoint-status |  |  | checkpoint | Compaction as per sample test results
label | 5c316744-7f26-531d-bbd4-816aa938e518 |  | note | H
label | cc0a7653-a96b-52e5-ba7b-b9d32bed51f7 |  | note | Reference or Specification: NZTA B/5
label | 043b2a5c-6517-5107-a919-6dbab6a49805 |  | note | Method/Test required:
label | 3398d414-5c9b-5b2d-a13d-06b18b49b1e9 |  | note | • Mean ≥95%
label | 11c94841-0e96-58ad-86c3-647234e6ebac |  | note | • Minimum ≥92%
label | 9e9de884-4bb4-50db-9308-b700cb7573ba |  | note | How Often? Every 20m alternating wheel tracks
label | 49173af8-d500-5efd-853c-5838382bb2db |  | note | Records Required: NDM Sheet
label | b76b3b52-3c94-5b50-b87d-5f99d4ef7544 |  | note | Responsibility: IANZ Accredited Lab
checkpoint-status |  |  | checkpoint | Impact hammer test
label | 680c8d34-ca05-5022-9099-1deea95b1211 |  | note | H
label | 7c2d6a11-6368-568f-9c64-a86fcfcef3af |  | note | Reference or Specification: Spec?
label | 196015ac-bcc8-5589-b25f-f6d47a2c27ea |  | note | Method/Test required: ≥70 CIV
label | 40a20b84-51a2-5c7b-b77c-32c0fc09d24d |  | note | How Often? Every 20m alternating wheel tracks
label | 259f8966-6dcc-5799-904d-55528f390b10 |  | note | Records Required: Clegg Sheet
label | 131017c0-2a28-5a3a-944e-ecc195e8ff27 |  | note | Responsibility: IANZ Accredited Lab
checkpoint-status |  |  | checkpoint | Confirm surface levels
label | bed4c548-1e0f-5d80-b4a4-e46ba226daa0 |  | note | T
label | 89a89dbf-2076-55f1-bf9e-8e7f08750010 |  | note | Reference or Specification: NZTA B/2 5.1
label | 387adf1a-4e89-59af-bdc1-603c6dcdd208 |  | note | Method/Test required: -5mm / +15mm
label | d21068b1-c78b-5d09-be60-d12348df6283 |  | note | How Often? Every 20m, full width
label | e917014d-1d21-5834-ba0a-a1d505541fb2 |  | note | Records Required: Stringline Sheet/As-Builts
label | d859786b-8c83-5799-a4e4-c73dbef89aad |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Surface Finish
label | 4629df34-1ea7-5406-ae47-b05f7165c7d3 |  | note | T
label | 05a81796-ccc5-5df8-8833-061ecbc7e71a |  | note | Reference or Specification: NZTA B/2 5.1
label | e660842d-8201-57e1-a32a-e6f1894ef1a8 |  | note | Method/Test required: -5mm / +15mm
label | 2bac587f-98cc-5960-a955-5fd1015003ab |  | note | How Often? Every 20m, full width
label | 0ba47bc4-4de1-57f6-b1bc-f3b81a335bde |  | note | Records Required: Stringline Sheet/As-Builts
label | 64b26e2c-fe93-5c96-a381-5d55f160299e |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Confirm surface levels
label | b69a9972-69aa-594c-bb92-e7708a82eead |  | note | H
label | febc5fe1-0d34-5940-abfa-c62c02de88b3 |  | note | Reference or Specification: NZTA B/2
label | db87e87a-d635-5a46-a552-7eb83d5a8467 |  | note | Method/Test required: On-Site Inspection
label | a3c7ce0f-48bc-5dc3-b238-67c235ff8a56 |  | note | How Often? Per site
label | 0ee85361-2f51-57bf-8045-fbc9760dfada |  | note | Records Required: Inspection between BECA/Higgins Staff
label | 7cb796ce-4d02-56cb-b417-1a2fb0dd1e62 |  | note | Responsibility: Renewals Manager
checkpoint-status |  |  | checkpoint | Surface Finish
label | a1ae4017-b135-52ac-a91c-3933ee03734f |  | note | H
label | 402c44bf-64a4-53d0-8543-fba480afad1f |  | note | Reference or Specification: NZTA B/2
label | f1dd320a-4d6b-55d5-8bf6-749813915f1a |  | note | Method/Test required: On-Site Inspection
label | 16d6bcbd-0df5-5e5e-98b4-7409eadbee39 |  | note | How Often? Per site
label | bc4b9e9a-8006-5c3d-b88a-121c5e804f34 |  | note | Records Required: Inspection between BECA/Higgins Staff
label | cc447cc4-61b6-5e60-b14e-4a379d4d6f63 |  | note | Responsibility: Renewals Manager
checkpoint-group |  |  | section | 5.0 Aggregate Testing – Sealing Chip
checkpoint-status |  |  | checkpoint | Crushing Strength
label | 7070f8d8-a0f5-57d0-8a3e-5824f4770671 |  | note | T
label | 748c5d9f-f7e4-5b72-b2b0-10f1bf06b808 |  | note | Reference or Specification: NZTA M/6 3.2
label | 4f866c38-8db4-5df1-ba87-5cc19f88e7ae |  | note | Method/Test required: <10% fines passing 2.36mm under 230 KN load
label | 7a8ded36-3778-5d35-a4b1-4d0a8d4de65e |  | note | How Often? 1 Test
label | beaa1565-22e3-59db-934d-ef72a58285eb |  | note | Records Required: Test Report
label | aea084fe-1f33-5d72-bb02-19fa6baf9280 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Weathering Quality
label | 9d9317af-5f3f-5f2a-86dd-d8733b7d5219 |  | note | T
label | 92499d89-57aa-5d15-9016-c90bb4dec94c |  | note | Reference or Specification: NZTA M/6 3.3
label | 169e6599-35e7-56b0-b968-833a3e3a0816 |  | note | Method/Test required: AA or BA
label | f06690c6-2e3d-5d33-a4b8-2b642be48f06 |  | note | How Often? 1 Test
label | 8bcdb6e6-65df-51df-9c0a-d8d5530e08f8 |  | note | Records Required: Test Report
label | 5bcb59ab-0e00-5aaf-a842-8c074e45c8b2 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Polished Stone Value
label | 8cafa7a5-85a4-581e-9155-f3e60813c009 |  | note | T
label | 5d170ef9-dd35-5933-964c-80054b3a1a85 |  | note | Reference or Specification: NZTA M/6 3.5
label | b7abbb26-4083-55e7-9430-cd44d52bf847 |  | note | Method/Test required: PSV Required = 52 min
label | 31066e80-2007-547c-b67b-2455d6f67c0b |  | note | How Often? 1 Test
label | 530a2762-d03a-5b27-8e8c-50150d26190f |  | note | Records Required: Test Report
label | 3a130578-c3f7-56ee-8d29-1d674d8c35e5 |  | note | Responsibility: Accredited PSV Testing Agency
checkpoint-status |  |  | checkpoint | Cleanliness
label | b69296ea-2e07-54e3-906e-b65dcb100599 |  | note | T
label | da6bb7ab-a42b-5ff2-8ce5-f41cc58e6dac |  | note | Reference or Specification: NZTA M/6 4.1.1
label | 2078bb69-dc2e-58be-8806-0a567c980fdf |  | note | Method/Test required:
label | 7ee7e749-29d0-5a20-8082-e1ab6ebf717d |  | note | • Grade 5 – 89 min
label | 41d6dfcc-6d05-5f27-acab-0acc92ae4466 |  | note | • Grade 3 – 87 min
label | bccbe0e5-c8ac-538e-8ad4-820da49a133a |  | note | • Grade 4 – 85 min
label | c2e3b567-f226-5344-b641-f4562ae52d52 |  | note | How Often? 1 Test
label | 97c54b40-18ae-5800-9726-317115cfc3fb |  | note | Records Required: Test Report
label | d6829b8d-c448-5f80-80b4-8fd8f9fb9740 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Grading
label | 24348b10-a28d-5fda-a031-35ba86c8b985 |  | note | T
label | 5b4bbfbf-fbe5-5e4b-a51b-43b8d678742a |  | note | Reference or Specification: NZTA M/6 4.2.1
label | e7189720-f022-5f4e-8648-64929346c7fd |  | note | Method/Test required: See NZTA M/6 4.2.1
label | 81e48e2c-7154-57ab-a70d-b8276f385a10 |  | note | How Often? 1 Test
label | d1621ec8-6c97-559e-ae14-a008c221731f |  | note | Records Required: Test Report
label | 590f871c-2c58-58fe-9683-f86407494c71 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-group |  |  | section | 6.0 Chipseal Control
checkpoint-status |  |  | checkpoint | Confirm viscosity of bitumen
label | 47df2033-a360-5a15-a90b-14d0719ab875 |  | note | T
label | f72afa0a-fdcb-5617-b964-921d3842fc53 |  | note | Reference or Specification: NZTA M/1 Table 1
label | 229ad8c9-c54f-5dee-9404-94727f5f71a9 |  | note | Method/Test required: Viscosity PaS at 60°C
label | 7804ba2f-5859-5490-a11a-dcbb68482113 |  | note | How Often? 1 Test
label | 2f6b3c3f-44d2-54d3-a610-a5d50c4e96e7 |  | note | Records Required: Construction
label | 2a19f162-53e7-5b73-a29a-1b72d29ad08c |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Confirm penetration grade of bitumen
label | 071b38a2-a96e-58ad-a8e6-f6e92971601a |  | note | T
label | f4d2f8b2-c4d9-5c92-bd0a-eb15475b7d16 |  | note | Reference or Specification: NZTA M/1 Table 1
label | b681b191-804b-5c34-9439-7adc8f00ada6 |  | note | Method/Test required: Penetration at 25°C,100g, five seconds
label | db474ba6-fcfc-50fe-88ce-be548abd47fe |  | note | How Often? 1 Test
label | 7cd55794-3c2c-526f-9d40-1e32164b7dc8 |  | note | Records Required: Construction
label | fb0af783-dbf3-597f-b979-31de0f316905 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Spray bitumen, then place chip *and roll – refer design for chipseal Grade
label | 8c4a121a-20a4-57bd-a485-95f37755e8fe |  | note | I
label | 8ba0e5f0-dba0-51d2-8bfc-09adc8a251f6 |  | note | Reference or Specification: NZTA M/1 Table 1
label | 2b810410-e512-515b-bead-1f850ecaeeec |  | note | Method/Test required: Visual Check
label | 5992d0df-2b6f-5201-aa93-038ed961e812 |  | note | How Often? On-Site
label | 3cb908ce-2534-5dd5-af3b-57edc92c8eda |  | note | Records Required: Visual check
label | 850e82eb-f2a2-5b7a-a1ce-a26b1b031053 |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | Check for excessive "windows"
label | dfae82b9-d6b5-5cfc-8d7b-a6ed7d0fc1cf |  | note | I
label | ebd0d65d-26cf-5c58-8390-4576578d894d |  | note | Reference or Specification: NZTA M/1 Table 1
label | e677fc85-7f52-512b-9475-83554ab826a9 |  | note | Method/Test required: Visual Check
label | 72df6607-5ed0-51a8-809e-1c2c433a12b8 |  | note | How Often? On-Site
label | e163318d-22d2-5e3f-a9c5-77e7c63c5847 |  | note | Records Required: Visual check
label | 3f7f11b5-30a6-5156-9018-70d6b95450f2 |  | note | Responsibility: Supervisor
checkpoint-group |  |  | section | 7.0 Site Close-out
checkpoint-status |  |  | checkpoint | Field Quality Review
label | 718daf32-2204-52ff-8302-66bf1ad11cc2 |  | note | I
label | 412e1f62-b1e1-5145-bb6d-eb69b1fec135 |  | note | Reference or Specification: QMP
label | 3a9f264c-f827-5b2b-97d1-83fec248b45d |  | note | Method/Test required: Verification of Work Standards
label | 49bc71f8-dcbd-51ed-ab1d-3ae48473bf28 |  | note | How Often? 10% of sites
label | b1b63f13-93cc-5e55-8cf9-d4dc92daa9bc |  | note | Records Required: Record in Audit Field of RAMM Contractor
label | 6ac1a871-4cf8-5d76-b90d-47bae6768724 |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | Collect RAMM Data
label | 71452bf1-2a5c-5d04-b3a4-9d329f380161 |  | note | I
label | 224c0ca6-bd40-5ea2-9848-c353d53ff609 |  | note | Reference or Specification: SHDOM / Data Quality Plan
label | 9f4e3e89-8120-50b8-880e-654b5502ec5e |  | note | Method/Test required: L1 Accredited Personnel
label | 97cffd38-f35d-5ffe-b215-0924c10da84c |  | note | How Often? All Jobs
label | 04a70fab-66fc-5dfc-b73f-c911e03dfa4e |  | note | Records Required: SHDOM Specs
label | 348b77a1-a5cb-5456-9c96-078167acce17 |  | note | Responsibility: Foreman / Supervisor
checkpoint-status |  |  | checkpoint | Verify RAMM Data
label | f72b2ee7-0942-5733-bb74-840fc7cb6e65 |  | note | I
label | dc3d4038-ad5c-5c88-a782-ab15a86f58af |  | note | Reference or Specification: SHDOM / Data Quality Plan
label | bbde9e30-d538-5cd3-b512-25e45455734f |  | note | Method/Test required: Level 2 Accredited Personnel
label | bb35265a-c611-524f-8bca-f26db01bf8d8 |  | note | How Often? All Jobs
label | 97fcedb0-1431-578b-8457-4110ea6f8365 |  | note | Records Required: SHDOM Specs
label | 22783c80-eb3c-5bc7-a4ab-619bda58830f |  | note | Responsibility: Renewals Manager
checklist-flat |  |  | checklist | Production and Testing ITPs |  |  |  |  | Yes | Production and Testing ITPs | ed7e3a13-3294-4682-90ab-838745b0937f
checkpoint-status |  |  | checkpoint | Production and Testing ITPs
checklist-flat |  |  | checklist | Approved Design Report |  |  |  |  | Yes | Approved Design Report | f9b0314d-fdc5-41e5-b6b7-8d9a75197b47
checkpoint-status |  |  | checkpoint | Approved Design Report