## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - CS Resurfacing Physical Works | itp |  |  |  | Yes | ITP - CS Resurfacing Physical Works
section | 1.0 Pre-Works (Off Site)
checkpoint | Stakeholder Management Requirements met
label | H
label | Reference or Specification - CSCMP
label | Method/Test Required - Confirm requirements followed
label | How Often? Each site
label | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
label | Responsibility - Project Manager / Renewals Manager
checkpoint | Confirm if any environmental protection is required
label | I
label | Reference or Specification - ESMP
label | Method/Test Required - Record decision
label | How Often? Each site
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Project Manager
checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
label | H
label | Reference or Specification - QMP
label | Method/Test Required - QMP
label | How Often? Each site
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Project Manager
section | 2.0 Pre-Construction (On Site)
checkpoint | Job start, identify risks and controls, communicated to team
label | H
label | Reference or Specification - HSMP
label | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
label | How Often? Each site
label | Records Required - Hazard ID form
label | Responsibility - Site Foreperson
checkpoint | Establish traffic management to plan
label | H
label | Reference or Specification - TMP
label | Method/Test Required - Site audit post set up
label | How Often? Each site
label | Records Required - TTM Diary
label | Responsibility - STMS
checkpoint | Confirm site is on approved programme
label | H
label | Reference or Specification - Approved Programme
label | Method/Test Required - Record as-built site dimensions
label | How Often? Each Site
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Site Foreperson
checkpoint | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details
label | H
label | Reference or Specification - Approved Programme
label | Method/Test Required - Record as-built site dimensions
label | How Often? Each Site
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Site Foreperson / Site QA
checkpoint | Stockpiled sealing chip is clean and suitable for sealing
label | H
label | Reference or Specification - QMP
label | Method/Test Required - Acceptable/Unacceptable
label | How Often? Each Stockpile
label | Records Required - Pre-seal Inspection Form & Photograph
label | Responsibility - Site Foreperson / Site QA
checkpoint | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design
label | H
label | Reference or Specification - QMP
label | Method/Test Required - Acceptable/Unacceptable
label | How Often? Each Stockpile
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Site Foreperson / Site QA
checkpoint | Record & photograph environmental protection measures installed
label | I
label | Reference or Specification - ESMP
label | Method/Test Required - Record temporary measures
label | How Often? Each site
label | Records Required - Pre-seal Inspection Form & Photograph
label | Responsibility - Site Foreperson / Site QA
checkpoint | Binder application rate
label | T
label | Reference or Specification - Seal Design / Spraying Insructions
label | Method/Test Required - Confirm seal design requirements from programme
label | How Often? Per site
label | Records Required - Spray Sheet
label | Responsibility - Site Foreperson / Site QA
checkpoint | Pre-Sealing surface condition
label | I
label | Reference or Specification - QMP
label | Method/Test Required - Acceptable/Unacceptable
label | How Often? Per Site
label | Records Required - Pre-seal Inspection Form & Photograph
label | Responsibility - Site Foreperson / Site QA
section | 3.0 Construction
checkpoint | Start spraying Temp >10°C
label | T
label | Reference or Specification - NZTA P/17
label | Method/Test Required - Start >10°C
label | How Often? Per site
label | Records Required - Spray Sheet
label | Responsibility - Site Foreperson / Site QA
checkpoint | Binder application variation
label | T
label | Reference or Specification - NZTA P/17
label | Method/Test Required - +/- 4% (spray rate), +/- 50l (tank dip)
label | How Often? Per site
label | Records Required - Spray Sheet
label | Responsibility - Site Foreperson / Site QA
checkpoint | Sealing chip application
label | I
label | Reference or Specification - NZTA P/17
label | Method/Test Required - Full and even coverage of sprayed area
label | How Often? Per site
label | Records Required - Post-seal Inspection Form
label | Responsibility - Site Foreperson / Site QA
checkpoint | PTR Rolling pattern
label | I
label | Reference or Specification - NZTA P/17
label | Method/Test Required - Initial rolling completed along with traffic-rolling under controlled TTM
label | How Often? Per Site
label | Records Required - Post-seal Inspection Form
label | Responsibility - Site Foreperson
checkpoint | Trafficating
label | I
label | Reference or Specification - Chapter 11 - Chipsealing in NZ
label | Method/Test Required - Initial rolling completed along with traffic-rolling under controlled TTM
label | How Often? Per Site
label | Records Required - Post-seal Inspection Form
label | Responsibility - Site Foreperson / STMS
checkpoint | Tagging for line marking
label | I
label | Reference or Specification - Chapter 11 - Chipsealing in NZ
label | Method/Test Required - Pre-seal Visual check
label | How Often? Per site
label | Records Required - Post-seal Inspection Form
label | Responsibility - Site Foreperson
checkpoint | Post-Sealing Surfacing Condition
label | I
label | Reference or Specification - QMP
label | Method/Test Required - Visual check
label | How Often? Per site
label | Records Required - Post-seal Inspection Form & Photograph
label | Responsibility - Site Foreperson
section | 4.0 Post-Construction
checkpoint | Linemarking and RRPM Reinstated; Matches previous linemarking - within 48 hours of sealing
label | H
label | Reference or Specification - MOTSAM
label | Method/Test Required - Visual check
label | How Often? Per site
label | Records Required - Photograph
label | Responsibility - Project Manager
checkpoint | Spray Sheet/s Checked & Supplied for Claiming
label | H
label | Reference or Specification - QMP
label | Method/Test Required - Spray sheet data verified against design/programme
label | How Often? Per site
label | Records Required - Spray Sheet/s
label | Responsibility - Project Manager
checkpoint | Collect & Upload RAMM data
label | H
label | Reference or Specification - Comply with Waka Kotahi format
label | Method/Test Required - Correct data supplied
label | How Often? Per site
label | Records Required - Spary Sheet/s & Photographs
label | Responsibility - Renewals Manager
section | 5.0 Out Of Season Sealing
checkpoint | Out of Season Sealing
label | H
label | Reference or Specification - Winter Surfacing Site Note
label | Method/Test Required - Waka Kotahi Approval
label | How Often? Per Applicable Site
label | Records Required - Copy of Waka Kotahi Approval on-site
label | Responsibility - Project Manager / Renewals Manager