## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | d7e66ae7-4b16-4843-a9cf-9825acbf5eac |  | checklist | Ceilings |  |  |  |  | Yes | Ceiling Checklist | 28610923-45f1-46b1-8756-5bf1c47c3341
checkpoint-status | 8af7b1f6-964c-4f9e-b426-e60b11341169 |  | checkpoint | SAMPLES
label | f5f62851-571e-50d2-9ead-979edbb48ea7 |  | note | Submitted and approved via Multiplex sample register
checkpoint-status | 6f9a391e-30ff-4c0a-a35a-06d663032df2 |  | checkpoint | MATERIALS
label | 949de2f6-b053-571b-bffe-3f19ebe486e7 |  | note | Checked at delivery for compliance to internal material schedule
checkpoint-status | 926db591-2425-435b-850a-d5e7a9970c42 |  | checkpoint | SET OUT
label | 2e34ac74-d686-5480-bd89-acd00fe76d41 |  | note | As per RCP DRAWING series
checkpoint-status | 576cd7af-5fbe-45e2-b9d4-f76de997e278 |  | checkpoint | FRAMING
label | acd9a45f-219e-59a5-8ffd-b4de72a32fba |  | note | Rondo- concealed key lock system- Hanger grid max 1200 x 1200
label | d6b80999-7ca4-507f-89dd-f3fa5d65c258 |  | note | Rondo- exposed grid tile system-Hanger grid max 1200 x 1200
label | 534e10ec-fdcf-55ae-b5a0-849792aab7ab |  | note | Provision for -Access panel - Electrical - mechanical framed out
label | 54c12bed-66d7-59dc-8508-9e559f10a178 |  | note | Any noggin requirements
label | a6dba487-f084-5155-8550-8d50feecb6f8 |  | note | Seismic considerations
checkpoint-status | 686a0082-1b90-4ad3-b96b-6e200e004f7c |  | checkpoint | HOLDPOINT / INSPECTION
label | 4c8bf869-1cfe-5b32-b34d-13da647b1bc8 |  | note | Expoconti - Multiplex- Suppliers inspection of works
label | a276e854-73e5-5a9a-ba3f-c4678ab5a97b |  | note | Reworks noted and actioned prior to pre sheet sign off
holdpoint | 081c4617-1d62-4205-a350-fd493770b283 |  | signoff | Request Sign Off
checkpoint-status | e637ec09-ec1f-468b-97ba-6f086428f6af |  | checkpoint | PRE SHEET SIGN OFF
label | 09ff4dca-bc93-56a7-ad84-d596c25c3f03 |  | note | Multiplex sign off system completed and instruction to proceed granted
checkpoint-status | caec5d31-fb7b-44e1-9f6f-1d818cfea532 |  | checkpoint | INSULATION
label | ded25b49-d03b-5057-94f4-ae23d89442f1 |  | note | Glasswool insulation -Type, "R" value and location as per RCP series
label | 4a91cdfb-2159-5d83-a533-98df870ae2ce |  | note | no gaps, all ceiling area covered with insulation
checkpoint-status | 6fc97e9f-7b8c-4afe-b9e9-c044373ba848 |  | checkpoint | LININGS
label | feeff56d-56c3-5d47-b7b2-f29a6d5aafd8 |  | note | Fire rated board- standard- wet areas- acoustic- impact CSR Red Book
label | a006f19a-9b30-562c-bc99-d45961bf1b7f |  | note | Nominated linings -RCP revisions
label | c31411aa-0f31-5d8a-a6b7-9b68eba2cbc9 |  | note | Fixings -spacings and staggered joins
label | 6c35370d-f3fb-5197-ab93-22b17b71d16f |  | note | Penetrations / lights cut outs
label | 3a57fb1f-aa21-50ee-b8a7-6d403ec41780 |  | note | Specialised linings
checkpoint-status | 57a0f4b8-c53c-4661-8891-99fc56fc16de |  | checkpoint | ACCESS PANELS
label | 3f90932e-3d19-5c36-9fd9-ea91f296687f |  | note | Panel type and size nominated drawings (RCP) revisions (Checkpoint: attach photo)
label | 328e255b-3591-597f-bf8e-e037b10062be |  | note | Installed to manufacturers recommendations
label | f27e2632-dae5-527f-b1c8-e226e8337dc0 |  | note | Positioning -As marked by service trades requirements - RCP
checkpoint-status | c3223101-364d-420e-8b5a-77bd8476efc7 |  | checkpoint | STOPPING / SANDING
label | 9c9b73f3-59de-5887-aefd-ff3fea5b238a |  | note | Class 4 finish
checkpoint-status | d2816f71-0a36-42ea-a632-cadaab748c20 |  | checkpoint | CAULKING /PENETRATIONS
label | 2350c9b3-fc01-55e0-8705-7ccbb7cb7170 |  | note | Gap between plaster & substrate 15mm max
label | 0d9823cb-16d0-5b6f-a14b-d561036870ba |  | note | All penetrations sealed and caulked
label | aa1e5a0d-88f1-568f-9a13-5911d8ac87d4 |  | note | All gaps sealed in presurised rooms-perimmitter, pressure boxes
checkpoint-status | 89cb5ea6-684b-4af3-84b5-34385d3a7c72 |  | checkpoint | HOLD POINT / INSPECTION
label | df9a439f-c2ce-5223-b2d1-91b186dc4fce |  | note | Expoconti - Multiplex- Suppliers inspection of works
label | 4b6a3c6d-0c5b-5fee-a400-b10baaca2ac8 |  | note | Reworks noted and actioned prior to final finish paint coat
holdpoint | 62bac1bb-923b-4282-ac7a-e3f969f49861 |  | signoff | Request Sign Off
checkpoint-status | f93eda95-906a-46bf-91da-696de4dfad4a |  | checkpoint | DEFECTS
label | 378d7d26-0f1e-518c-97b0-b851d31ba499 |  | note | Multiplex/Client defects closed out via Aconex field
checkpoint-status | 90305f3b-6e3b-419c-a3e0-c9c64b3d4964 |  | checkpoint | FINAL INSPECTION/ SIGNOFF
label | 6c963cff-6971-5043-a1c3-acfb82a2e7de |  | note | Conformation that Expoconti representative has reviewed and verifies that all works have been completed and conforms to contract specifications
checklist-flat | cc69e9b5-b3ea-4631-a522-b46cfabfd020 |  | checklist | Manufacturer's Inspection Report |  |  |  |  | Yes | Manufacturer's Inspection Report | 2888fa40-3b1e-471c-abb8-caa3871f662e
checkpoint-status | 9baf40ee-b917-4c67-95c3-a73d8cdc6d12 |  | checkpoint | Issued Report & Action
checklist-flat | ae85171a-f6c7-419c-951e-c32e034ba95a |  | checklist | Speedpanel |  |  |  |  | Yes | Speedpanel Checklist | 4b372cde-32c1-4075-96fc-bfc653dd9cae
checkpoint-status | cc9da118-664a-46e0-ab2a-57d68329a30b |  | checkpoint | Drawing Reference - Latest IFC drawing referenced
checkpoint-status | 2ac8d6ec-a2e1-4ec9-9998-94283c9cf76a |  | checkpoint | Current revision (Photo of title block with drawing No. and revision)
checkpoint-status | 50ebd676-8df4-4bfe-a324-7f6a8e7627a2 |  | checkpoint | Area clean and accessible to start work
checkpoint-status | aff56729-a3e4-47c3-b828-5385fa1b6ae0 |  | checkpoint | Confirm panel thickness used - 78mm
checkpoint-status | a967156e-054e-446a-b1ba-64d735bdc3dc |  | checkpoint | Setout of wall location verified
checkpoint-status | 113ee85d-e636-459e-8da9-d827389ba607 |  | checkpoint | Apply approved fire rated sealant (Hilti 606) between c-track and structure to entire perimeter (Photo)
checkpoint-status | b6607ba5-99f9-4a80-a8e3-48cfb5dc6cd2 |  | checkpoint | Fix c-track to structure using Hiliti Huss anchors at 500mm centres (Photo)
checkpoint-status | a14ef264-98fc-4c57-a596-66baaa348ead |  | checkpoint | Apply approved fire rated sealant (Hilti 606) to internal corner ot the c-track (one side) to entire perimeter (Photo)
checkpoint-status | b37855e2-bf54-4b23-a77c-575bea4ff981 |  | checkpoint | Verify maximum 20mm gap between speedpanel and top c-track (Photo)
checkpoint-status | 834a6dd5-9f41-416c-a43a-b8f0ef17ad78 |  | checkpoint | Panel fixing - Perimeter 500mm centres / Horizontal 250mm centres / Vertical 1000mm centres
checkpoint-status | 5180e09e-8630-49a6-b18a-dceffd4bf3e4 |  | checkpoint | If pressurised riser, all joins have been sealed - panel end & perimeter
checkpoint-status | 81fd2e9c-4752-478b-b447-c2595cc17639 |  | checkpoint | Install head track protection fixed with 30mm screws at 125mm centres (Photo of completed wall)
checklist-flat | ee8339c3-3d34-49aa-9870-12bb6676c3d9 |  | checklist | Walls |  |  |  |  | Yes | zSYS - Wall Checklist (old version) | 63589c10-2e82-4bf7-9d0c-051fc4b57c5c
checkpoint-status | 5ab20835-4388-47d8-a239-9f2fab6d0298 |  | checkpoint | SAMPLES
label | 6e731246-bf9d-57a3-bc96-220c7a558123 |  | note | Submitted and approved via Multiplex sample register
checkpoint-status | 381c3355-410b-4216-abf7-e6b0d253674f |  | checkpoint | MATERIALS
label | 68a66919-db0d-55f7-9237-4dd0694c7355 |  | note | Checked at delivery for compliance to internal material schedule
checkpoint-status | fec651e3-114f-4c3a-a39c-77a69b3186db |  | checkpoint | SET OUT
label | f839f39a-e29e-5629-86aa-7996f8c704e4 |  | note | As per WALL TYPE & INSULATION plans AR-0-140 series
checkpoint-status | 6b3c2c79-7484-4836-a210-79fc6449caef |  | checkpoint | WALL FRAMING
label | cbba3be1-4408-5932-9b9b-38aebe53b364 |  | note | Stud configeration conforms to Wall Types AR-0-230 series
label | 47ff25d0-f4c3-5e75-bbf7-c612bcbf766b |  | note | Conforms to Rondo (building B) / Studco (buildings D/E) seismic designs (Checkpoint - either studco/rondo)
label | 61de5463-195c-58fb-89bf-49f3f8640b9e |  | note | Fixings max 600 centres
label | 116d68c7-024b-5602-b64e-83a92d992047 |  | note | Stud spacings max 600 centres- Noggin track to suit
label | 1b83036d-2ad6-5180-8164-033ecee17881 |  | note | Framing to accommodate for penetrations
checkpoint-status | 70a8baba-d26c-48a2-ac42-f5f0a740493d |  | checkpoint | PENETRATIONS THROUGH SMOKE SEAL
label | 3ab89110-345b-5555-be88-12a5d264a4c4 |  | note | Drilled through smoke seal
label | 68f5375b-e470-59d6-b31c-a5c1ebb98187 |  | note | Vacuum clean
label | 7fa086c2-37a7-5e31-bf92-e593013acc77 |  | note | Pre-filled hole with hilti cp606
label | 8dd37b69-88f5-5121-8473-a47152491cf8 |  | note | Caulking bead full length of bottom track
label | c3fbec38-da17-5902-b004-f1d819b53c09 |  | note | Fixed bottom track with HUSSBOLT 6mm
label | 217cc37d-032c-5a91-9b03-f5e7f81fa77d |  | note | Caulk exposed fixing head with cp606
checkpoint-status | 26cfa900-112a-4d3a-8662-11466817758d |  | checkpoint | DOOR FRAMES
label | 5a0ca6be-6263-5bca-8107-4c3b0e92b21b |  | note | Installed in conjunction with Door Function Schedule AR-0-280 series
label | 90564238-8867-5f65-a27e-ba6799e2a047 |  | note | Installed plumb and square
label | 392dadee-269a-520f-8a06-8974a301330a |  | note | Fire rated frames backfilled and caulked
label | 97be9f87-452d-53d1-89da-29b8fcccad1a |  | note | Lead rated frames delivered lined
label | 7aaba241-6465-5ca5-bc33-e2ef8ad22538 |  | note | Spreader bars removed
checkpoint-status | aaa3e459-9724-4986-80de-342564dcc9d9 |  | checkpoint | NOGGINS PRESSURE BOXES
label | 0df09a9c-d597-5acb-bb5b-8e80f88b7b1f |  | note | Installed as set out and required by service trades
checkpoint-status | 38abf8fa-caee-4fc9-b183-fc59ae152cc9 |  | checkpoint | HOLDPOINT / INSPECTION
label | 49fae463-364b-58b5-a48a-229dcbf69aef |  | note | Expoconti - Multiplex- Suppliers inspection of works
label | cf1f7933-51ce-50e8-851d-fbb67de2655c |  | note | Reworks noted and actioned prior to pre sheet sign off
holdpoint | 6c93d7ba-0d2a-4b1c-93a9-3b9da2b08363 |  | signoff | Request Sign Off
checkpoint-status | 4d31a4ae-9753-4f0e-b741-4dd7b04998f2 |  | checkpoint | PRE SHEET SIGN OFF
label | 76318eef-d2b6-50c7-8b99-b5c23fbb3c03 |  | note | Multiplex sign off system completed and instruction to proceed granted
checkpoint-status | 729c357c-9a6e-4f9c-8104-8aee1da02a6e |  | checkpoint | INSULATION
label | 3a2bf32c-b9f6-5b05-a261-41fd75f74593 |  | note | Type and location as per Wall Type & Insulation plans AR-0- 230 series (Checkpoint: input insulation type)
label | 5cf4e594-01bf-5db7-870f-7a2de61deb11 |  | note | Installed tight between studs - no gaps
checkpoint-status | 12030a77-e5ed-4000-a434-d3ffe3472346 |  | checkpoint | LININGS
label | 134f024b-92f0-59ab-8114-1f548accbb16 |  | note | Conformation type & location AR-0-230 series (Checkpoint: standard / bathroom / Fire)
label | 3c64c2f0-5b95-5437-81de-eb1e370d3098 |  | note | Fire rated board- standard- wet areas- acoustic- impact CSR Red Book
label | 82f128a7-91c0-5494-8958-1241ddf5c3f5 |  | note | Staggered joins- Screw spacings to Edge (200mm max) field (300mm max)
label | 2f7d347a-4561-5741-8671-2afda2dec79d |  | note | No gaps - square and plumb
label | 3faf4b86-86d5-5669-bf23-6827e37d3ecd |  | note | Overlap at corner junctions
label | 61572ff6-e6bb-5ebf-b317-3508e8dcfb82 |  | note | Penetrations stopped/ caulked
checkpoint-status | a7f8c0b1-c2a0-4004-9213-e6fa85e09696 |  | checkpoint | STOPPING / SANDING
label | 68deef0e-5b41-5cd2-b008-9805d79474f1 |  | note | Class 4 finish
checkpoint-status | b543cc54-5878-48b7-8967-d36635d479ce |  | checkpoint | CAULKING /PENETRATIONS
label | f3c7bd2f-bf97-502e-9c05-f446fe525671 |  | note | Acoustic and Fire rated caulk- Hilti 606
label | bb44b611-fbe9-572c-88ae-a120d1a5a4cc |  | note | Ensure all Fire rated walls fully caulked
label | 9449556d-f880-56d8-9f6b-f003a72377c8 |  | note | Gap between plaster & substrate 15mm max
label | 8499bf14-7cb9-5b33-a12f-51e4c2d831d3 |  | note | All penetrations sealed and caulked
label | 1e169c46-f903-5b59-b03c-ee4045b378c2 |  | note | All gaps sealed in presurised rooms-perimmitter, pressure boxes
checkpoint-status | 36fa9195-ae67-46bf-9bd8-774c3e872abd |  | checkpoint | HOLD POINT / INSPECTION
label | 8affe789-e978-51a0-bd77-0e724566842a |  | note | Expoconti - Multiplex- Suppliers inspection of works
label | b37e633e-deea-50c1-865e-cdaee7648a0c |  | note | Reworks noted and actioned prior to final finish paint coat
holdpoint | 08d1200e-d02f-4cdf-a3a9-74afcb50e334 |  | signoff | Request Sign Off
checkpoint-status | b53edc63-2dbd-4726-82fe-07ba6f952477 |  | checkpoint | DEFECTS
label | 227d6390-eb5b-566e-ae59-845bc86a0ddb |  | note | Multiplex/Client defects closed out via Aconex field
checkpoint-status | e929ca8e-9c3b-4511-9121-74eda557c530 |  | checkpoint | FINAL INSPECTION/ SIGNOFF
label | 4a2e3db7-3e26-5658-afa2-2dac69735224 |  | note | Conformation that Expoconti representative has reviewed and verifies that all works have been completed and conforms to contract specifications
checklist-flat | 06c268a6-1455-409e-8163-0f3c222b410b |  | checklist | Flat Slab Placement |  |  |  |  | Yes | Flat Slab Placement | 87a39b4d-f2fc-4b18-b6be-907793bbaa8b
checkpoint-status | 9a54d56a-bfbe-4c38-8516-922fec949cbd |  | checkpoint | Check RL of landing place
checkpoint-status | 0c54a925-bb71-40c9-94b2-30105896d07d |  | checkpoint | Mark out flat slab layout on site
checkpoint-status | 68c63239-c219-47b9-8bd2-4c02e1b75332 |  | checkpoint | Install bearing strip
checkpoint-status | 5e125243-e121-4ecb-b12c-f3cbd8b52f64 |  | checkpoint | Set heights for midspan
checkpoint-status | dce0645d-a4e8-4359-ac83-299e2027eb41 |  | checkpoint | Check dimensions of the panel - on delivery
button | 2e3c7dcc-82ed-57da-b46c-c4a0ad152a15 |  | button | If applicable cut flat slab | Yes,No
checkpoint-status | d8f5135d-9624-4ca8-983b-6495e6defe2d |  | checkpoint | Place flat slab
checkpoint-status | 2935ec96-0a44-447c-b0c5-222b2330b350 |  | checkpoint | Photos and observations
holdpoint | ce848dcb-068f-4928-bc98-fdd4dd23f42e |  | signoff | Request Review
checklist-flat | 00414ce7-286d-490a-9bad-5428c8d3c98b |  | checklist | Delivery Checklist |  |  |  |  | Yes | Delivery Checklist | 9ac09f09-f935-453d-a90b-b2d00f9263e2
checkpoint-status | 9bb5ef2f-d302-4935-8230-4ad291355357 |  | checkpoint | Delivery details and docket uploaded below
checklist-flat | 8195a32f-e55c-4ce9-8e35-b7c17e1a82b5 |  | checklist | Speedpanel |  |  |  |  | Yes | Speedpanel Checklist (+Door Frames) | bcbcea95-f74a-41a8-a3c6-e4c487353982
checkpoint-status | cf594091-3c59-48bf-82a5-afc4d974296e |  | checkpoint | Drawing Reference - Latest IFC drawing referenced
checkpoint-status | a1d8f159-5c65-41dc-ade2-557dec7b52e7 |  | checkpoint | Current revision (Photo of title block with drawing No. and revision)
checkpoint-status | 1a2f992f-d182-4f01-a78f-3697abe388d6 |  | checkpoint | Area clean and accessible to start work
checkpoint-status | ec40071b-6e5f-460c-80d4-c0f8b2c61a06 |  | checkpoint | Confirm panel thickness used - 78mm
checkpoint-status | 30ed978e-d74c-481e-ba55-d6d00e50baab |  | checkpoint | Setout of wall location verified
checkpoint-status | c8b13d88-ba8f-4b9b-a377-cf95315632ca |  | checkpoint | Apply approved fire rated sealant (Hilti 606) between c-track and structure to entire perimeter (Photo)
checkpoint-status | d956039c-508c-494e-8052-8b7db827cc48 |  | checkpoint | Fix c-track to structure using Hiliti Huss anchors at 500mm centres (Photo)
checkpoint-status | 58a7cef4-d28e-4f5e-8884-bbc319d70812 |  | checkpoint | Apply approved fire rated sealant (Hilti 606) to internal corner ot the c-track (one side) to entire perimeter (Photo)
checkpoint-status | 42ef662f-5422-4e26-ac14-c1cd436a90cd |  | checkpoint | Verify maximum 20mm gap between speedpanel and top c-track (Photo)
checkpoint-status | 8863efa9-34a0-428a-9e5a-1964582634bf |  | checkpoint | Panel fixing - Perimeter 500mm centres / Horizontal 250mm centres / Vertical 1000mm centres
checkpoint-status | 6fa8d0a3-004a-488d-829b-f81743916951 |  | checkpoint | If pressurised riser, all joins have been sealed - panel end & perimeter
checkpoint-status | f02c7db3-2945-460a-aa01-e460b939a853 |  | checkpoint | Install head track protection fixed with 30mm screws at 125mm centres (Photo of completed wall)
checkpoint-status | e05f9dc0-d6e0-4f08-a763-49b34df753ef |  | checkpoint | DOOR FRAMES
label | 0046df1e-7c23-5716-b04c-e034ef96a5a2 |  | note | Installed in conjunction with Door Function Schedule AR-0-280 series
label | 42e9d95a-17e7-5e2b-9bdb-542d6919810b |  | note | Installed plumb and square
label | 2f012a51-3820-583c-8f5d-345c57d2a9f4 |  | note | Fire rated frames backfilled and caulked
label | 25482b9a-ceac-5512-866b-ecc0f0495918 |  | note | Lead rated frames delivered lined
label | 96db60d2-07e6-5187-9104-ee014b60ad60 |  | note | Spreader bars removed