## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Manufacturing QA - Noise Wall Panels
| Scope |  |  | Manufacturing QA | Noise Wall Panels
Rows
|  | Manufacturing QA - Noise Wall Panels | dynamic | Manufacturing QA | Noise Wall Panels
Columns
|  | Current, approved & attached |  | current, approved & attached | pre-pour
|  | Production Actual Date | Production Actual Date | current, approved & attached | pre-pour
|  | Delivery Date | Delivery Date | current, approved & attached | pre-pour
|  | Forms clean & release agent/oil applied |  | pre-pour | forms clean & release agent/oil applied
|  | Chamfers installed as per drawings |  | pre-pour | chamfers installed as per the drawings
|  | Drawing Dimensions within Tolerances |  | pre-pour | drawing dimensions within tolerances
|  | Order Number recorded on manufacture drg. |  | pre-pour | order number recorded on manufacture drg.
|  | Reo in accordance with drawings/within tolerance/marked on drawing |  | pre-pour | reo in accordance with drawings, within tolerance and marked on drawing
|  | Block outs/Drains/Bolts/Ferrules/Debonding/couplers Correct type, located, secure & marked on drawing |  | pre-pour | e.g. block outs, drains, bolts, ferrules, debonding, couplers, etc. correct type, correctly located, secure and marked on drawing.
|  | Correct rating/length/location |  | pre-pour | correct rating, length, location
|  | Void Formers, Location & correct installation |  | pre-pour | void formers, location & correct installation
|  | Pour arrangements agreed & equipment adequate |  | pour arrangements agreed & equipment adequate. | pre-pour
|  | Concrete mix selected as per approved mix design |  | concrete mix selected as per approved mix design | pre-pour
|  | Unit ID placed on reo/lifter or embedded in concrete face/edge |  | pre-pour | unit id has been placed on reo/lifter or embedded in concrete face/ edge.
|  | All checks/holdpoints signed before concrete placed |  | pre-pour | all checks and hold points signed before concrete may be placed.
|  | Strength achieved - Lifting strength at least 15 Mpa |  | post pour | strength achieved - lifting strength at least 15 mpa
|  | Membrane curing - coating as per spec CONCURE 99A REMOVAL BY OTHERS |  | membrane curing - if required, coating as per specification concure 99a removal by others | post pour
|  | Embedded items alignment & position correct/marked on drawing |  | embedded items alignment and position correct and marked on drawing | post pour
|  | NCR raised & closed as required. All repairs completed |  | post pour | ncr raised and closed as required. all repairs completed
|  | Survey complete & dimensions marked up on shop drawing issued for construction |  | post pour | survey complete and dimensions marked up on shop drawing issued for construction.
Manufacturing QA - Facia Panels
| Scope |  |  | Manufacturing QA | Facia Panels
Rows
|  | Manufacturing QA - Facia Panels | dynamic | Manufacturing QA | Facia Panels
Columns
|  | Current, approved & attached |  | current, approved & attached | pre-pour
|  | Production Actual Date | Production Actual Date | current, approved & attached | pre-pour
|  | Delivery Date | Delivery Date | current, approved & attached | pre-pour
|  | Forms clean & release agent/oil applied |  | pre-pour | forms clean & release agent/oil applied
|  | Chamfers installed as per drawings |  | pre-pour | chamfers installed as per the drawings
|  | Drawing Dimensions within Tolerances |  | pre-pour | drawing dimensions within tolerances
|  | Order Number recorded on manufacture drg. |  | pre-pour | order number recorded on manufacture drg.
|  | Reo in accordance with drawings/within tolerance/marked on drawing |  | pre-pour | reo in accordance with drawings, within tolerance and marked on drawing
|  | Block outs/Drains/Bolts/Ferrules/Debonding/couplers Correct type, located, secure & marked on drawing |  | pre-pour | e.g. block outs, drains, bolts, ferrules, debonding, couplers, etc. correct type, correctly located, secure and marked on drawing.
|  | Correct rating/length/location |  | pre-pour | correct rating, length, location
|  | Void Formers, Location & correct installation |  | pre-pour | void formers, location & correct installation
|  | Pour arrangements agreed & equipment adequate |  | pour arrangements agreed & equipment adequate. | pre-pour
|  | Concrete mix selected as per approved mix design |  | concrete mix selected as per approved mix design | pre-pour
|  | Unit ID placed on reo/lifter or embedded in concrete face/edge |  | pre-pour | unit id has been placed on reo/lifter or embedded in concrete face/ edge.
|  | All checks/holdpoints signed before concrete placed |  | pre-pour | all checks and hold points signed before concrete may be placed.
|  | Strength achieved - Lifting strength at least 15 Mpa |  | post pour | strength achieved - lifting strength at least 15 mpa
|  | Membrane curing - coating as per spec CONCURE 99A REMOVAL BY OTHERS |  | membrane curing - if required, coating as per specification concure 99a removal by others | post pour
|  | Embedded items alignment & position correct/marked on drawing |  | embedded items alignment and position correct and marked on drawing | post pour
|  | NCR raised & closed as required. All repairs completed |  | post pour | ncr raised and closed as required. all repairs completed
|  | Survey complete & dimensions marked up on shop drawing issued for construction |  | post pour | survey complete and dimensions marked up on shop drawing issued for construction.
Site QA - Noise Wall Panels
| Scope |  |  | Site QA | Noise Wall Panels
Rows
|  | Site QA - Noise Wall Panels | dynamic | Site QA | Noise Wall Panels
Columns
|  | Relevant QA photos/documents |  | attach any relevant qa photos or documents
Site QA - Facia Panels
| Scope |  |  | Site QA | Facia Panels
Rows
|  | Site QA - Facia Panels | dynamic | Site QA | Facia Panels
Columns
|  | Relevant QA photos/documents |  | attach any relevant qa photos or documents