## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-041 ITP Underpass Stage 2 | itp |  |  |  |  | DN1210-041 ITP Underpass Stage 2 Rev 2
section | SECTION 3 – EARTHWORKS SUBGRADE
checkpoint | 3.1.1 - Cut Subgrade Inspection
label | Detail - Engineer to inspect all foundation surface inspections
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.1 - Cut Subgrade Testing - Cohesive Soil - Shear Vane
label | Detail - This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ Single Test Min SU: >50kPa
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.3.1 - Cut Subgrade Testing - Granular Soil - Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.4.1 - Undercut Surface Inspection
label | Detail - Engineer to inspect undercut surface and determine undercut requirements.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Across undercut area
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 3.4.2 - Placement of Geotextile on Undercut
label | Detail - Geotextile to be placed across the undercut base and up the sides, with joints overlapped by 500mm minimum
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4 TNZ F/7: 2003 8.3
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Across undercut area
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 3.4.3 - Backfill undercut
label | Detail - Backfill undercut with AP100 and lightly compact.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - In Eight ref: DN1210-WSP-NTC-0207
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Across undercut area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.5.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Shear vane Strength 70kPa
label | Standard / Specification - PS- 21.7.2 Appendix V
label | Verifying Document - Scala test result or Shear vane result
label | Testing Quantity Required (based from schedule qtys) - One test per 20m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 1 Tests
label | ○ 0m-20m: 2 Tests
label | ○ 0m-50m: 4 Tests
label | ○ 0m-100m: 6 Test
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.5.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 1 Sheet STW 0405. PS- 21.6.11 AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.5.3 - Undercut Backfill Compliance (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 20m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 1 Tests
label | ○ 0m-20m: 2 Tests
label | ○ 0m-50m: 4 Tests
label | ○ 0m-100m: 6 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.5.4 - Bedding and Embedment Zone Compaction Testing (Polypropylene(civil boss)/Polyethylene Pipe).
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Bedding Zone:
label | — 100mm(for DN300 & DN375)
label | — 150mm (for pipes greater than DN375)
label | ○ Embedment Zone:
label | — Pipe Dia ≤450 - 150mm GAP20/AP20 - Overlay
label | — Pipe Dia 450< D ≤900 - 150mm GAP20/AP20 - Overlay
label | — Pipe Dia 900< D ≤4000 - 150mm GAP20/AP20 - Overlay
label | ○ Minimum Compaction - Trafficable and Non-Trafficable 95% MDD on metal.
label | Standard / Specification - PS- Table 21.7, PS- Table 21.12 AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 20m evenly spaced intervals along pipeline with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 1 Tests
label | ○ 0m-20m: 2 Tests
label | ○ 0m-50m: 4 Tests
label | ○ 0m-100m: 6 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.5.5 - Survey
label | Detail - Surveyor to Setout
label | Acceptance / Conformance Criteria - Vertical design Setout:
label | ○ Pipes ≤ 1% grade: +/- 10mm variance
label | ○ Pipes > 1% grade: +/- 20mm variance
label | ○ Horizontal design Setout: +/-30mm variance
label | Standard / Specification - PS- 21.7.6 Table 21.15
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Every 100m or at Chambers (whichever distance is the lesser)
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.5.6 - Backfill Compaction Testing
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - GAP65/AP65/LRAP65
label | ○ Backfill Compacted in 200mm layers.
label | ○ Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal.
label | Standard / Specification - PS- 21.6.12 Appendix V
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 20m evenly spaced intervals along pipeline with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 1 Tests
label | ○ 0m-20m: 2 Tests
label | ○ 0m-50m: 4 Tests
label | ○ 0m-100m: 6 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.5.7 - Pipe Inspection
label | Detail - Inspection of Drainage line
label | Acceptance / Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place.
label | ○ Check for gaps and/or defects and check pipe alignment for straightness
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Drainage line record
label | Testing Quantity Required (based from schedule qtys) - Continuous 1 per Line
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.6.1 - Settlement Monitoring
label | Detail - Settlement monitoring with installing the settlement plate at underpass foundation level and as described in PS 18.5.4 during the construction at various levels.
label | Acceptance / Conformance Criteria - Settlement monitoring done regularly after completion of foundation, on completion of precast installation, on completion of cover fill, on completion of finish structure.
label | Standard / Specification - PS 18.5.4
label | Verifying Document - Installation of Settlement plates/Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - as per construction sequence per PS 18.5.4
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.6.2 - Placement of Geotextile
label | Detail - A layer of Class C Geotextile Fabric to be placed between cut surface and imported A1 Structural Fill with 500mm overlaps
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - NTC084
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - As Required
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.6.3 - Compaction - Clegg Hammer for GAP65 & AP40
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Structural Fill
label | ○ Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.6.4 - Placement of Geogrid
label | Detail - The Durargid X 40/40 Geogrid shall be placed on top of the GAP65 layer and the first AP40 layer.
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - STR Drawings Sheet 203
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Across gravel raft
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 3.6.5 - Compaction - NDM on top AP40 layer
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | ○ Non Granular Material
label | ○ Max Air Voids 8%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) on last lift of AP40
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 4 – PRE-CONSTRUCTION - MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.1.1 - Reinforcing steel and Strands
label | Detail - All Reinforcement bars and strands used in structural concrete to be approved by the engineer prior to construction.
label | ○ Post tensioning strand to be high tension ASTM galvanized and complying with AS/NZ standard
label | Acceptance / Conformance Criteria - Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of any work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work.
label | ○ High yield steel, Grade 500E, Seismic MA.
label | ○ Post tensioning strand to be high tension ASTM galvanized and complying with AS/NZ standard
label | Standard / Specification - PS 18.3.3, 18.5.7 and 19.13.1
label | Verifying Document - Supplier data sheet/ Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - Concrete Spacer Blocks
label | Detail - Reinforcement cover spacer blocks shall be either made from concrete with a specified strength at least 10mPa stronger than the surrounding concrete; or Plastic spacer blocks.
label | Acceptance / Conformance Criteria - Concrete cover spacing blocks = at least 10mPa stronger than surrounding concrete.
label | Standard / Specification - PS 19.3.2
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Concrete mix design
label | Detail - Approved mix design - Concrete shall be of the class as defined by NZS 3104 have a minimum 28 days compression strength as specified for various members: for underpass apron pour: 40mpa
label | Acceptance / Conformance Criteria - 28 Day concrete requirements: UNDERPASS APRON POUR: 40MPA
label | Standard / Specification - PS 19.3.3
label | Verifying Document - Approved Mix design
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Shop Drawing Approval
label | Detail - Shop drawing review and approval from Engineer and Production QA Records to be submitted
label | Acceptance / Conformance Criteria - Send shop drawings to the Engineer for review, at least 14 days prior to manufacture. Any variations between the Drawings and shop drawings shall be clearly identified and brought to the attention of the Engineer.
label | Standard / Specification - PS 19.12.6
label | Verifying Document - Shop Drawing Approval, QA records
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.5 - Anti-graffiti products
label | Detail - Permanent (not sacrificial) anti-graffiti coatings shall be applied to the exposed faces of all concrete surfaces including wingwalls. The coatings shall have a design life of not less than 10 years. The Contractor shall submit the proposed extent of application for authorisation by the Engineer.
label | Acceptance / Conformance Criteria - Permanent (not sacrificial) anti-graffiti coatings shall be applied to the exposed faces of all concrete surfaces including wingwalls. The coatings shall have a design life of not less than 10 years. The Contractor shall submit the proposed extent of application for authorisation by the Engineer.
label | Standard / Specification - PS 14.7.1
label | Verifying Document - Details of pre qualified product
label | Testing Quantity Required (based from schedule qtys) - Prior to Application - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.6 - Joint Sealing and Waterproofing Sealant
label | Detail - Pre approved joint sealant meeting the specification requirements
label | Acceptance / Conformance Criteria - Joints are to be sealed using a fuel resistant, multi-component polysulphide sealant designed for horizontal and vertical joints in concrete and is joint sealant pourable or gunning grade as appropriate.
label | Standard / Specification - PS 19.12.6
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - Engineers approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.7 - Compressible filler board
label | Detail - Compressible filler board specification to meet the project requirements.
label | Acceptance / Conformance Criteria - Details of the compressible filler board proposed to be used as a construction joint shall meet specification requirements.
label | Standard / Specification - PS 19.12.6
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.8 - Application of Non-Slip Coating - Sikafloor 91 or Sikafloor150
label | Detail - Proposed product to be approved by Engineer
label | Acceptance / Conformance Criteria - The top of the underpass floor slab and bottom chamfers will have Sikafloor 91 or Sikafloor 150 applied after the installation of the box culvert segments. The thickness of this is to be between 3 and 5mm. The application of the product must be done in accordance with the manufacturer’s specifications.
label | Standard / Specification - PS 19.2.4
label | Verifying Document - Product data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – CONSTRUCTION ACTIVITIES - BLINDING AND PRE-CAST POUR
checkpoint | 5.1.1 - Setting out of Underpass Blinding level with 1% fall towards Northern end
label | Detail - Setting out boxing and complete site checks as concrete is poured to ensure flat surface for placing precast units
label | Acceptance / Conformance Criteria - Site supervisor verification
label | Standard / Specification - PS 18.5.3
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
checkpoint | 5.1.2 - Blinding Concrete
label | Detail - Concrete Compressive Strength on 28 days to gain min of 10MPa
label | Acceptance / Conformance Criteria - Blinding concrete shall have a minimum 28 days compressive strength of 10 Mpa and comply with the requirements for prescribed mix concrete specified by NZS 3104
label | Standard / Specification - PS 19.3.3
label | Verifying Document - Concrete Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.3 - Setting out of positions of the Underpass units
label | Detail - Setting out to follow design coordinates and levels within tolerance as specified in PS 18.5.3 by approved licensed surveyor to certify the Set-Out positions.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 18.5.3
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
checkpoint | 3.2.1 - Forms and Moulds
label | Detail - Tolerance on the placement of internal forms and moulds shall be +-5mm
label | Acceptance / Conformance Criteria - Moulds shall be rigid accurately formed and of sufficient strength and stiffness to prevent distortion under vibration.
label | Standard / Specification - PS 19.12.5
label | Verifying Document - Manufacturer QA records
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.1 - Pre Pour Inspection
label | Detail - Pre Pour inspection to check:
label | — Reinforcing
label | — Moulds
label | — Cover Spacer Blocks
label | Acceptance / Conformance Criteria - The Engineer shall be informed 8 hours prior to the casting of any unit, to allow the Engineer to attend the pre-casting plant to inspect before and during production of the units.
label | ○ Reinforcing shall be pre assembled wherever possible into rigid cages using a template or jig. Reinforcing shall be tied together with wire unless otherwise accepted by the Engineer
label | ○ Confirm correct type and location of cover block is used.
label | Standard / Specification - PS 19.3.2, 19.4.3 & 19.12.3
label | Verifying Document - Pre pour inspection checklist, Manufacturer QA records
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2.2 - Concrete sampling and testing
label | Detail - Pre cast Methodology from Pre co to submit to Engineer and Compression Test Report
label | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
label | ○ For repetitive precast underpass units with 6.42m3 each pours undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 days compressive strength in an approved laboratory.
label | Standard / Specification - PS 19.4.3
label | Verifying Document - Slump Test/ Compressive strength test Report at 28 days/Pre pour inspection checklist
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2.3 - Surface Finish of pre cast concrete Units
label | Detail - Surface finish to comply the requirements for pre cast concrete units.
label | Acceptance / Conformance Criteria - For all precast concrete units all surfaces except those against which concrete will be subsequently placed, shall have a concrete surface finish complying with the requirements of NZS 3114, F4 finish for formed surfaces and U3 finish for unformed surfaces.
label | Standard / Specification - PS 19.7.1
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Each Item
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.1 - Post Pour inspections
label | Detail - Post Pour inspection
label | Acceptance / Conformance Criteria - Following the concrete pour and stripping out form works: the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | Standard / Specification - PS 19.3.1
label | Verifying Document - Visual Inspection/ Post pour checklist
label | Testing Quantity Required (based from schedule qtys) - Each Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3.2 - Defective Concrete Finishes
label | Detail - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | Standard / Specification - PS 19.3.1
label | Verifying Document - Visual Inspection/ Post pour checklist
label | Testing Quantity Required (based from schedule qtys) - All Concrete Elements
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3.3 - Joint Sealing of Pre cast members
label | Detail - Joint sealing of pre cast members
label | Acceptance / Conformance Criteria - Joints are to be sealed using a fuel resistant, multi-component polysulphide sealant designed for horizontal and vertical joints in concrete and is joint sealant pourable or gunning grade as appropriate.
label | Standard / Specification - PS 19.12.6
label | Verifying Document - Post installation inspection check list
label | Testing Quantity Required (based from schedule qtys) - After placing pre-cast units
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 – CONSTRUCTION ACTIVITY- POST TENSIONING OF UNDERPASS UNITS
checkpoint | 6.1.1 - Detail methodology for Post Tensioning of Stage 1 of underpass units to develop and send to designer for approval
label | Detail - Detail method of stressing
label | Acceptance / Conformance Criteria - 1*15.2 Galvanized, greased and sheathed strand per corner (Ungrouted) to be inserted in each corner for stage 1, 16 units of underpass.
label | ○ Both ends will have a 40mm rebate for grouting.
label | ○ And those strands will be tensioned to meet the project specification.
label | Standard / Specification - PS 19.14.1
label | Verifying Document - Method Statement
label | Testing Quantity Required (based from schedule qtys) - Before installing units
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1.2 - Detensioning of stage1 underpass units for Stage 2 construction
label | Detail - Detail method of stressing
label | Acceptance / Conformance Criteria - Detensioning will be done on one corner at a time, remove wedges via special pocket pull new strand and tension.
label | ○ This will ensure at least 3 corners remain under tension at any given time.
label | Standard / Specification - PS 19.14.1
label | Verifying Document - Method Statement
label | Testing Quantity Required (based from schedule qtys) - Before landing stage 2 units
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1.3 - Stressing Operation
label | Detail - Post tensioning of strand to be done not to exceed 80% of maximum ultimate breaking strength. Post tensioning strands to be stressed simultaneously or following the sequence of stressing as noted on shop drawings.
label | Acceptance / Conformance Criteria - Stressing forces shall be as per NZS 3101 section 19 for maximum permissible levels of force within a strand during and after stressing.
label | ○ In no case shall a strand be stressed to greater than 80% of its ultimate breaking strength.
label | Standard / Specification - NZS3101 Section 19 PS 19.14.1
label | Verifying Document - Method Statement
label | Testing Quantity Required (based from schedule qtys) - All units for tensioning
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1.4 - Concrete Strength at time of stressing
label | Detail - Samples taken during construction of concrete member to be tested for compressive strength and the results shall be used to determine the acceptability of the structural member for stressing.
label | Acceptance / Conformance Criteria - The minimum compressive strength required before stressing shall be 30MPa unless noted otherwise on the drawings.
label | Standard / Specification - PS 19.14.1
label | Verifying Document - Concrete Test Reports
label | Testing Quantity Required (based from schedule qtys) - as per test report in section 2.2.2
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1.5 - Stressing Calculations
label | Detail - Calculation done will form the basis of comparison to the actual stressing results recorded as an indication that the appropriate levels of stressing are being achieved in each strand.
label | Acceptance / Conformance Criteria - Theoretical calculations for each strand size and profile to determine theoretical jacking forces and corresponding theoretical elongations. These calculations shall be based on the assumed property of strand and forwarded to the Engineer for review and approval at least 7 working days prior to the stressing operations commencing.
label | Standard / Specification - PS 19.14.1
label | Verifying Document - Calculation data sheet
label | Testing Quantity Required (based from schedule qtys) - All units for tensioning
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1.6 - Protection of Strands
label | Detail - Post tensioning strands shall be cut flush with the end faces of the pre cast unit (including any recess) unless noted otherwise on the drawings. Gas cutting of Strand is not permitted.
label | Acceptance / Conformance Criteria - Cut ends of the strand sealed and protected with minimum of 5mm of epoxy mortar or a coat of high build epoxy paint.
label | Standard / Specification - PS 19.14.1
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - All units with Strands
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.1.7 - Stressing Records
label | Detail - Record of stressing shall be taken and reported to designer.
label | Acceptance / Conformance Criteria - Stressing record as per PS 19.14.1 section IV, subsection I
label | Standard / Specification - PS 19.14.1
label | Verifying Document - Stressing records
label | Testing Quantity Required (based from schedule qtys) - All units with Strands
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 7 – CONSTRUCTION ACTIVITY- UNDERPASS WINGWALL, DUCTING AND BACKFILL
checkpoint | 7.1.1 - Position Monitoring
label | Detail - Surveying to be done on the primary structural elements as their construction is completed, location of base slab, strip footing, roof of slab, top of wing walls
label | Acceptance / Conformance Criteria - Surveying done as per PS 18.5.4 on various stages of the construction of underpass. Position of underpass as built and recorded
label | Standard / Specification - PS 18.5.4
label | Verifying Document - Survey recording of position to the required tolerances
label | Testing Quantity Required (based from schedule qtys) - When each construction step finishes
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.1.2 - Placement of Geotextile on Cut Surface
label | Detail - Geotextile to be placed up the sides of the cut surface, with joints overlapped by 500mm minimum
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4 TNZ F/7: 2003 8.3
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Across undercut area
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 7.1.3 - Place Cirtex Armourflow at the face of underpass for backfilling with pavement millings
label | Detail - Armourflow to be placed up the sides of the underpass precast units with lapping as indeicated in the data sheet
label | Acceptance / Conformance Criteria - as per DN1210-WSP-GCO-300
label | Standard / Specification - correspondence
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - side of the underpass pre cast units
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.1.4 - Compaction - Clegg Hammer for underpass side backfill with pavement millings
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Structural Fill Min CIV 28
label | Standard / Specification - DN1210--WSP -GCO-360
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.2.1 - Trench Excavation
label | Detail - To be excavated to within a tolerance.
label | ○ Not more than 100 metres of trench associated with each site shall remain open at one time.
label | Acceptance / Conformance Criteria - +/- 100 mm of the planned horizontal.
label | ○ The maximum deviation shall be 1 in 20 in both the horizontal and vertical planes.
label | ○ Less than 100m
label | Standard / Specification - PS 25.13.2 (Ai)
label | Verifying Document - Survey
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.2 - Unsuitable Materials
label | Detail - All confirmed unsuitable material shall be excavated down to suitable materials.
label | Acceptance / Conformance Criteria - Dig Down to Get Suitable Materials or get Engineers Approval.
label | Standard / Specification - PS 25.13.2 (Bii)
label | Verifying Document - Visual
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.3 - Foundation Compliance
label | Detail - It shall be de-watered prior to installation of bedding material.
label | ○ If the bottom of the trench is naturally occurring rock, or has stones, gravel or other sharp material in occurrence
label | Acceptance / Conformance Criteria - Witness.
label | ○ 50mm granular layer shall be laid and compacted before the bedding layer is laid.
label | Standard / Specification - PS 25.13.2 (G)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.4 - Bedding
label | Detail - The floor of the trench shall be clear of any obstacles and shall be as flat as possible.
label | Acceptance / Conformance Criteria - Mixed Dust to be placed 50mm minimum thickness (compacted) over the bottom of the trench.
label | Standard / Specification - PS 25.13.2 (g) Modified by Engineer WSP
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.5 - Bedding (Enchased in concrete)
label | Detail - Concrete Bedding to be placed. Compressive strength of concrete used no less than 20MPa
label | Acceptance / Conformance Criteria - 50mm
label | Standard / Specification - PS 25.13.7 c)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.6 - Installation of Ducts
label | Detail - If more than 2 ducts are being placed.
label | Acceptance / Conformance Criteria - Must have 50 mm bedding material between the two ducts.
label | Standard / Specification - PS 25.13.7 (B3)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.7 - Warning Tape
label | Detail - Warning tape to be placed above services.
label | Acceptance / Conformance Criteria - Warning Tape to be placed no more than 300mm above the duct
label | Standard / Specification - PS 25.13.7 b) iii & f)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Every Lift
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.8 - Overlay
label | Detail - Mixed Dust to be placed and compacted
label | Acceptance / Conformance Criteria - 100mm thick mixed dust
label | Standard / Specification - PS 25.13.7 b) ii
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Every Lift
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.9 - Overlay (Concrete Enchased Ducts)
label | Detail - Overlay and surroundings to be placed with concrete.
label | Acceptance / Conformance Criteria - 100mm thick on top of Ducts
label | ○ 50mm thick side of the Ducts
label | Standard / Specification - PS 25.13.7 c)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.10 - Overlay Testing (Concrete Enchased)
label | Detail - Placed Concrete needs to meet the strength Criteria
label | Acceptance / Conformance Criteria - >20 MPA
label | Standard / Specification - PS 25.13.7 c)
label | Verifying Document - Concrete Dockets
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 7.2.11 - Backfill
label | Detail - GAP20 to be used if site material is not approved.
label | ○ NDM Testing to be carried out.
label | Acceptance / Conformance Criteria - 100 to 250mm thick compacted material.
label | ○ Min 92% compaction and Average of 95%.
label | Standard / Specification -
label | Verifying Document - Lab report.
label | Testing Quantity Required (based from schedule qtys) - Every Lift
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 7.2.12 - After Completion of Ducts
label | Detail - The Contractor shall pull the pig through the ducts to ensure there are no blockages between access points and no foreign material remains in the duct.
label | Acceptance / Conformance Criteria - The diameter of the pig used for proving the duct or pipe shall be at least 90% of the actual internal diameter of the pipe or duct being proofed.
label | ○ No blockage inside the pipe
label | Standard / Specification - SP 25.13.7 E(1)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.13 - Caps
label | Detail - All duct ends shall be capped
label | Acceptance / Conformance Criteria - Capped ducts
label | Standard / Specification - PS 25.13.7 (EV)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Every time
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.2.14 - Survey As Built
label | Detail - As Built every ducts joint before backfill
label | Acceptance / Conformance Criteria - Completed as per drawings
label | Standard / Specification - Standard Practise
label | Verifying Document - Survey
label | Testing Quantity Required (based from schedule qtys) - on going
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 7.2.15 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Structural Fill
label | — Min CIV 18
label | — Ave CIV 20
label | ○ Non-Structural Fill
label | — Min CIV 10
label | — Max CIV 12
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.2.16 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | ○ Non Granular Material
label | ○ Max Air Voids 8%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.3.1 - Subsoil Drain inspection
label | Detail - Subsoils to be placed adjacent to the underpass and inspected by Engineer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 17.6.3
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - No less than 24 hours prior to placement of backfill
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
checkpoint | 7.3.2 - Excavation
label | Detail - Excavation of Trench should be within tolerances.
label | Acceptance / Conformance Criteria - 335mm deep x 300mm wide
label | Standard / Specification - Drawings
label | Verifying Document - Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.3.3 - Placement of Bidim
label | Detail - A29 Bidim to be placed and wrapped around Trench.
label | Acceptance / Conformance Criteria - Minimum Width 300mm.
label | Standard / Specification - Drawings
label | Verifying Document - Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.3.4 - Cushion (Bedding)
label | Detail - Pipe must have 75mm of Cushion. Drainage 60:40 Material to be used.
label | Acceptance / Conformance Criteria - Minimum 75mm
label | Standard / Specification - Drawings
label | Verifying Document - Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.3.5 - Placement of Pipe
label | Detail - 110mm Perforated Pipe to be laid Down
label | Acceptance / Conformance Criteria - As Per Drawings
label | Standard / Specification - Drawings
label | Verifying Document - Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 7.3.6 - Backfill
label | Detail - Pipe Must have a 150mm cover from Bottom of Pavement.
label | ○ Drainage 20:40 Material to be used.
label | Acceptance / Conformance Criteria - >150mm Cover
label | Standard / Specification - Drawings
label | Verifying Document - Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
section | SECTION 8 - UNDERPASS GRATED TRENCH DRAIN
checkpoint | 8.1 - Installation of Channel Drain
label | Detail - 300mm wide grated trench drain with WAVE HEELSAFE grate to be located at end of underpass apron. Trench drain to connect to SWMH2.1.5 via dn150 pvc-u sn16 pipe. Grated trench drain to have min. loading class C.
label | Acceptance / Conformance Criteria - Installed as per manufactures instructions
label | Standard / Specification - 21.5.8
label | Verifying Document - Inspection and record
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
section | SECTION 9 - AS-BUILTS/ REDPEN MARKUPS (Wave Heelsafe grate and minimum internal fall of 0.5%.)
checkpoint | 9.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria - As built drawing red pen markups
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - D
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature