## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | LQS-QA-6000 - ITP - Compliance Record | itp |  |  |  |  | LQS-QA-6000 - ITP - Compliance Record
section | Compliance Record
checkpoint | 1 - Pre-construction sign-offs
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Is there a Safe Work Method Statement for this task?
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review, Submission
label | CONFORMANCE CRITERIA - Relevant parties to review, Note Method statement in the Comments
label | RECORDS - Sign off this task
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Review relevent design / task characteristics and identify hold points
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - All design requirements are met
label | RECORDS - Sign off this task
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Is a temporary works design required for this task?
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review, Submission
label | CONFORMANCE CRITERIA - Temporary Works design completed and attached
label | RECORDS - TW design, Sign off this task
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Technical Reports
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - If relevant attach technical reports
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - All related reports attached
label | RECORDS - Sign off this task
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Materials
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - If required provide required laboratory testing reports, material designs and attach i.e. grading curves, concrete design, steel certs etc.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review, submission
label | CONFORMANCE CRITERIA - All related reports are attached
label | RECORDS - Laboratory test results, Sign off this task
checkpoint | 5 - Field Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Complete any field testing and Checksheets required by permanent design or temporary works design
label | FREQUENCY - During construction
label | INSPECTION - Testing
label | CONFORMANCE CRITERIA - All related reports are attached
label | RECORDS - Field Test, Sign off this task
checkpoint | 6 - Photo Records
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Attach photo records
label | FREQUENCY - As completed
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - All related photos are attached
label | RECORDS - Photo records, Sign off this task
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | LQS-QA-6007 - ITP - Drainage Installation | itp |  |  |  |  | LQS-QA-6007 - ITP - Drainage Installation
section | Drainage Installation
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), PTW #2 Trench Excavation Inspection, Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - IFC Drawings
label | RECORDS - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Setout inlet & outlet points with inverts as required by Contractor to construct to design
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Survey is correct and consistent with plans
label | RECORDS - Photo
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Fill Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Bedding, Side support and Overlay materials tested in accordance with Specifications
label | FREQUENCY - Prior to Installation
label | INSPECTION - Document review, Lab Testing
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Lab Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pipes and Precast Units (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Confirm pipes diameter, class & jointing type, as well as manholes, are as shown on the drawings, and that the pipes/pre-cast units are correct and in good condition.
label | FREQUENCY - Each delivery to site
label | INSPECTION - Certification
label | CONFORMANCE CRITERIA - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
label | RECORDS - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pipes and Precast Units (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Flanges, Valve boxes, Fire Hydrants, bolts, nuts, washers shall be as in accordance with the Specifications
label | FREQUENCY - Prior to Installation
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Trenching (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Inspect trench profile and ensure it is correct to lines and levels to design. Ensure trench width is sufficient to provide enough space on either side of the pipe for compaction
label | FREQUENCY - Prior to Installation
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - 350mm for external dia >900. DN900 for SW1, Line and level is correct
label | RECORDS - LQS-CS-4025
checkpoint | 6 - Trenching (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Base of trenching to be inspected by Design Engineer. If undercutting required or excess water encountered, backfill material and method to be agreed before proceeding
label | FREQUENCY - Scalar 1/20m length of trench
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Review Inferred CBRs with Design Engineer to sign-off
label | RECORDS - LQS-CS-4003 Scala Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Pipe Installation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Bedding to be placed and compacted 150mm thick bedding for pipe dia between 450 to 1500
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Lab Testing
label | CONFORMANCE CRITERIA - AP20 Bedding
label | ○ Clegg hammer CIV = >25 in engineered fill, and within berm (if req'd) CIV = >20
label | ○ Pea Metal Bedding
label | ○ Photo record of bedding.
label | RECORDS - LQS-CS-4025
checkpoint | 7 - Pipe Installation (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 5mm
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Vertical tolerance +/- 5mm, unless approved by eng rep
label | RECORDS - LQS-CS-4025
checkpoint | 7 - Pipe Installation (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Pipe invert checks shall be carried out at least once per day with a maximum of 20m between checks.
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Vertical tolerance +/- 5mm, unless approved by eng rep
label | RECORDS - LQS-CS-4025
checkpoint | 7 - Pipe Installation (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - No defects/ gaps / pipes are aligned correctly
label | RECORDS - Photos
checkpoint | 7 - Pipe Installation (5)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Backfill compacted and tested in 200mm thick layers
label | FREQUENCY - 1/20m length of pipe
label | INSPECTION - Measure/Testing
label | CONFORMANCE CRITERIA - <Subbase Layer
label | — Clegg CIV >25 for engineered fill. In berms, Photo record.
label | ○ Subbase Layer
label | — 95% MDD under carriageway for engineered fill. In berms, Photo record
label | ○ Basecourse Layer
label | — 98% MDD for engineered fill. In berms, Photo record
label | RECORDS - Lab test Results/Photo/Clegg Sheet
checkpoint | 8 - Structure installation (Manhole, Catchpit, Wingwall) (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Base of structure to be tested. Scala's to be minimum of 3 blows per 100mm
label | FREQUENCY - 1 test per structure
label | INSPECTION - Testing
label | CONFORMANCE CRITERIA - Scala minimum 3 blows/100mm
label | RECORDS - LQS-LA-4003
checkpoint | 8 - Structure installation (Manhole, Catchpit, Wingwall) (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Structures to be installed to the design survey location and level
label | FREQUENCY - During structure construction
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - As-Built Survey
label | RECORDS - LQS-CS-4006, As-Builts
checkpoint | 8 - Structure installation (Manhole, Catchpit, Wingwall) (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Corbals to be poured around each connection to a manhole structure
label | FREQUENCY - During structure construction
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - Pipe joint to structure shall be encased in 200mm (min.) thick 20MPa concrete
label | RECORDS - LQS-CS-4006
checkpoint | 8 - Structure installation (Manhole, Catchpit, Wingwall) (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - As-built survey of the structure and all invert levels
label | FREQUENCY - Once installed
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - As Built Survey
label | RECORDS - As builts
checkpoint | 9 - CCTV
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - For pipes <900mm a CCTV inspection must be completed. Pipes >900mm must be visually inspected
label | FREQUENCY - At completion of the works
label | INSPECTION - Visual Inspection/ CCTV inspection
label | CONFORMANCE CRITERIA - No Defects
label | RECORDS - Inspection Report CCTV DVD
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Testing of Manholes & Pipelines
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - If required, testing for water tightness in the structures and low pressure air testing of the pipelines is to be carried out - test sheets to be filling in where required
label | FREQUENCY - One per line/structure
label | INSPECTION - Measurement
label | CONFORMANCE CRITERIA - Drainage Structure Water Tightness Test Record & Low Pressure Air Test Record
label | RECORDS - LQS-CS-4073 & FHIMS-CS-4074
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure all drainage lines comply with design prior to carrying on with next construction process
label | FREQUENCY - At completion of drainage line
label | INSPECTION - Measurement
label | RECORDS - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Updated drawings to be submitted with As-built line and levels recorded
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | LQS-QA-6090 - ITP - Service Installation | itp |  |  |  |  | LQS-QA-6090 - ITP - Service Installation
section | Service Installation
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), PTW #1 - Confined Space, PTW #2 - Trench Excavation Inspection, Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - IFC Drawings
label | RECORDS - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Set out utiliy service alignment, and depths per construction drawings
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Survey is correct and consistent with plans
label | RECORDS - Photo
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - PVC ducting shall be of approved material and/or supplied by service provider
label | FREQUENCY - Prior to instalment
label | INSPECTION - Document/Visual
label | CONFORMANCE CRITERIA - Ducts are acceptable to the service providers standards
label | RECORDS - Delivery Docket/ Service Provider acceptance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure cables, transformers and ring main units are to (service Providers) specifications
label | FREQUENCY - Prior to installation
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - As per (Power Providers) specifications
label | RECORDS - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Bedding material/backfill shall meet the specifications of the service provider/Specifications
label | FREQUENCY - Prior to installation
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - As per (Power Providers) specifications, NTLDM
label | RECORDS - Delivery dockets, Lab Material testing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Trenching & Service Installation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Inspect trench profile and ensure it is correct to lines and levels set out by survey
label | FREQUENCY - Daily
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Depth and line is correct as per for construction drawings
label | RECORDS - FHIMS-CS-4010
checkpoint | 6 - Trenching & Service Installation (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - 100mm thick bedding to be placed and compacted and cable laid (by other)
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - >100mm of clean sand bedding
label | RECORDS - FHIMS-CS-4010
checkpoint | 6 - Trenching & Service Installation (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - As built survey at intervals of no more than 20m and at each change in direction
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - As-built points spacing to be less than 20m at all times
label | RECORDS - As-Builts
checkpoint | 6 - Trenching & Service Installation (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - If required, Mag slab to be installed 300mm above the cable
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Mag slab to be laid on top of clean sand layer
label | RECORDS - FHIMS-CS-4010
checkpoint | 6 - Trenching & Service Installation (5)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet (Power Providers) specification.
label | FREQUENCY - Every 300mm lift
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - <Subbase Layer
label | — Clegg CIV >25 for engineered fill. In berms, Photo record.
label | ○ Subbase Layer
label | — 95% MDD under carriageway for engineered fill. In berms, Photo record
label | ○ Basecourse Layer
label | — 98% MDD for engineered fill. In berms, Photo record
label | RECORDS - Lab Test results, Clegg Hammer Checksheet
checkpoint | 7 - Directional Drilling (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - PE Pipe installed by drilling to survey setout, draw wire/draw rope installed and cable pulled through pipe
label | FREQUENCY - Daily
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Line and depth consistent with for construction drawings
label | RECORDS - Survey receipt
checkpoint | 7 - Directional Drilling (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - As built survey of the PE pipe installed including depth using depths marked by drilling contractors
label | FREQUENCY - After duct has been installed
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - As-built points spacing to be less than 20m at all times
label | RECORDS - As-Builts
checkpoint | 7 - Directional Drilling (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Backfill connection pits, Sand placed to bed cabling. Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet power providers specification.
label | FREQUENCY - As required by specification
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - <Subbase Layer
label | — Clegg CIV >25 for engineered fill. In berms, Photo record.
label | ○ Subbase Layer
label | — 95% MDD under carriageway for engineered fill. In berms, Photo record
label | ○ Basecourse Layer
label | — 98% MDD for engineered fill. In berms, Photo record
label | RECORDS - Lab Test results,Photo
checkpoint | 8 - Feature installation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Feature such as poles, transformers, distribution pillars installed as per IFC drawings
label | FREQUENCY - Daily checks
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Location of feature consistent with for construction drawings
label | RECORDS - Survey receipt
checkpoint | 8 - Feature installation (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Install overhead lines to the locations shown on the drawings
label | FREQUENCY - Daily checks
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Consistent with for construction drawings
label | RECORDS - Certificate of acceptance
checkpoint | 9 - Connection
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Complete all jointing and carry out testing
label | FREQUENCY - After instalment of Cable/Ducts
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Commissioning tests all pass
label | RECORDS - Confirmation Note
checkpoint | 10 - Service handover
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Service accepted by the service provider
label | FREQUENCY - Completion of works
label | INSPECTION - Document
label | CONFORMANCE CRITERIA - Service provider approval
label | RECORDS - Certificate of acceptance
checkpoint | 11 - Abandonment (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Once the existing power line is taken out of service it shall be capped and sealed in the locations on the IFC drawings
label | FREQUENCY - Completion of works
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Consistent with for construction drawings
label | RECORDS - As-built drawings
checkpoint | 11 - Abandonment (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Remove all other redundant items such as redundant poles, pillar boxes, overhead lines etc.
label | FREQUENCY - Completion of works
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Site clear of redundant items
label | RECORDS - As-built drawings
checkpoint | 12 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Updated drawings to be submitted with As-built line and levels recorded
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, service provider secification
label | RECORDS - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | LQS-QA-6092 - ITP - Water Services | itp |  |  |  |  | LQS-QA-6092 - ITP - Water Services
section | Water Services
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), PTW #2 Trench Excavation Inspection, Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - IFC Drawings
label | RECORDS - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Set out watermain alignment, design features and depths per construction drawings
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Survey is correct and consistent with plans
label | RECORDS - Photo
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Bedding, Side support and Overlay materials tested in accordance with Specifications
label | FREQUENCY - Baseline test
label | INSPECTION - Document review Lab Testing
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Lab Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - HDPE pipe is in accordance with specifications. If Butt welded, this has been completed in accordance with Specifications and correct number of test welds completed
label | FREQUENCY - Prior to Installation
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, Project specification
label | RECORDS - PE welder Record, Delivery Dockets, Test weld cert
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - PVC pipe is in accordance with specifications. Joins shall have spigot and socket joints with rubber rings
label | FREQUENCY - Prior to Installation
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, Project specification
label | RECORDS - Photo, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Flanges, Valve boxes, Fire Hydrants, bolts, nuts, washers shall be as in accordance with the Specifications
label | FREQUENCY - Prior to Installation
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (5)
label | DETAIL - Concrete - ensure its in accordance with the Specifications
label | FREQUENCY - Prior to Installation
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Delivery Dockets
checkpoint | 6 - Trenching (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Inspect trench profile and ensure it is correct to lines and levels set out by survey
label | FREQUENCY - Daily
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Depth and line is correct as per for construction drawings
label | RECORDS - LQS-CS-4101
checkpoint | 6 - Trenching (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Base of trenching to be inspected by Design Engineer. If underctting required, backfill material and method to be agreed before proceeding
label | FREQUENCY - Scalar 1/20m length of trench
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Review Inferred CBRs with Design Engineer to sign-off
label | RECORDS - LQS-CS-4003 Scala Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Pipe Installation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - 100mm thick bedding to be placed and compacted
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Lab Testing
label | CONFORMANCE CRITERIA - AP20 Bedding
label | ○ Clegg hammer CIV = >35 in engineered fill, and within berm (if req'd) CIV = >25
label | ○ Pea Metal Bedding
label | ○ Photo record of bedding.
label | ○ NTLDM 7.8.7
label | RECORDS - LQS-CS-4101
checkpoint | 7 - Pipe Installation (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - The pipe and fittings will be laid to within tolerance/specification.
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - As-Built
checkpoint | 7 - Pipe Installation (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Pipe bends installed in the locations as per the drawings
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing
label | RECORDS - Photo/As-Built
checkpoint | 7 - Pipe Installation (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Thrust blocks installed as required and per drawings
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - 25 Mpa concrete unless otherwise stated, per design drawings
label | RECORDS - Delivery dockets
checkpoint | 7 - Pipe Installation (5)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Denso to be applied to all steel fittings, bolts, nuts and washers
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Photo
checkpoint | 7 - Pipe Installation (6)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - As built survey at 20m intervals and at each change in direction, and butt weld/EF
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - As-Built
checkpoint | 7 - Pipe Installation (7)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Approved Detector tape for Watermain to be installed 300mm above the pipe
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, SD702
label | RECORDS - LQS-CS-4101
checkpoint | 7 - Pipe Installation (8)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Backfill compacted and tested in 200mm thick layers
label | FREQUENCY - 1/20m length of pipe
label | INSPECTION - Measure/Testing
label | CONFORMANCE CRITERIA - <Subbase Layer
label | — Clegg CIV >25 for engineered fill. In berms, Photo record.
label | ○ Subbase Layer
label | — 95% MDD under carriageway for engineered fill. In berms, Photo record
label | ○ Basecourse Layer
label | — 98% MDD for engineered fill. In berms, Photo record
label | RECORDS - Lab test Results/Photo/Clegg Sheet
checkpoint | 8 - Hydrants and Valves (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Fire Hydrant Lids shall be painted golden yellow. A yellow triangle shall be painted on or near the centre line of the road and RRPM. A yellow circle encircling the hydrant shall be painted if its location can be obscured by parked vehicles.
label | FREQUENCY - All fire hydrants
label | INSPECTION - Painting
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, SD709
label | RECORDS - Photo
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Hydrants and Valves (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Marker plates on posts shall be installed near all watermain valves, if required. Valves to be painted to sepcification
label | FREQUENCY - All valves
label | INSPECTION - Post installation
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, SD709
label | RECORDS - Photo
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Inspection and Pretesting
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Watermain, service connections and fittings shall be flushed before testing
label | FREQUENCY - Prior to Testing
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - LQS-CS-4101
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pre-commissioning (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All mains, service connections and fittings shall be pressure tested
label | FREQUENCY - Prior to Pre-Commissioning
label | INSPECTION - Rebound Testing
label | CONFORMANCE CRITERIA - 1200kPa for treated water mains
label | — 540kPa for DN375 raw water
label | — 645kPa for DN450 raw water pipe
label | — 1350 kPa Wasterwater pipe
label | (1.5 x operating pressure rule of thumb)
label | RECORDS - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pre-commissioning (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Pipe sterilisation testing for the whole length. Once completed Chorinated water to be discharged
label | FREQUENCY - Prior to Commissioning
label | INSPECTION - Residual Chlorine Test
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pre-commissioning (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Bacteriological Test
label | FREQUENCY - Prior to Commissioning
label | INSPECTION - Tests
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM. 0 E.coli present in pipe
label | RECORDS - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Shutdown
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Apply for Shutdown of Mains with diagram, site preparation plan and duration. Notify Council of Shutdown Commencement, carry out required work, notify Council of completion of works.
label | FREQUENCY - Prior to programmed work
label | INSPECTION - Liaise with Council
label | CONFORMANCE CRITERIA - Completed shutdown plan approved by council
label | RECORDS - Written approval from the Council
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Tie-in and commissioning (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Connection to existing water reticulation per specifiction
label | FREQUENCY - During shutdown
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Tie-in and commissioning (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Post connection inspection
label | FREQUENCY - Completion of works
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Inspection
label | RECORDS - Site confimation
checkpoint | 13 - Abandonment
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Remove all fittings from disused watermains if required. Capping of ends of abandoned pipes
label | FREQUENCY - After Tie-in
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Photos
checkpoint | 14 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Updated drawings to be submitted with As-built line and levels recorded
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
label | RECORDS - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP