## Table 1
Scope: Speedpanel & Pre-hang Fire Rated Plasterboard |  |  | ITP Document No.: 1 |  |  |  | Revision No. A |  |  | Date of Revision: 24/05/2025
Project Name: St John of God Midland Private Hospital | [6 empty] | Organization Name: Built
Project Address: Lot 787 & Lot 788 Workshop Avenue Midland, WA, 6056
Prepared by
Name: Austin Han |  |  | Position: Contract Administrator |  |  |  | Signature: |  |  | Date: 24/05/2025
Approved by
Name: Shiyong Lim |  |  | Position: Site Foreman |  |  |  | Signature: |  |  | Date: 24/05/2025
Level: | [6 empty] | Zone:
Project Specification: STH-AR-SPC-0001 ¦ Australian Standards: AS2589 ¦ Project Drawings: STH-A03, STH-A08 Series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity | Reference Documents |  | Acceptance Criteria |  | Frequency |  |  | Verification Records/Comments | Inspection By
[10 empty] | Subcontractor | Built | Client
1 | Set out Speedpanel walls | STH-A03, STH-A08 Series |  | Light Weight Wall Plan approved by Built Speedpanel Concrete Connections Edition 2 Release 1 |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
2 | Install Speedpanel | STH-A03, STH-A08 Series |  | Light Weight Wall Plan approved by Built. Speedpanel Concrete Connections Edition 2 Release 1 |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
3 | Caulking |  |  | Speedpanel Concrete Connections Edition 2 Release 1 |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
4 | Clean up |  |  | Waste all cleaned. Tools and materials placed well. |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos |  | R
5 | Pre-hang fire rated plasterboard | Architect drawings |  | Light Weight Wall Plan approved by Built. GTEK Ceiling & Wall Solution Rev. Mar.2024 |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
6 | Taping and stopping | Architect drawings |  | GTEK Ceiling & Wall Solution Rev. Mar.2024 |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
7 | Clean up |  |  | Waste all cleaned. Tools and materials placed well. |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos |  | R
Comments:
Date of Inspection: |  |  |  |  | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [7 empty] | Attachments  Checklists |  |  Photos
[8 empty] |  Dockets |  |  Sample Material
[8 empty] |  Drawings |  |  Calibration Certificates
[8 empty] |  Test Results / Certificate |  |  Others:
 Inspection reports
Signed : | [7 empty] | Date: