## Table 1
Scope: Hang ceilings and stop, sand walls & ceilings |  |  | ITP Document No.: 4 |  |  | Revision No. A |  |  | Date of Revision: 24/05/2025
Project Name: St John of God Midland Private Hospital | [5 empty] | Organization Name: Built
Project Address: Lot 787 & Lot 788 Workshop Avenue Midland, WA, 6056
Prepared by
Name: Austin Han |  |  | Position: Contract Administrator |  |  | Signature: |  |  | Date: 24/05/2025
Approved by
Name: ChunLong Zang |  |  | Position: Construction Manager |  |  | Signature: |  |  | Date: 24/05/2025
Level: | [5 empty] | Room No./Area:
Project Specification: STH-AR-SPC-0001 ¦ Australian Standards: AS2589 ¦ Project Drawings: STH-A00, STH-A03, STH-A04, STH-A05, STH-A06, STH-A08, STH- A012 Series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity | Reference Documents | Acceptance Criteria | Frequency |  |  | Verification Records/Comments |  | Inspection By
[9 empty] | Subcontractor | Built | Client
1 | Insulation to ceilings | Architect drawings | Architect RCP drawings approved by Built. | Each unit |  |  | Visual Checklist Attached marked off drawings and photos |  | S | S
2 | Sheets to ceiling | Architect drawings | Architect RCP drawings approved by Built. GTEK Ceiling & Wall Solutions Rev. Mar.2024 Siniat Blueprint Lightweight Construction Manual Ver 4 April 2025 | Each unit |  |  | Visual Checklist Attached marked off drawings and photos |  | S | HP
3 | Stopping to walls & ceilings | Architect drawings | GTEK Ceiling & Wall Solutions Rev. Mar.2024 Siniat Blueprint Lightweight Construction Manual Ver 4 April 2025 | Each location |  |  | Visual Checklist Attached marked off drawings and photos |  | S | S
4 | Sanding to walls & ceilings | Architect drawings | GTEK Ceiling & Wall Solutions Rev. Mar.2024 Siniat Blueprint Lightweight Construction Manual Ver 4 April 2025 | Each location |  |  | Visual Checklist Attached marked off drawings and photos |  | S | S
5 | Fit access hatch frame | Architect drawings | Architect RCP drawings approved by Built. | Each location |  |  | Visual Checklist Attached marked off drawings and photos |  | S | S
6 | Cut out for lights | Architect drawings | Architect RCP drawings approved by Built. | Each location |  |  | Visual Checklist Attached marked off drawings and photos |  | S | S
7 | Clean up |  | Waste all cleaned. Tools and materials placed well. | Each location |  |  | Visual Checklist Attached marked off drawings and photos |  |  | R
Comments:
Date of Inspection: |  |  |  | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) |  |  |  |  | Attachments  Checklists |  |  |  Photos
[5 empty] |  Dockets |  |  |  Sample Material
[5 empty] |  Drawings |  |  |  Calibration Certificates
[5 empty] |  Test Results / Certificate |  |  |  Others:
 Inspection reports
Signed : |  |  |  |  | Date: