## Table 1
Inspection and Test Plan
Scope: Rigid Board |  |  | ITP Document No.: 5 |  |  | Revision No. A |  |  | Date of Revision: 24/05/2025
Project Name: St John of God Midland Private Hospital | [5 empty] | Organization Name: Built
Project Address: Lot 787 & Lot 788 Workshop Avenue Midland, WA, 6056
Prepared by
Name: Austin Han |  |  | Position: Contract Administrator |  |  | Signature: |  |  | Date: 24/05/2025
Approved by
Name: Shiyong Lim |  |  | Position: Site Foreman |  |  | Signature: |  |  | Date: 24/05/2025
Level: | [5 empty] | Room No./Area:
Specification: STH-AR-SPC-0001 ¦ Project Drawings: STH-A05 series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity | Reference Documents | Acceptance Criteria | Frequency |  |  | Verification Records/Comments | Inspection By
[8 empty] | Subcontractor |  | Built | Client
1 | Set out Rigid Board | Architect drawings | Insulation U/S Concrete Slab drawing approved by Built | Each location |  |  | Visual Checklist | S |  | S
2 | Install Rigid Board | Architect drawings | Insulation U/S Concrete Slab drawing approved by Built Kingspan Kooltherm K10 G2 Installation Instruction | Each location |  |  | Visual Checklist | S |  | S
3 | Tape & Seal |  | Kingspan Kooltherm K10 G2 Installation Instruction | Each location |  |  | Visual Checklist | S |  | S
4 | Clean up |  | Waste all cleaned. Tools and materials placed well. | Each location |  |  | Visual Checklist |  |  | R
Comments:
Date of Inspection: |  |  |  |  | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [5 empty] | Attachments  Checklists |  |  Photos
[6 empty] |  Dockets |  |  Sample Material
[6 empty] |  Drawings |  |  Calibration Certificates
[6 empty] |  Test Results / Certificate |  |  Others:
 Inspection reports
Signed : | [5 empty] | Date:
Page 1 of 1