## Sheet1
1 | Set out Speedpanel walls | STH-A03, STH-A08 Series | Light Weight Wall Plan approved by Built Speedpanel Concrete Connections Edition 2 Release 1 | Each location | Visual Checklist Attached marked off drawings and photos | S | S | 1 - Set out Speedpanel walls | Reference Documents - STH-A03, STH-A08 Series | Acceptance Criteria - Light Weight Wall Plan approved by Built Speedpanel Concrete Connections Edition 2 Release 1 | Frequency - Each location | Verification Records/Comments - Visual Checklist Attached marked off drawings and photos | Inspection By: Subcontractor - S | Inspection By: Built - S | Inspection By: Client - | 1 - Set out Speedpanel walls
2 | Install Speedpanel | STH-A03, STH-A08 Series | Light Weight Wall Plan approved by Built. Speedpanel Concrete Connections Edition 2 Release 1 | Each location | Visual Checklist Attached marked off drawings and photos | S | S | [8 empty] | Reference Documents - STH-A03, STH-A08 Series
3 | Caulking |  | Speedpanel Concrete Connections Edition 2 Release 1 | Each location | Visual Checklist Attached marked off drawings and photos | S | S | [8 empty] | Acceptance Criteria - Light Weight Wall Plan approved by Built Speedpanel Concrete Connections Edition 2 Release 1
4 | Clean up |  | Waste all cleaned. Tools and materials placed well. | Each location | Visual Checklist Attached marked off drawings and photos |  | R | [8 empty] | Frequency - Each location
5 | Pre-hang fire rated plasterboard | Architect drawings | Light Weight Wall Plan approved by Built. GTEK Ceiling & Wall Solution Rev. Mar.2024 | Each location | Visual Checklist Attached marked off drawings and photos | S | S | [8 empty] | Verification Records/Comments - Visual Checklist Attached marked off drawings and photos
6 | Taping and stopping | Architect drawings | GTEK Ceiling & Wall Solution Rev. Mar.2024 | Each location | Visual Checklist Attached marked off drawings and photos | S | S | [8 empty] | Inspection By: Subcontractor - S
7 | Clean up |  | Waste all cleaned. Tools and materials placed well. | Each location | Visual Checklist Attached marked off drawings and photos |  | R | [8 empty] | Inspection By: Built - S
Inspection By: Client -