## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP01 - 7059 - KAITAIA WASTEWATER OVERFLOW REDUCTION STAGE 1 | itp
section | ESTABLISHMENT
checkpoint | Pre-Start/Site Establishment
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Pipeline Specification, page 7
label | ACTIVITY/TASK - Visual inspection of site establishment.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to commencing works on site.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
checkpoint | Site Clearance - Inspection of Defined Limits and Vegetation Removal
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Pipeline Specification, page 9
label | ACTIVITY/TASK - Visual inspection of defined limits and vegetation removal.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY -
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
checkpoint | Survey Setout
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Pipeline Specification, page 15
label | ACTIVITY/TASK - Set out the work to conform with the drawings.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to commencing each stage of work.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
checkpoint | Service Location
label | SPECIFICATION REFERENCE - Project Specification, page 16, clause 6.4
label | ACTIVITY/TASK - Locate and protect existing services. Arrange with external network utility operators as required.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to commencing each stage of work.
label | ACCEPTANCE CRITERIA - Record of services location. Photos.
label | UCCL -
label | FNDC -
checkpoint | Aggregate
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Page 121, Clause 3.3
label | ACTIVITY/TASK - Aggregate testing to comply with FNDC Engineering Standards.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Test certificates to be provided to Engineer for approval prior to using aggregate on site.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Material test certificates.
label | UCCL - H
label | FNDC - H
section | MANHOLE/PIPELINE INSTALLATION (TRENCHED)
checkpoint | Manhole Excavation and Bedding
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 39
label | ACTIVITY/TASK - Visual check of excavation. Subgrade meets specification. Hardfill layer constructed as per project drawings.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to installing each manhole.
label | ACCEPTANCE CRITERIA - Subgrade meets minimum CBR of 5 (1.5 blows/50mm).
label | ○ Miniumum 150mm layer of GAP65, minimum CIV of 25.
label | UCCL - H
label | FNDC - H
checkpoint | Materials Quality
label | SPECIFICATION REFERENCE - FNDC Approved Material List
label | ACTIVITY/TASK - Visual check for approved materials, quality and condition.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On arrival to site, prior to using materials.
label | ACCEPTANCE CRITERIA - Delivery dockets, photos.
label | UCCL - W
label | FNDC - R
checkpoint | Manhole Installation
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 39
label | ACTIVITY/TASK - Manhole installed in correct position and to correct level as per Project Drawings and FNDC EES.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of each manhole.
label | ACCEPTANCE CRITERIA - Completed manhole installation checklist, photos.
label | UCCL - P
label | FNDC - R
checkpoint | Pipeline Excavation and Bedding
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 9. FNDC Engineering Standards 2023, Sheets 31-37
label | ACTIVITY/TASK - Visual check of excavation. Lower bedding layer constructed as per project drawings.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to laying pipe.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Photos.
label | UCCL - H
label | FNDC - H
checkpoint | Pipeline Installation
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 9.
label | ACTIVITY/TASK - Pipeline installed to correct invert levels and grade.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each pipeline (manhole-to-mahole) prior to backfilling.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. As-builts drawings. Completed pipeline installation checklist, photos.
label | UCCL - H
label | FNDC - H
checkpoint | Testing of Manholes and Pipelines
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 9.
label | ACTIVITY/TASK - Engineer's Representative to witness testing of manholes and pipelines.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - During testing of manholes and pipelines.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Testing checklists.
label | UCCL - H
label | FNDC - H
checkpoint | Sewer Connections (Household)
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Sheet 37
label | ACTIVITY/TASK - Visual check of connection.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of each connection.
label | ACCEPTANCE CRITERIA - As-built drawings. Photos.
label | UCCL - P
label | FNDC - R
checkpoint | Sewer Connection (to Existing Wastewater System)
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 9.
label | ACTIVITY/TASK - Inspection prior to connection into exisitng wastewater system.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of installation, prior to connecting to existing wastewater system.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
Section | STORAGE TANK
checkpoint | Aggregate
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Aggregate certificates to comply with tank design.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to using as hardfill/backfill.
label | ACCEPTANCE CRITERIA - Approval by tank designer. Acceptance by Engineer's Representative. Material certificates.
label | UCCL - H
label | FNDC - H
checkpoint | Excavation to Top of Sheetpiles
label | SPECIFICATION REFERENCE -
label | ACTIVITY/TASK - Visual check of excavation, levels, position.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of excavation.
label | ACCEPTANCE CRITERIA - Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Sheetpile Installation
label | SPECIFICATION REFERENCE -
label | ACTIVITY/TASK - Sheetpiles installed as per temporary works design. As-built taken of sheet-piles to use for periodic checks throughout construction.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of sheet piling, prior to excavtion.
label | ACCEPTANCE CRITERIA - Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Excavation and Subgrade inside Sheetpiles
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 3.
label | ACTIVITY/TASK - Visual check of excavation, levels, position. Subgrade meets specification. Engineer to confirm grounding conditions and wastewater control.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of excavation, prior to placing hardfill.
label | ACCEPTANCE CRITERIA - Acceptance by Engeineer's Representative.
label | UCCL - H
label | FNDC - H
checkpoint | Hardfill Layer
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Visual check of hardfill layer. Hardfill layer meets specification.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY -
label | ACCEPTANCE CRITERIA - Confirmation from tank design Engineer. Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Deadman Beams
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Deadman beams placed as per specification.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of deadman beams, prior to backfilling.
label | ACCEPTANCE CRITERIA - As-built drawings. Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Tank Installation
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Tank installed as per specification.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of tank, prior to backfilling.
label | ACCEPTANCE CRITERIA - As-built drawings. Photos.
label | UCCL - P
label | FNDC - W
checkpoint | Tank Backfill
label | SPECIFICATION REFERENCE - As per Tank Design.
label | ACTIVITY/TASK - Tank backfill as per specification.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of backfill.
label | ACCEPTANCE CRITERIA - Record of 'Vertical Diamter Measurements'. Photos.
label | UCCL - P
label | FNDC - W
Section | WET WELL INSTALLATION
checkpoint | Pumps and Mechanical Equipment
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 4.
label | ACTIVITY/TASK - Engineer to approve specification prior to contractor placing supplier order.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to ordering pumps and mechanical equipment.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Specifications for pumps and mechanical equipment.
label | UCCL - R
label | FNDC - R
checkpoint | Excavation and Subgrade inside Sheetpiles
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 3.
label | ACTIVITY/TASK - Visual check of excavation, levels, position. Subgrade meets specification. Engineer to confirm grounding conditions and wastewater control.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of excavation, prior to placing hardfill.
label | ACCEPTANCE CRITERIA - Acceptance by Engeineer's Representative.
label | UCCL - H
label | FNDC - H
checkpoint | Pumps and Mechanical Equipment
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 4.
label | ACTIVITY/TASK - Engineer to review certification and inspect installation.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of pumps and mechanical equipment.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
checkpoint | Hydrostatic Testing
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 10.
label | ACTIVITY/TASK - Testing done by manufacturer/supplier. Certificate to be provided with tank.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On acceptance of tank on site.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Supplier documentation.
label | UCCL - H
label | FNDC - H
checkpoint | Testing of Pumps
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Technical Specification Part B, page 10.
label | ACTIVITY/TASK - Witness draw-down testing of pumps.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - During commissioning of pumps.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Commissioning checklist.
label | UCCL - H
label | FNDC - H
checkpoint | Electrical and SCADA
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage 1 Electrical Specification, page 20.
label | ACTIVITY/TASK - Review switchboard test certification and inspect the installation.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of installation of the wet well.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative.
label | UCCL - H
label | FNDC - H
Section | PAVEMENT
checkpoint | Aggregate
label | SPECIFICATION REFERENCE - FNDC Engineering Standards 2023, Page 121, Clause 3.3
label | ACTIVITY/TASK - Aggregate testing to comply with FNDC Engineering Standards.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Test certificates to be provided to Engineer for approval prior to using aggregate on site.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Material test certificates.
label | UCCL - H
label | FNDC - H
checkpoint | Compaction - Reinstate Pavement Layers
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage One Specification
label | ACTIVITY/TASK - Compaction of trenched pavement as per FNDC Engineering Standards Sheet 31.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - On completion of compacted pavement layers.
label | ACCEPTANCE CRITERIA - Acceptance by Enginner's Representative. Compaction records. Photos.
label | UCCL - H
label | FNDC - H
checkpoint | Road Re-Surfacing
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage One Specification
label | ACTIVITY/TASK - Pre-seal inspection.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to final road resurfacing.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Representative. Supplier documentation. Photos.
label | UCCL - H
label | FNDC - H
checkpoint | Kerb and Channel/Footpaths
label | SPECIFICATION REFERENCE - Kaitaia Wastewater Overflow Reduction Stage One Specification
label | ACTIVITY/TASK - Pre-pour inspection, inspect foundations.
label | INSPECTION BY - FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to placing concrete.
label | ACCEPTANCE CRITERIA - Acceptance by Engineer's Represetative. Photos.
label | UCCL - H
label | FNDC - H