## Excavation
INSPECTION & TEST PLAN
|  | Contract Name: 7063- Whainui Matari- Remediation Works | [6 empty] | Rev: | Originator | Date | Approved | Date
[5 empty] | Hold Point (H) | Verify (V) |  |  | 0 | Cameron | 24/04/2025
Hinge
|  |  | Contractual Obligations |  | Submit (S) | Review (R) |  |  | 1
ITP001- Whainui Matari- Remediation Works |  |  |  |  | Approve(A) | Witness (W)
Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL Signature | Client | UCCL | Client | DATE |  | COMMENTS
Signature
Materials
Hardfill GAP65 | Wainui Road RP4666&4995 - Technical Specification 11.7 | IANZ Test certificates | UCCL, FNDC | 1 test per source submitted 2 weeks prior to MSE Construction | GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA |  |  | H | R
Subbase GAP65 | Wainui Road RP4666&4995 - Technical Specification 11.7 | IANZ Test certificates | UCCL, FNDC | 1 test per source submitted 2 weeks prior to MSE Construction | GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA |  |  | H | R
Basecourse TNZ40 | NZTA M/4 | IANZ Test certificates | UCCL, FNDC | 1 test per source submitted 2 weeks prior to MSE Construction | TNZ40 shall comply with NZTA M/4 items 3.3 and 4.2 |  |  | H | R
F2 Drainage material | Wainui Road RP4666&4995 - Technical Specification 12.4 | IANZ Test certificates | UCCL, FNDC | 1 test per source submitted 2 weeks prior to MSE Construction | Aggregate must comply with NZTA F/2 with the exception that 5% of material by weight may pass the 75 um test seive. |  |  | H | R
Geogrid | Wainui Road RP4666&4995 - Technical Specification 11.4 | Manufacturers certificates, Delivery Dockets | UCCL, FNDC | Prior to placement of geogrid | Geogrid shall be Specification as shown on Drawing RDC03 |  |  | H | R
Subsoil | Wainui Road RP4666&4995 - Technical Specification 13.4 | Manufacturers certificates, Delivery Dockets | UCCL, FNDC | Prior to placement of subsoil | Subsoil drains shall be NZTA F/2 compliant. No filter sock is to be used. |  |  | H | R
Pre Construction Site works
Temporary Works Design | Drawing | Temporary works drawings | UCCL, FNDC | Prior to Excavation | Temporary works design shall be completed prior to excavation for the retaining of the cut face. |  |  | V | Su
Excavation and installation
Subgrade | Wainui Road RP4666&4995 - DWG - SPEC-01 - Subgrade | QF 021 | UCCL, FNDC |  | Subgrade is to be cut ti stiff/medium dense natural materials. |  |  | H | H
Subsoil | Wainui Road RP4666&4995 - NZTA F2 | Photographs, asbuilts | UCCL, FNDC | Prior to Backfill | Subsoil shall be placed at the line, grade and level shown on the drawings. F2 drainage material shall be installed as shown on the drawings. |  |  | V | W
Subbase GAP65 | Wainui Road RP4666&4995 - DWG - SPEC-01 & NZTA B/02 | QF 046 | UCCL, FNDC | 1 Set per 0.2m lift | Hardfill shall be placed and compacted in layers no greater than 200mm. Hardfill shall be tested at a rate of 1 set per 0.3m lift and 15m linear and shall meet a 95% of the MDD average with no tests less than 92% of the MDD |  |  | V | V, W
Geogrid | Wainui Road RP4666&4995 - DWG RDC03 | Photographs, asbuilts | UCCL, FNDC | Prior to Backfill | Geogrid shall be placed in a continuous strip with no joints in the strength direction, all other joints require a bodkin connection. Geogrid shall be tensioned as backfilling occurs |  |  | V | W
Basecourse | Wainui Road RP4666&4995 - Technical Specification TNZ M/4 | QF 046 | UCCL, FNDC | 1 Set per lift Pre Seal Engineer Inspection | 95% of the MDD average with no tests less than 92% of the |  |  | V | V, W
MDD
Post Construction
As builts and Redline Markup | CO14.7 | Asbuilt file | UCCL, FNDC | Following completion of construction | As built drawings, redline markups and RAMM sheets |  |  | S | A

## Retaining Wall
INSPECTION & TEST PLAN
|  | Contract Name: 7063- Whainui Matari- Remediation Works | [8 empty] | Rev: | Originator | Date | Approved | Date
|  | Retaining Wall |  |  | Hold Point (H) | Verify (V) |  |  |  |  | 0 | Cameron Hinge | 2025-05-21
ITP001- Whainui Matari- Remediation Works |  |  |  |  | Submit (S) | Review (R) |  |  |  |  | 1
[5 empty] | Approve(A) | Witness (W)
Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL Signature | Client Signature | SBC Signature | UCCL | Client | SBC | DATE | COMMENTS
Piling Works
Reinforcing Cage - Procurement | DWG No. SPEC-01. | Detail sheets. Mill certificates. Engineers inspection. | UCCL, HGK, HW | Prior delivery to site | Engineers Approval |  |  |  | R, V, S | R, V, A | S
Concrete - Procurement | DWG No. SPEC 01. DWG No. SPEC 02. DWG No. SPEC 03. | Concrete mix design | UCCL, HGK, HW | Following Award | Engineers Approval |  |  |  | R, V, S | R, A | S
Retaining Wall Location | DWG No. SPEC 02. ROP-03 | Engineers inspection. | UCCL, HGK, HW | Prior delivery to site | Engineers Approval |  |  |  | R, S | V, A | S, H
Pile Drill Records - Ground conditions/Drilled excavation | DWG No. SPEC 02. | Drill records - Final excavation depth to road level. - Depth and nature of groundwater encountered. - Depth of any notable change in piling conditions (ground conditions, colour, or change in material). Engineers inspection | UCCL, HGK, HW | Drill logs - each pile. Engineers inspection - As required | Engineers Approval |  |  |  | R, S | R, A, V | H
Reinforcing Cage - Placement | DRW No. SPEC 02. | Engineers inspection. | UCCL, HGK, HW | Each pile / as required | Engineers Approval |  |  |  | R, S | R, A, V | H
Concrete - Placement | DWG No. SPEC 01. SESOC / NZGS Bored and Driven Pile Construction Specifications. Haigh Workman Technical Specfications. | Engineers inspection. | UCCL, HGK, HW | Each pile / as required | Engineers Approval |  |  |  | W | W | H
Capping Beam |  |  | UCCL, HGK, HW
Reinforcing Cage - Procurement | DWG No. SPEC-01. | Detail sheets. Mill certificates. Engineers inspection. | UCCL, HGK, HW | Following delivery to site | Engineers Approval |  |  |  | R, S | R, A | R, S, H
Concrete - Procurement | DWG No. SPEC 01. DWG No. SPEC 02. DWG No. SPEC 03. | Concrete mix design | UCCL, HGK, HW | Following Award | Engineers Approval |  |  |  | W | R, A | H
Reinforcing - Placement | DRW No. SPEC 02. | Engineers inspection | UCCL, HGK, HW | Prior to Concrete Placement | Engineers Approval |  |  |  | R, S | R, A, V | H