## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP001 - 7063 - Whainui Matari - Remediation Works | itp |  |  |  |  | ITP001 - 7063 - Whainui Matari - Remediation Works Rev 2
section | Materials
checkpoint | Hardfill GAP65
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - Technical Specification 11.7
label | TEST REQUIRED - IANZ Test certificates
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction
label | ACCEPTANCE CRITERIA - GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA
label | UCCL - H
label | FNDC - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Subbase GAP65
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - Technical Specification 11.7
label | TEST REQUIRED - IANZ Test certificates
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction
label | ACCEPTANCE CRITERIA - GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA
label | UCCL - H
label | FNDC - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Basecourse TNZ40
label | SPECIFICATION REFERENCE - NZTA M/4
label | TEST REQUIRED - IANZ Test certificates
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction
label | ACCEPTANCE CRITERIA - TNZ40 shall comply with NZTA M/4 items 3.3 and 4.2
label | UCCL - H
label | FNDC - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | F2 Drainage material
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - Technical Specification 12.4
label | TEST REQUIRED - IANZ Test certificates
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction
label | ACCEPTANCE CRITERIA - Aggregate must comply with NZTA F/2 with the exception that 5% of material by weight may pass the 75 um test seive.
label | UCCL - H
label | FNDC - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Geogrid
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - Technical Specification 11.4
label | TEST REQUIRED - Manufacturers certificates, Delivery Dockets
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to placement of geogrid
label | ACCEPTANCE CRITERIA - Geogrid shall be Specification as shown on Drawing RDC03
label | UCCL - H
label | FNDC - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Subsoil
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - Technical Specification 13.4
label | TEST REQUIRED - Manufacturers certificates, Delivery Dockets
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to placement of subsoil
label | ACCEPTANCE CRITERIA - Subsoil drains shall be NZTA F/2 compliant. No filter sock is to be used.
label | UCCL - H
label | FNDC - R
holdpoint | AUTHORITY HOLDPOINT
section | Pre Construction Site works
checkpoint | Temporary Works Design
label | SPECIFICATION REFERENCE - Drawing
label | TEST REQUIRED - Temporary works drawings
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to Excavation
label | ACCEPTANCE CRITERIA - Temporary works design shall be completed prior to excavation for the retaining of the cut face.
label | UCCL - V
label | FNDC - Su
section | Excavation and installation
checkpoint | Subgrade
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - DWG - SPEC-01 - Subgrade
label | TEST REQUIRED - QF 021
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY -
label | ACCEPTANCE CRITERIA - Subgrade is to be cut ti stiff/medium dense natural materials.
label | UCCL - H
label | FNDC - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Subsoil
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - NZTA F2
label | TEST REQUIRED - Photographs, asbuilts
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to Backfill
label | ACCEPTANCE CRITERIA - Subsoil shall be placed at the line, grade and level shown on the drawings. F2 drainage material shall be installed as shown on the drawings.
label | UCCL - V
label | FNDC - W
checkpoint | Subbase GAP65
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - DWG - SPEC-01 & NZTA B/02
label | TEST REQUIRED - QF 046
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - 1 Set per 0.2m lift
label | ACCEPTANCE CRITERIA - Hardfill shall be placed and compacted in layers no greater than 200mm. Hardfill shall be tested at a rate of 1 set per 0.3m lift and 15m linear and shall meet a 95% of the MDD average with no tests less than 92% of the MDD
label | UCCL - V
label | FNDC - V, W
checkpoint | Geogrid
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - DWG RDC03
label | TEST REQUIRED - Photographs, asbuilts
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - Prior to Backfill
label | ACCEPTANCE CRITERIA - Geogrid shall be placed in a continuous strip with no joints in the strength direction, all other joints require a bodkin connection. Geogrid shall be tensioned as backfilling occurs
label | UCCL - V
label | FNDC - W
checkpoint | Basecourse
label | SPECIFICATION REFERENCE - Wainui Road RP4666&4995 - Technical Specification TNZ M/4
label | TEST REQUIRED - QF 046
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - 1 Set per lift, Pre Seal Engineer Inspection
label | ACCEPTANCE CRITERIA - 95% of the MDD average with no tests less than 92% of the MDD
label | UCCL - V
label | FNDC - V, W
section | Post Construction
checkpoint | As builts and Redline Markup
label | SPECIFICATION REFERENCE - CO14.7
label | TEST REQUIRED - Asbuilt file
label | INSPECTION BY - UCCL, FNDC
label | TASK TIMING OR TASK FREQUENCY - Following completion of construction
label | ACCEPTANCE CRITERIA - As built drawings, redline markups and RAMM sheets
label | UCCL - S
label | FNDC - A