## Sheet1
1 | Permits | H | Obtain Permits | As required | Document Review | Control Checklist - Digging / Excavating (incl. marking out CHAR(AMP) potholing existing services), PTW #1 - Confined Space, PTW #2 - Trench Excavation Inspection, Notify Worksafe NZ if required. Ensure all necessary Permit to Works CHAR(AMP) Controlled Checklists are in place | Permit attached or permit number noted | 1 - Permits | ACTION (Hold, Monitor, Witness) - H | DETAIL - Obtain Permits | FREQUENCY - As required | INSPECTION - Document Review | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out CHAR(AMP) potholing existing services), PTW #1 - Confined Space, PTW #2 - Trench Excavation Inspection, Notify Worksafe NZ if required. Ensure all necessary Permit to Works CHAR(AMP) Controlled Checklists are in place | RECORDS - Permit attached or permit number noted | 1 - Permits
2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | IFC Drawings | Check Drawing Register | 2 - Design | ACTION (Hold, Monitor, Witness) - H | DETAIL - Ensure that Design is approved and Drawings are of the latest revision | FREQUENCY - Prior to commencement | INSPECTION - Document Review | CONFORMANCE CRITERIA - IFC Drawings | RECORDS - Check Drawing Register | ACTION (Hold, Monitor, Witness) - H
3 | Survey Setout | H | Set out utiliy service alignment, and depths per construction drawings | Prior to commencement | Survey | Survey is correct and consistent with plans | Photo | 3 - Survey Setout | ACTION (Hold, Monitor, Witness) - H | DETAIL - Set out utiliy service alignment, and depths per construction drawings | FREQUENCY - Prior to commencement | INSPECTION - Survey | CONFORMANCE CRITERIA - Survey is correct and consistent with plans | RECORDS - Photo | DETAIL - Obtain Permits
5 | Material Compliance (1) | H | PVC ducting shall be of approved material and/or supplied by service provider | Prior to instalment | Document/Visual | Ducts are acceptable to the service providers standards | Delivery Docket/ Service Provider acceptance | 5 - Material Compliance (1) | ACTION (Hold, Monitor, Witness) - H | DETAIL - PVC ducting shall be of approved material and/or supplied by service provider | FREQUENCY - Prior to instalment | INSPECTION - Document/Visual | CONFORMANCE CRITERIA - Ducts are acceptable to the service providers standards | RECORDS - Delivery Docket/ Service Provider acceptance | FREQUENCY - As required
5 | Material Compliance (2) | H | Ensure cables, transformers and ring main units are to (service Providers) specifications | Prior to installation | Document review | As per (Power Providers) specifications | Delivery Dockets | 5 - Material Compliance (2) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Ensure cables, transformers and ring main units are to (service Providers) specifications | FREQUENCY - Prior to installation | INSPECTION - Document review | CONFORMANCE CRITERIA - As per (Power Providers) specifications | RECORDS - Delivery Dockets | INSPECTION - Document Review
5 | Material Compliance (3) | H | Bedding material/backfill shall meet the specifications of the service provider/Specifications | Prior to installation | Document review | As per (Power Providers) specifications, NTLDM | Delivery dockets, Lab Material testing | 5 - Material Compliance (3) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Bedding material/backfill shall meet the specifications of the service provider/Specifications | FREQUENCY - Prior to installation | INSPECTION - Document review | CONFORMANCE CRITERIA - As per (Power Providers) specifications, NTLDM | RECORDS - Delivery dockets, Lab Material testing | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out CHAR(AMP) potholing existing services), PTW #1 - Confined Space, PTW #2 - Trench Excavation Inspection, Notify Worksafe NZ if required. Ensure all necessary Permit to Works CHAR(AMP) Controlled Checklists are in place
6 | Trenching CHAR(AMP) Service Installation (1) | W | Inspect trench profile and ensure it is correct to lines and levels set out by survey | Daily | Visual | Depth and line is correct as per for construction drawings | FHIMS-CS-4010 | 6 - Trenching CHAR(AMP) Service Installation (1) | ACTION (Hold, Monitor, Witness) - W | DETAIL - Inspect trench profile and ensure it is correct to lines and levels set out by survey | FREQUENCY - Daily | INSPECTION - Visual | CONFORMANCE CRITERIA - Depth and line is correct as per for construction drawings | RECORDS - FHIMS-CS-4010 | RECORDS - Permit attached or permit number noted
6 | Trenching CHAR(AMP) Service Installation (2) | W | 100mm thick bedding to be placed and compacted and cable laid (by other) | Prior to backfilling | Visual | >100mm of clean sand bedding | FHIMS-CS-4010 | 6 - Trenching CHAR(AMP) Service Installation (2) | ACTION (Hold, Monitor, Witness) - W | DETAIL - 100mm thick bedding to be placed and compacted and cable laid (by other) | FREQUENCY - Prior to backfilling | INSPECTION - Visual | CONFORMANCE CRITERIA - >100mm of clean sand bedding | RECORDS - FHIMS-CS-4010 | 2 - Design
6 | Trenching CHAR(AMP) Service Installation (3) | W | As built survey at intervals of no more than 20m and at each change in direction | Prior to backfilling | Survey | As-built points spacing to be less than 20m at all times | As-Builts | 6 - Trenching CHAR(AMP) Service Installation (3) | ACTION (Hold, Monitor, Witness) - W | DETAIL - As built survey at intervals of no more than 20m and at each change in direction | FREQUENCY - Prior to backfilling | INSPECTION - Survey | CONFORMANCE CRITERIA - As-built points spacing to be less than 20m at all times | RECORDS - As-Builts | ACTION (Hold, Monitor, Witness) - H
6 | Trenching CHAR(AMP) Service Installation (4) | W | If required, Mag slab to be installed 300mm above the cable | Prior to backfilling | Visual | Mag slab to be laid on top of clean sand layer | FHIMS-CS-4010 | 6 - Trenching CHAR(AMP) Service Installation (4) | ACTION (Hold, Monitor, Witness) - W | DETAIL - If required, Mag slab to be installed 300mm above the cable | FREQUENCY - Prior to backfilling | INSPECTION - Visual | CONFORMANCE CRITERIA - Mag slab to be laid on top of clean sand layer | RECORDS - FHIMS-CS-4010 | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
6 | Trenching CHAR(AMP) Service Installation (5) | W | Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet (Power Providers) specification. | Every 300mm lift | Visual | CHAR(LESS)Subbase Layer - Clegg CIV >25 for engineered fill. In berms, Photo record. Subbase Layer - 95% MDD under carriageway for engineered fill. In berms, Photo record Basecourse Layer - 98% MDD for engineered fill. In berms, Photo record | Lab Test results, Clegg Hammer Checksheet | 6 - Trenching CHAR(AMP) Service Installation (5) | ACTION (Hold, Monitor, Witness) - W | DETAIL - Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet (Power Providers) specification. | FREQUENCY - Every 300mm lift | INSPECTION - Visual | CONFORMANCE CRITERIA - CHAR(LESS)Subbase Layer - Clegg CIV >25 for engineered fill. In berms, Photo record. Subbase Layer - 95% MDD under carriageway for engineered fill. In berms, Photo record Basecourse Layer - 98% MDD for engineered fill. In berms, Photo record | RECORDS - Lab Test results, Clegg Hammer Checksheet | FREQUENCY - Prior to commencement
7 | Directional Drilling (1) | W | PE Pipe installed by drilling to survey setout, draw wire/draw rope installed and cable pulled through pipe | Daily | Visual | Line and depth consistent with for construction drawings | Survey receipt | 7 - Directional Drilling (1) | ACTION (Hold, Monitor, Witness) - W | DETAIL - PE Pipe installed by drilling to survey setout, draw wire/draw rope installed and cable pulled through pipe | FREQUENCY - Daily | INSPECTION - Visual | CONFORMANCE CRITERIA - Line and depth consistent with for construction drawings | RECORDS - Survey receipt | INSPECTION - Document Review
7 | Directional Drilling (2) | W | As built survey of the PE pipe installed including depth using depths marked by drilling contractors | After duct has been installed | Survey | As-built points spacing to be less than 20m at all times | As-Builts | 7 - Directional Drilling (2) | ACTION (Hold, Monitor, Witness) - W | DETAIL - As built survey of the PE pipe installed including depth using depths marked by drilling contractors | FREQUENCY - After duct has been installed | INSPECTION - Survey | CONFORMANCE CRITERIA - As-built points spacing to be less than 20m at all times | RECORDS - As-Builts | CONFORMANCE CRITERIA - IFC Drawings
7 | Directional Drilling (3) | W | Backfill connection pits, Sand placed to bed cabling. Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet power providers specification. | As required by specification | Visual | CHAR(LESS)Subbase Layer - Clegg CIV >25 for engineered fill. In berms, Photo record. Subbase Layer - 95% MDD under carriageway for engineered fill. In berms, Photo record Basecourse Layer - 98% MDD for engineered fill. In berms, Photo record | Lab Test results,Photo | 7 - Directional Drilling (3) | ACTION (Hold, Monitor, Witness) - W | DETAIL - Backfill connection pits, Sand placed to bed cabling. Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet power providers specification. | FREQUENCY - As required by specification | INSPECTION - Visual | CONFORMANCE CRITERIA - CHAR(LESS)Subbase Layer - Clegg CIV >25 for engineered fill. In berms, Photo record. Subbase Layer - 95% MDD under carriageway for engineered fill. In berms, Photo record Basecourse Layer - 98% MDD for engineered fill. In berms, Photo record | RECORDS - Lab Test results,Photo | RECORDS - Check Drawing Register
8 | Feature installation (1) | W | Feature such as poles, transformers, distribution pillars installed as per IFC drawings | Daily checks | Visual | Location of feature consistent with for construction drawings | Survey receipt | 8 - Feature installation (1) | ACTION (Hold, Monitor, Witness) - W | DETAIL - Feature such as poles, transformers, distribution pillars installed as per IFC drawings | FREQUENCY - Daily checks | INSPECTION - Visual | CONFORMANCE CRITERIA - Location of feature consistent with for construction drawings | RECORDS - Survey receipt | 3 - Survey Setout
8 | Feature installation (2) | W | Install overhead lines to the locations shown on the drawings | Daily checks | Visual | Consistent with for construction drawings | Certificate of acceptance | 8 - Feature installation (2) | ACTION (Hold, Monitor, Witness) - W | DETAIL - Install overhead lines to the locations shown on the drawings | FREQUENCY - Daily checks | INSPECTION - Visual | CONFORMANCE CRITERIA - Consistent with for construction drawings | RECORDS - Certificate of acceptance | ACTION (Hold, Monitor, Witness) - H
9 | Connection | W | Complete all jointing and carry out testing | After instalment of Cable/Ducts | Visual | Commissioning tests all pass | Confirmation Note | 9 - Connection | ACTION (Hold, Monitor, Witness) - W | DETAIL - Complete all jointing and carry out testing | FREQUENCY - After instalment of Cable/Ducts | INSPECTION - Visual | CONFORMANCE CRITERIA - Commissioning tests all pass | RECORDS - Confirmation Note | DETAIL - Set out utiliy service alignment, and depths per construction drawings
10 | Service handover | W | Service accepted by the service provider | Completion of works | Document | Service provider approval | Certificate of acceptance | 10 - Service handover | ACTION (Hold, Monitor, Witness) - W | DETAIL - Service accepted by the service provider | FREQUENCY - Completion of works | INSPECTION - Document | CONFORMANCE CRITERIA - Service provider approval | RECORDS - Certificate of acceptance | FREQUENCY - Prior to commencement
11 | Abandonment (1) | W | Once the existing power line is taken out of service it shall be capped and sealed in the locations on the IFC drawings | Completion of works | Visual | Consistent with for construction drawings | As-built drawings | 11 - Abandonment (1) | ACTION (Hold, Monitor, Witness) - W | DETAIL - Once the existing power line is taken out of service it shall be capped and sealed in the locations on the IFC drawings | FREQUENCY - Completion of works | INSPECTION - Visual | CONFORMANCE CRITERIA - Consistent with for construction drawings | RECORDS - As-built drawings | INSPECTION - Survey
11 | Abandonment (2) | W | Remove all other redundant items such as redundant poles, pillar boxes, overhead lines etc. | Completion of works | Visual | Site clear of redundant items | As-built drawings | 11 - Abandonment (2) | ACTION (Hold, Monitor, Witness) - W | DETAIL - Remove all other redundant items such as redundant poles, pillar boxes, overhead lines etc. | FREQUENCY - Completion of works | INSPECTION - Visual | CONFORMANCE CRITERIA - Site clear of redundant items | RECORDS - As-built drawings | CONFORMANCE CRITERIA - Survey is correct and consistent with plans
12 | As-builts | H | Updated drawings to be submitted with As-built line and levels recorded | At the completion of the Lot of work | Drawings | Council Water Main Specification - NTLDM, service provider secification | Asbuilt Drawing | 12 - As-builts | ACTION (Hold, Monitor, Witness) - H | DETAIL - Updated drawings to be submitted with As-built line and levels recorded | FREQUENCY - At the completion of the Lot of work | INSPECTION - Drawings | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, service provider secification | RECORDS - Asbuilt Drawing | RECORDS - Photo
5 - Material Compliance (1)
ACTION (Hold, Monitor, Witness) - H
DETAIL - PVC ducting shall be of approved material and/or supplied by service provider
FREQUENCY - Prior to instalment
INSPECTION - Document/Visual
CONFORMANCE CRITERIA - Ducts are acceptable to the service providers standards
RECORDS - Delivery Docket/ Service Provider acceptance
5 - Material Compliance (2)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Ensure cables, transformers and ring main units are to (service Providers) specifications
FREQUENCY - Prior to installation
INSPECTION - Document review
CONFORMANCE CRITERIA - As per (Power Providers) specifications
RECORDS - Delivery Dockets
5 - Material Compliance (3)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Bedding material/backfill shall meet the specifications of the service provider/Specifications
FREQUENCY - Prior to installation
INSPECTION - Document review
CONFORMANCE CRITERIA - As per (Power Providers) specifications, NTLDM
RECORDS - Delivery dockets, Lab Material testing
6 - Trenching CHAR(AMP) Service Installation (1)
ACTION (Hold, Monitor, Witness) - W
DETAIL - Inspect trench profile and ensure it is correct to lines and levels set out by survey
FREQUENCY - Daily
INSPECTION - Visual
CONFORMANCE CRITERIA - Depth and line is correct as per for construction drawings
RECORDS - FHIMS-CS-4010
6 - Trenching CHAR(AMP) Service Installation (2)
ACTION (Hold, Monitor, Witness) - W
DETAIL - 100mm thick bedding to be placed and compacted and cable laid (by other)
FREQUENCY - Prior to backfilling
INSPECTION - Visual
CONFORMANCE CRITERIA - >100mm of clean sand bedding
RECORDS - FHIMS-CS-4010
6 - Trenching CHAR(AMP) Service Installation (3)
ACTION (Hold, Monitor, Witness) - W
DETAIL - As built survey at intervals of no more than 20m and at each change in direction
FREQUENCY - Prior to backfilling
INSPECTION - Survey
CONFORMANCE CRITERIA - As-built points spacing to be less than 20m at all times
RECORDS - As-Builts
6 - Trenching CHAR(AMP) Service Installation (4)
ACTION (Hold, Monitor, Witness) - W
DETAIL - If required, Mag slab to be installed 300mm above the cable
FREQUENCY - Prior to backfilling
INSPECTION - Visual
CONFORMANCE CRITERIA - Mag slab to be laid on top of clean sand layer
RECORDS - FHIMS-CS-4010
6 - Trenching CHAR(AMP) Service Installation (5)
ACTION (Hold, Monitor, Witness) - W
DETAIL - Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet (Power Providers) specification.
FREQUENCY - Every 300mm lift
INSPECTION - Visual
CONFORMANCE CRITERIA - CHAR(LESS)Subbase Layer - Clegg CIV >25 for engineered fill. In berms, Photo record. Subbase Layer - 95% MDD under carriageway for engineered fill. In berms, Photo record Basecourse Layer - 98% MDD for engineered fill. In berms, Photo record
RECORDS - Lab Test results, Clegg Hammer Checksheet
7 - Directional Drilling (1)
ACTION (Hold, Monitor, Witness) - W
DETAIL - PE Pipe installed by drilling to survey setout, draw wire/draw rope installed and cable pulled through pipe
FREQUENCY - Daily
INSPECTION - Visual
CONFORMANCE CRITERIA - Line and depth consistent with for construction drawings
RECORDS - Survey receipt
7 - Directional Drilling (2)
ACTION (Hold, Monitor, Witness) - W
DETAIL - As built survey of the PE pipe installed including depth using depths marked by drilling contractors
FREQUENCY - After duct has been installed
INSPECTION - Survey
CONFORMANCE CRITERIA - As-built points spacing to be less than 20m at all times
RECORDS - As-Builts
7 - Directional Drilling (3)
ACTION (Hold, Monitor, Witness) - W
DETAIL - Backfill connection pits, Sand placed to bed cabling. Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet power providers specification.
FREQUENCY - As required by specification
INSPECTION - Visual
CONFORMANCE CRITERIA - CHAR(LESS)Subbase Layer - Clegg CIV >25 for engineered fill. In berms, Photo record. Subbase Layer - 95% MDD under carriageway for engineered fill. In berms, Photo record Basecourse Layer - 98% MDD for engineered fill. In berms, Photo record
RECORDS - Lab Test results,Photo
8 - Feature installation (1)
ACTION (Hold, Monitor, Witness) - W
DETAIL - Feature such as poles, transformers, distribution pillars installed as per IFC drawings
FREQUENCY - Daily checks
INSPECTION - Visual
CONFORMANCE CRITERIA - Location of feature consistent with for construction drawings
RECORDS - Survey receipt
8 - Feature installation (2)
ACTION (Hold, Monitor, Witness) - W
DETAIL - Install overhead lines to the locations shown on the drawings
FREQUENCY - Daily checks
INSPECTION - Visual
CONFORMANCE CRITERIA - Consistent with for construction drawings
RECORDS - Certificate of acceptance
9 - Connection
ACTION (Hold, Monitor, Witness) - W
DETAIL - Complete all jointing and carry out testing
FREQUENCY - After instalment of Cable/Ducts
INSPECTION - Visual
CONFORMANCE CRITERIA - Commissioning tests all pass
RECORDS - Confirmation Note
10 - Service handover
ACTION (Hold, Monitor, Witness) - W
DETAIL - Service accepted by the service provider
FREQUENCY - Completion of works
INSPECTION - Document
CONFORMANCE CRITERIA - Service provider approval
RECORDS - Certificate of acceptance
11 - Abandonment (1)
ACTION (Hold, Monitor, Witness) - W
DETAIL - Once the existing power line is taken out of service it shall be capped and sealed in the locations on the IFC drawings
FREQUENCY - Completion of works
INSPECTION - Visual
CONFORMANCE CRITERIA - Consistent with for construction drawings
RECORDS - As-built drawings
11 - Abandonment (2)
ACTION (Hold, Monitor, Witness) - W
DETAIL - Remove all other redundant items such as redundant poles, pillar boxes, overhead lines etc.
FREQUENCY - Completion of works
INSPECTION - Visual
CONFORMANCE CRITERIA - Site clear of redundant items
RECORDS - As-built drawings
12 - As-builts
ACTION (Hold, Monitor, Witness) - H
DETAIL - Updated drawings to be submitted with As-built line and levels recorded
FREQUENCY - At the completion of the Lot of work
INSPECTION - Drawings
CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, service provider secification
RECORDS - Asbuilt Drawing