## Sheet1
Hardfill GAP65 | Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 11.7 | IANZ Test certificates | UCCL, FNDC | 1 test per source submitted 2 weeks prior to MSE Construction | GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA | H | R | Hardfill GAP65 | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 11.7 | TEST REQUIRED - IANZ Test certificates | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction | ACCEPTANCE CRITERIA - GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA | UCCL - H | FNDC - R | Hardfill GAP65
Subbase GAP65 | Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 11.7 | IANZ Test certificates | UCCL, FNDC | 1 test per source submitted 2 weeks prior to MSE Construction | GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA | H | R | Subbase GAP65 | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 11.7 | TEST REQUIRED - IANZ Test certificates | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction | ACCEPTANCE CRITERIA - GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA | UCCL - H | FNDC - R | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 11.7
Basecourse TNZ40 | NZTA M/4 | IANZ Test certificates | UCCL, FNDC | 1 test per source submitted 2 weeks prior to MSE Construction | TNZ40 shall comply with NZTA M/4 items 3.3 and 4.2 | H | R | Basecourse TNZ40 | SPECIFICATION REFERENCE - NZTA M/4 | TEST REQUIRED - IANZ Test certificates | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction | ACCEPTANCE CRITERIA - TNZ40 shall comply with NZTA M/4 items 3.3 and 4.2 | UCCL - H | FNDC - R | TEST REQUIRED - IANZ Test certificates
F2 Drainage material | Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 12.4 | IANZ Test certificates | UCCL, FNDC | 1 test per source submitted 2 weeks prior to MSE Construction | Aggregate must comply with NZTA F/2 with the exception that 5% of material by weight may pass the 75 um test seive. | H | R | F2 Drainage material | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 12.4 | TEST REQUIRED - IANZ Test certificates | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction | ACCEPTANCE CRITERIA - Aggregate must comply with NZTA F/2 with the exception that 5% of material by weight may pass the 75 um test seive. | UCCL - H | FNDC - R | INSPECTION BY - UCCL, FNDC
Geogrid | Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 11.4 | Manufacturers certificates, Delivery Dockets | UCCL, FNDC | Prior to placement of geogrid | Geogrid shall be Specification as shown on Drawing RDC03 | H | R | Geogrid | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 11.4 | TEST REQUIRED - Manufacturers certificates, Delivery Dockets | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - Prior to placement of geogrid | ACCEPTANCE CRITERIA - Geogrid shall be Specification as shown on Drawing RDC03 | UCCL - H | FNDC - R | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction
Subsoil | Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 13.4 | Manufacturers certificates, Delivery Dockets | UCCL, FNDC | Prior to placement of subsoil | Subsoil drains shall be NZTA F/2 compliant. No filter sock is to be used. | H | R | Subsoil | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 13.4 | TEST REQUIRED - Manufacturers certificates, Delivery Dockets | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - Prior to placement of subsoil | ACCEPTANCE CRITERIA - Subsoil drains shall be NZTA F/2 compliant. No filter sock is to be used. | UCCL - H | FNDC - R | ACCEPTANCE CRITERIA - GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA
Temporary Works Design | Drawing | Temporary works drawings | UCCL, FNDC | Prior to Excavation | Temporary works design shall be completed prior to excavation for the retaining of the cut face. | V | Su | Temporary Works Design | SPECIFICATION REFERENCE - Drawing | TEST REQUIRED - Temporary works drawings | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - Prior to Excavation | ACCEPTANCE CRITERIA - Temporary works design shall be completed prior to excavation for the retaining of the cut face. | UCCL - V | FNDC - Su | UCCL - H
Subgrade | Wainui Road RP4666CHAR(AMP)4995 - DWG - SPEC-01 - Subgrade | QF 021 | UCCL, FNDC |  | Subgrade is to be cut ti stiff/medium dense natural materials. | H | H | Subgrade | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - DWG - SPEC-01 - Subgrade | TEST REQUIRED - QF 021 | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - | ACCEPTANCE CRITERIA - Subgrade is to be cut ti stiff/medium dense natural materials. | UCCL - H | FNDC - H | FNDC - R
Subsoil | Wainui Road RP4666CHAR(AMP)4995 - NZTA F2 | Photographs, asbuilts | UCCL, FNDC | Prior to Backfill | Subsoil shall be placed at the line, grade and level shown on the drawings. F2 drainage material shall be installed as shown on the drawings. | V | W | Subsoil | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - NZTA F2 | TEST REQUIRED - Photographs, asbuilts | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - Prior to Backfill | ACCEPTANCE CRITERIA - Subsoil shall be placed at the line, grade and level shown on the drawings. F2 drainage material shall be installed as shown on the drawings. | UCCL - V | FNDC - W | Subbase GAP65
Subbase GAP65 | Wainui Road RP4666CHAR(AMP)4995 - DWG - SPEC-01 CHAR(AMP) NZTA B/02 | QF 046 | UCCL, FNDC | 1 Set per 0.2m lift | Hardfill shall be placed and compacted in layers no greater than 200mm. Hardfill shall be tested at a rate of 1 set per 0.3m lift and 15m linear and shall meet a 95% of the MDD average with no tests less than 92% of the MDD | V | V, W | Subbase GAP65 | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - DWG - SPEC-01 CHAR(AMP) NZTA B/02 | TEST REQUIRED - QF 046 | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - 1 Set per 0.2m lift | ACCEPTANCE CRITERIA - Hardfill shall be placed and compacted in layers no greater than 200mm. Hardfill shall be tested at a rate of 1 set per 0.3m lift and 15m linear and shall meet a 95% of the MDD average with no tests less than 92% of the MDD | UCCL - V | FNDC - V, W | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 11.7
Geogrid | Wainui Road RP4666CHAR(AMP)4995 - DWG RDC03 | Photographs, asbuilts | UCCL, FNDC | Prior to Backfill | Geogrid shall be placed in a continuous strip with no joints in the strength direction, all other joints require a bodkin connection. Geogrid shall be tensioned as backfilling occurs | V | W | Geogrid | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - DWG RDC03 | TEST REQUIRED - Photographs, asbuilts | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - Prior to Backfill | ACCEPTANCE CRITERIA - Geogrid shall be placed in a continuous strip with no joints in the strength direction, all other joints require a bodkin connection. Geogrid shall be tensioned as backfilling occurs | UCCL - V | FNDC - W | TEST REQUIRED - IANZ Test certificates
Basecourse | Wainui Road RP4666CHAR(AMP)4995 - Technical Specification TNZ M/4 | QF 046 | UCCL, FNDC | 1 Set per lift Pre Seal Engineer Inspection | 95% of the MDD average with no tests less than 92% of the MDD | V | V, W | Basecourse | SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification TNZ M/4 | TEST REQUIRED - QF 046 | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - 1 Set per lift Pre Seal Engineer Inspection | ACCEPTANCE CRITERIA - 95% of the MDD average with no tests less than 92% of the MDD | UCCL - V | FNDC - V, W | INSPECTION BY - UCCL, FNDC
As builts and Redline Markup | CO14.7 | Asbuilt file | UCCL, FNDC | Following completion of construction | As built drawings, redline markups and RAMM sheets | S | A | As builts and Redline Markup | SPECIFICATION REFERENCE - CO14.7 | TEST REQUIRED - Asbuilt file | INSPECTION BY - UCCL, FNDC | TASK TIMING OR TASK FREQUENCY - Following completion of construction | ACCEPTANCE CRITERIA - As built drawings, redline markups and RAMM sheets | UCCL - S | FNDC - A | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction
ACCEPTANCE CRITERIA - GAP65 shall meet the grading from Table 14.27, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA
UCCL - H
FNDC - R
Basecourse TNZ40
SPECIFICATION REFERENCE - NZTA M/4
TEST REQUIRED - IANZ Test certificates
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction
ACCEPTANCE CRITERIA - TNZ40 shall comply with NZTA M/4 items 3.3 and 4.2
UCCL - H
FNDC - R
F2 Drainage material
SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 12.4
TEST REQUIRED - IANZ Test certificates
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction
ACCEPTANCE CRITERIA - Aggregate must comply with NZTA F/2 with the exception that 5% of material by weight may pass the 75 um test seive.
UCCL - H
FNDC - R
Geogrid
SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 11.4
TEST REQUIRED - Manufacturers certificates, Delivery Dockets
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - Prior to placement of geogrid
ACCEPTANCE CRITERIA - Geogrid shall be Specification as shown on Drawing RDC03
UCCL - H
FNDC - R
Subsoil
SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification 13.4
TEST REQUIRED - Manufacturers certificates, Delivery Dockets
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - Prior to placement of subsoil
ACCEPTANCE CRITERIA - Subsoil drains shall be NZTA F/2 compliant. No filter sock is to be used.
UCCL - H
FNDC - R
Temporary Works Design
SPECIFICATION REFERENCE - Drawing
TEST REQUIRED - Temporary works drawings
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - Prior to Excavation
ACCEPTANCE CRITERIA - Temporary works design shall be completed prior to excavation for the retaining of the cut face.
UCCL - V
FNDC - Su
Subgrade
SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - DWG - SPEC-01 - Subgrade
TEST REQUIRED - QF 021
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY -
ACCEPTANCE CRITERIA - Subgrade is to be cut ti stiff/medium dense natural materials.
UCCL - H
FNDC - H
Subsoil
SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - NZTA F2
TEST REQUIRED - Photographs, asbuilts
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - Prior to Backfill
ACCEPTANCE CRITERIA - Subsoil shall be placed at the line, grade and level shown on the drawings. F2 drainage material shall be installed as shown on the drawings.
UCCL - V
FNDC - W
Subbase GAP65
SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - DWG - SPEC-01 CHAR(AMP) NZTA B/02
TEST REQUIRED - QF 046
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - 1 Set per 0.2m lift
ACCEPTANCE CRITERIA - Hardfill shall be placed and compacted in layers no greater than 200mm. Hardfill shall be tested at a rate of 1 set per 0.3m lift and 15m linear and shall meet a 95% of the MDD average with no tests less than 92% of the MDD
UCCL - V
FNDC - V, W
Geogrid
SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - DWG RDC03
TEST REQUIRED - Photographs, asbuilts
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - Prior to Backfill
ACCEPTANCE CRITERIA - Geogrid shall be placed in a continuous strip with no joints in the strength direction, all other joints require a bodkin connection. Geogrid shall be tensioned as backfilling occurs
UCCL - V
FNDC - W
Basecourse
SPECIFICATION REFERENCE - Wainui Road RP4666CHAR(AMP)4995 - Technical Specification TNZ M/4
TEST REQUIRED - QF 046
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - 1 Set per lift Pre Seal Engineer Inspection
ACCEPTANCE CRITERIA - 95% of the MDD average with no tests less than 92% of the MDD
UCCL - V
FNDC - V, W
As builts and Redline Markup
SPECIFICATION REFERENCE - CO14.7
TEST REQUIRED - Asbuilt file
INSPECTION BY - UCCL, FNDC
TASK TIMING OR TASK FREQUENCY - Following completion of construction
ACCEPTANCE CRITERIA - As built drawings, redline markups and RAMM sheets
UCCL - S
FNDC - A