## Checklists
type | name | values
checklist | Anchoring ITP
checkpoint | Attach any relevant photos and documents
text | Row
text | Anchor No
text | Anchor Type
text | Anchor Angle
text | Anchor Borehole Dia
text | Anchor Size
text | No of Strands
text | Entry Level (RL)
text | Bond Length
text | Free Length
text | Total Drill Length
text | Drill Date
text | Grout Date
text | Grout Type
text | Stress Date
checklist | Anchoring Works
section | Prior to Start
checkpoint | Safety Documentation in place |  | Remove
checkpoint | Drawings
Tick box | Drawing name |  | Add under "drawings"
Tick box | Drawing number |  | Add under "drawings"
Tick box | Revision number |  | Add under "drawings"
checkpoint | Site Establishment (Drill 3. Rig, Equipment, Materials) |  | Remove
checkpoint | Anchor Supply
Tick box | Mill certificate |  | Add under "Anchor Supply"
Tick box | Test Certificate |  | Add under "Anchor Supply"
Tick box | Batch number Noted |  | Add under "Anchor Supply"
checkpoint | Locate/Install washout area and any other required environmental control measures |  | Remove
checkpoint | Anchor Survey Set out
Tick box | Anchor points to be marked by surveyor and confrimed with DELTA |  | Add under "Anchor Survey Setout"
Tick box | Surveyor Records |  | Add under "Anchor Survey Setout"
section | Anchor Works
checkpoint | Anchor Strand Centralisers
Tick box | Mill certificate |  | Add under "Anchor Strand Centralisers"
Tick box | Test Certificate |  | Add under "Anchor Strand Centralisers"
Tick box | Batch number Noted |  | Add under "Anchor Strand Centralisers"
checkpoint | Excavation & preparation of Anchor Wall face/batter |  | Add
Tick box | As per drawings & site inspection from DELTA |  | Add under "Excavation & preparation of Anchor Wall face/batter"
checkpoint | Anchor Drilling |  | Add
Tick box | Hole to be drilled to sepcification |  | Add under "Anchor Drilling"
Tick box | On Record as per Drilling and Installation docket |  | Add under "Anchor Drilling"
checkpoint | Grout Equipment
Tick box | Grout pump to be actuated by a piston of screw pump |  | Add under "Grout Equipment"
checkpoint | Grout supply
Tick box | Water & Cement grout mix as per design |  | Add under "Grout supply"
Tick box | TDS, PDS, Batch number |  | Add under "Grout supply"
checkpoint | Grout batching
Tick box | Batch by dry weight measure water by calibrated flow meter, continuous agitating after mixing use recirculation system inject within 30 mins of batching |  | Add under "Grout Batching"
checkpoint | Grout Testing
Tick Box | Field testing of grout for Compressive Strength, Per batch, 3 tests |  | Add under "Grout Testing"
checkpoint | Installation & Grouting of Rock Bolt/Anchors/Soil Nails
Tick box | Place anchor in prepared clean hole, fill hole from the bottom using grout tube allow grout to flow until pure grout comes out top of hole |  | Add under "Installation & Grouting of Rock Bolt/Anchors/Soil Nails"
Tick box | TDS, PDS, batch number, Mill certificates, Test Certificates |  | Add under "Installation & Grouting of Rock Bolt/Anchors/Soil Nails"
checkpoint | Anchor Stressing
Tick box | AS per drawings & specification |  | Add under "Anchor Stressing"
Tick box | Drilling and installation docket for Anchors done on a daily basis |  | Add under "Anchor Stressing"
Tick box | Stressing records captured per AGT records |  | Add under "Anchor Stressing"

## Project Structure
Folder Structure | Checklists
Site QA | Ability to Add

## Sheet3
type | name | values
checklist | Anchoring Works
section | Prior to Start
checkpoint | Safety Documentation in place
checkpoint | Drawings
checkpoint | Site Establishment (Drill 3. Rig, Equipment, Materials)
checkpoint | Anchor Supply
checkpoint | Locate/Install washout area and any other required environmental control measures
checkpoint | Anchor Survey Set out
section | Anchor Works
checkpoint | Anchor Strand Centralisers
checkpoint | Excavation & Preparation of Anchor Wall face / batter
checkpoint | Anchor Drilling
checkpoint | Grout Equipment
checkpoint | Grout supply
checkpoint | Grout batching
checkpoint | Grout Testing
checkpoint | Installation & Grouting of Rock Bolt/Anchors/Soil Nails
checkpoint | Anchor Stressing