## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Anchoring ITP |  |  |  |  | Yes | Anchoring ITP | 15eecff3-804b-4448-b3d3-d1222c6dfb42
checkpoint-status |  |  | checkpoint | Attach any relevant photos and documents
text | 028f0315-74ab-5e73-a1fb-c08d51035f83 |  | textbox | Row
text | 97045238-baad-5c1b-a67d-7422f4a62d10 |  | textbox | Anchor No
text | be690863-9e7d-5333-863e-137118c3d567 |  | textbox | Anchor Type
text | 6768772d-e176-557f-a7e0-a60d95c4e39b |  | textbox | Anchor Angle
text | 60848a84-582c-55b8-a9a9-fce7105aa2b0 |  | textbox | Anchor Borehole Dia
text | ac6991ef-4f44-526f-80a5-5731e4c07f7f |  | textbox | Anchor Size
text | 3f6b5f47-6c3f-526b-9e9a-c7c0602e3896 |  | textbox | No of Strands
text | db577cf1-84d9-5f1e-bbcc-949cf8e6d8de |  | textbox | Entry Level (RL)
text | 73e0f5ed-1488-5690-878d-3dd407cd96fb |  | textbox | Bond Length
text | 40ee1ebd-9d82-5798-b6c3-4eae2112da48 |  | textbox | Free Length
text | a33c20b7-1d7b-5d3d-b7c3-f611e24649c6 |  | textbox | Total Drill Length
text | 3e88ccc5-fa81-5161-8e53-a80c5fd8ad5d |  | textbox | Drill Date
text | 19eefdf4-5cf5-5a09-bb1a-ac475b5c1647 |  | textbox | Grout Date
text | d1f402e8-8203-5f30-bf6c-58aaf31429af |  | textbox | Grout Type
text | 3071cbeb-f427-5cb8-b7b5-099b41c87280 |  | textbox | Stress Date
checklist-sectioned |  |  | checklist | Anchoring Works |  |  |  |  | Yes | Anchoring Works | 27f2a3f9-1a6e-47ea-8911-9e936a68f047
checkpoint-group |  |  | section | Prior to Start
checkpoint-status |  |  | checkpoint | Safety Documentation in place
checkpoint-status |  |  | checkpoint | Drawings
checkpoint-status |  |  | checkpoint | Site Establishment (Drill 3. Rig, Equipment, Materials)
checkpoint-status |  |  | checkpoint | Anchor Supply
checkpoint-status |  |  | checkpoint | Locate/Install washout area and any other required environmental control measures
checkpoint-status |  |  | checkpoint | Anchor Survey Set out
checkpoint-group |  |  | section | Anchor Works
checkpoint-status |  |  | checkpoint | Anchor Strand Centralisers
checkpoint-status |  |  | checkpoint | Excavation & Preparation of Anchor Wall face / batter
checkpoint-status |  |  | checkpoint | Anchor Drilling
checkpoint-status |  |  | checkpoint | Grout Equipment
checkpoint-status |  |  | checkpoint | Grout supply
checkpoint-status |  |  | checkpoint | Grout batching
checkpoint-status |  |  | checkpoint | Grout Testing
checkpoint-status |  |  | checkpoint | Installation & Grouting of Rock Bolt/Anchors/Soil Nails
checkpoint-status |  |  | checkpoint | Anchor Stressing