## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Anchoring Works |  |  |  |  | Yes | Anchoring Works | 27f2a3f9-1a6e-47ea-8911-9e936a68f047
section | Prior to Start
checkpoint | Drawings
bool | Drawing name
bool | Drawing number
bool | Revision number
checkpoint | Anchor Supply
bool | Mill certificate
bool | Test Certificate
bool | Batch number Noted
checkpoint | Anchor Survey Set out
bool | Anchor points to be marked by surveyor and confrimed with DELTA
bool | Surveyor Records
section | Anchor Works
checkpoint | Anchor Strand Centralisers
bool | Mill certificate
bool | Test Certificate
bool | Batch number Noted
checkpoint | Excavation & Preparation of Anchor Wall face / batter
bool | As per drawings & site inspection from DELTA
checkpoint | Anchor Drilling
bool | Hole to be drilled to sepcification
bool | On Record as per Drilling and Installation docket
checkpoint | Grout Equipment
bool | Grout pump to be actuated by a piston of screw pump
checkpoint | Grout supply
bool | Water & Cement grout mix as per design
bool | TDS, PDS, Batch number
checkpoint | Grout batching
bool | Batch by dry weight measure water by calibrated flow meter, continuous agitating after mixing use recirculation system inject within 30 mins of batching
checkpoint | Grout Testing
bool | Field testing of grout for Compressive Strength, Per batch, 3 tests
checkpoint | Installation & Grouting of Rock Bolt/Anchors/Soil Nails
bool | Place anchor in prepared clean hole, fill hole from the bottom using grout tube allow grout to flow until pure grout comes out top of hole
bool | TDS, PDS, batch number, Mill certificates, Test Certificates
checkpoint | Anchor Stressing
bool | AS per drawings & specification
bool | Drilling and installation docket for Anchors done on a daily basis
bool | Stressing records captured per AGT records