## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | SYM-ITP-019 - CLADDING (Rev A) |  |  |  |  | Yes | SYM-ITP-019 - CLADDING (Rev A) | 10300ea7-17ee-4a13-9506-7530027b24c9
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-group |  |  | section | 2.0 Pre-Construction Activities
checkpoint-status |  |  | checkpoint | • Has the structure been surveyed, including any fixing inserts, before commencement?
checkpoint-status |  |  | checkpoint | • Is the structure clear of dirt and blemishes?
checkpoint-group |  |  | section | 3.0 Construction
checkpoint-status |  |  | checkpoint | • Have stone cladding fixings been provided as required, sufficient to support, restrain and resist the structural design loads on each cladding panel, as specified?
button | b03af459-3662-5621-b93d-3ea0c7708830 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | c9550cd2-95b7-5605-8ac6-19f0db62ff98 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Have adhesives been applied where required, as specified?
button | 19ef7d68-85d9-5401-bb2f-5e4c5042c3c6 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 21ee1199-fa43-5be7-981a-f2172aa39e78 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has cladding been installed as described in specification, considering given tolerances?
button | 1277887d-4f02-54d5-a1d0-29cc0d4c4ea6 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | f0020853-b4d3-5e5f-8c1a-a0358fa7e3c3 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 22583509-7d14-5d8b-9d89-49e9cb86b66c |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-013 - Retaining walls and wall footings (Rev A) |  |  |  |  | Yes | SYM-ITP-013 - Retaining walls and wall footings (Rev A) | 12b46283-0377-4db2-ad3a-f5d1077c1d04
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-status |  |  | checkpoint | • Is Mix design approved prior to placement and material properties meet project specification, AS 3600, AS 1379.
text | cc8f77fb-7f3d-5bb3-999f-e019f5299c2e |  | textbox | • Concrete Strength |  |  | MPA
button | 0fe4eca4-d1bb-508c-bc50-17939df73b59 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 1b9b1fe3-74bd-5ca4-9716-95f49c5ff858 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | a81d7320-ed35-5386-b0cf-f78f393769a5 |  | textbox | • Wall/Footing Reference
text | e27872bc-945b-5767-a6f1-8c5220a5b7ea |  | textbox | • Zone
text | 1e75b118-b12e-5dfe-9345-5b6c3db8c21e |  | textbox | • Stage
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
button | 9052007a-7630-506b-8358-0d4d318ae747 |  | button | • Relevant permits have been signed and approved. | PASS,FAIL,N/A
button | 5295f313-f18c-5e72-ade2-1f17a73ceb38 |  | button | • Extents and levels correct to relevant drawings | PASS,FAIL,N/A
button | 598d1473-0efd-58cf-b099-482682c9acc2 |  | button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | PASS,FAIL,N/A
text | 358b2e68-0eb7-50f0-a620-d0b1d86cd611 |  | textbox | • Excavation to a total depth of |  |  | mm
button | a819a9b8-941b-58fa-bedc-fc485613f7eb |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 24dd1b16-d645-52ab-8d12-e8c4f5440a35 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Wall Footings
checkpoint-status |  |  | checkpoint | • Formwork has been installed correctly and sufficiently braced.
button | ba89aa26-0120-5b25-b0cd-3b4bc8c13603 |  | button | • Formwork set out has been done as per latest design drawings and specifications | PASS,FAIL,N/A
button | 105808e6-d5b6-5691-a0fd-c41422fe2fe8 |  | button | • Were Construction joints/Expansion Joints/Isolation Joints Installed | PASS,FAIL,N/A
button | 7b099768-ca25-5cb3-a117-d5d459377b2c |  | button | • Any Backfill/ Underlay Material as per drawings & specifications | PASS,FAIL,N/A
button | a25d615a-65ce-5fac-9e00-751190557009 |  | button | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified | PASS,FAIL,N/A
button | 78a7bcbc-0407-5f66-bd21-bd8abdc3a15f |  | button | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval? | PASS,FAIL,N/A
button | a79d8cdf-826b-52a5-8e54-cbe2358d0ab5 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | b1b37f94-b69c-5bf9-91c1-78652dddda4f |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
button | 4339d7d7-ae45-59ba-b497-0c7a5b195d3c |  | button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | PASS,FAIL,N/A
button | 33cceb58-be36-5841-a10d-7590855dbcf6 |  | button | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars | PASS,FAIL,N/A
button | aa3626ce-9925-5f95-a897-1313422621ba |  | button | • Correct concrete cover and chairs on sides, bottom and top Verified | PASS,FAIL,N/A
button | 9b352076-7a04-541b-86ca-9c6aef83da14 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | df4590ba-a6fb-55b9-860e-7e0b1987ac5c |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 276b005e-fd7a-528d-98e0-30375eb66e75 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has steel reinforcement been placed correctly with adequate cover?
button | 60bce546-4f97-5164-bb1a-5af0df8c93b2 |  | button | • Have tie bars and expansion joints been installed at the correct intervals? | PASS,FAIL,N/A
button | c5ebc635-58be-5f80-981b-0119b72f4e16 |  | button | • Pour area is free of loose debris, oils, water | PASS,FAIL,N/A
button | 65fa9afe-bf32-579e-a911-8c8326de9f82 |  | button | • Have any services located within the slab been installed, surveyed and pinned down | PASS,FAIL,N/A
button | aef72b54-bb76-5caf-9a0f-878c061475d7 |  | button | • Concrete Testing Lab Representative will be available during concrete pour | PASS,FAIL,N/A
button | 1eae6a45-6019-59a8-8f66-54edac3d1587 |  | button | • CYP D&C JV informed of concrete pour date and start time | PASS,FAIL,N/A
button | ef7e336a-d6e2-5cdb-a4fb-f2a37c759719 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | ae3f0531-ea35-5b3b-b074-5fcd8199d28f |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 5cc09fe0-cbbf-56d8-85a2-0a299e54e715 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials.
button | ac87bc92-c518-5619-89a9-28669c07904a |  | button | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects. | PASS,FAIL,N/A
button | 6a4d8484-4ba2-5b63-ba44-7bc58f4e51f7 |  | button | • Has a minimum of one of vibrator used at all times while the concreting is in operation | PASS,FAIL,N/A
button | bc6fb722-eb5a-56f8-b143-1f2884fc57ea |  | button | • Ensure monitoring forms/cast in items during the pour | PASS,FAIL,N/A
button | daf103db-e7b1-55e4-81e9-28ba73a9bc93 |  | button | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy | PASS,FAIL,N/A
button | 82f61e67-75e3-5d24-8d41-d0bee41a039f |  | button | • Concrete Dockets Received, Attach last Docket | PASS,FAIL,N/A
text | 15dd3cd8-1925-55d7-8d92-8be3b6599ca5 |  | textbox | • Pour date
text | 1d2ee7a1-9a07-5a23-a938-280de1f1ebcd |  | textbox | • Total pour Concrete quantity |  |  | M3
button | fdc962ec-e075-5045-9a68-785c1a06d001 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 6e5b33e2-b97c-5e05-82e9-31e732c382a0 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Was Curing agent applies as per project specifications
button | f6b666fc-f088-5d2e-925b-12fabebe99b1 |  | button | • Concrete reached design strength to strip formwork | PASS,FAIL,N/A
button | d8af1e80-64b5-51d6-ac92-c09509e7c35a |  | button | • Any identified defects after striping rectified | PASS,FAIL,N/A
button | 2ca9b8ec-fe56-512d-96e3-2b7dd4dbf27e |  | button | • Attach Subcontractor’s QA | PASS,FAIL,N/A
button | ce371394-8d0c-51f7-9a2d-b21a2f0c4304 |  | button | • Does Backfill material compl;y with Vicroad specs, Project specs and drawings? | PASS,FAIL,N/A
button | 5d28d68d-7a56-5863-a384-6b3f3693f326 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | f45dc812-e81f-592f-95bc-a9e01465f670 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 17d0a988-b2f0-5622-86e1-40f6aefc2a3a |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
button | d3f69738-81f1-51b9-973b-06148b0626f1 |  | button | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | PASS,FAIL,N/A
button | 96505ef7-bf9b-5d3d-af63-64b08db089e0 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | bf7f6597-b5e4-56a2-8c19-fbb425d6fb28 |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Retaining Walls
checkpoint-status |  |  | checkpoint | • Formwork has been installed correctly and sufficiently braced.
button | f43f9b85-af2f-5eaa-b747-b200933d5277 |  | button | • Formwork set out has been done as per latest design drawings and specifications | PASS,FAIL,N/A
button | e1d50749-0b6e-5734-9daf-9eb1a45265e7 |  | button | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed | PASS,FAIL,N/A
button | 31eb4c69-f43d-5add-83c0-1e20267a78a4 |  | button | • Any Backfill/ Underlay Material as per drawings & specifications | PASS,FAIL,N/A
button | dbb7a36e-fd50-56d8-8e97-9b62af534ad0 |  | button | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified | PASS,FAIL,N/A
button | b5ad831c-a8bb-5830-b4f0-6d37511a0fba |  | button | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval? | PASS,FAIL,N/A
button | 7fbaf055-aa9a-5852-8235-2a5cc3bcd3d3 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 020c4e88-72f2-580f-9475-b6149ade66cb |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
button | 14182ac1-60d9-54d6-be9e-f5d9a206caaf |  | button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | PASS,FAIL,N/A
button | bb8a68fa-02f6-5d73-9226-98ce37279fd4 |  | button | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars | PASS,FAIL,N/A
button | 08b06dc1-ca26-5271-abae-18499145da77 |  | button | • Correct concrete cover and chairs on sides, bottom and top Verified | PASS,FAIL,N/A
button | b1565801-5205-526b-a702-3643d7c71e4c |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 634f6485-1f07-5bdc-95f0-a94b834c560f |  | button | WITNESS POINT - Signature by IR | Yes,No
button | a85f1c27-39a6-5ff1-be48-f27b4b619517 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has steel reinforcement been placed correctly with adequate cover?
button | d4e58cbe-c36f-514e-94f9-7da1615eb17c |  | button | • Have tie bars and expansion joints been installed at the correct intervals? | PASS,FAIL,N/A
button | 0cbb05ba-21dc-5cd2-8c3c-dbd939e9a29b |  | button | • Pour area is free of loose debris, oils, water | PASS,FAIL,N/A
button | 32de3e20-e13e-55a1-a66a-3fdc0c42a027 |  | button | • Have any services located within the slab been installed, surveyed and pinned down | PASS,FAIL,N/A
button | 9548cedd-41a5-5f9d-a3a8-dec859705375 |  | button | • Concrete Testing Lab Representative will be available during concrete pour | PASS,FAIL,N/A
button | fd6f2d84-f9d8-566d-974d-3171a395c509 |  | button | • CYP D&C JV informed of concrete pour date and start time | PASS,FAIL,N/A
button | c02b7de0-5f08-5332-b9e8-34a40e4f5fd9 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | bfc8900f-fd33-5aa3-a8df-e5befb2a6b98 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 5661ec24-bc49-5169-9898-df038d0d6aa1 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials.
button | f9eef35c-a979-5720-b2d5-2d7858d767e0 |  | button | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects. | PASS,FAIL,N/A
button | 7db9e215-4034-52fe-a675-3081117e632b |  | button | • Has a minimum of one of vibrator used at all times while the concreting is in operation | PASS,FAIL,N/A
button | 84dc3bcc-d612-5f32-b907-5e373a44b606 |  | button | • Ensure monitoring forms/cast in items during the pour | PASS,FAIL,N/A
button | ff3b8f9f-f769-5d09-998e-c24bc865236c |  | button | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy | PASS,FAIL,N/A
button | 4b2d2186-9ae8-5748-b388-bfab0f55d592 |  | button | • Concrete Dockets Received, Attach last Docket | PASS,FAIL,N/A
text | 5c73d975-5946-505c-8d25-ca98b2c3e451 |  | textbox | • Pour date
text | bb5afb56-dca0-5399-8649-948c374db6b4 |  | textbox | • Total pour Concrete quantity |  |  | M3
button | f4024a9b-854a-5eb8-bbb5-26cd3408ad83 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | f6550a9f-96f1-5105-99db-332fe10a0847 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Was Curing agent applies as per project specifications
button | 9337ced7-0eb0-51a0-a878-2a1ecfabef3e |  | button | • Concrete reached design strength to strip formwork | PASS,FAIL,N/A
button | 57e48ff3-19dc-5c0c-b408-c26f27d8c07f |  | button | • Any identified defects after striping rectified | PASS,FAIL,N/A
button | 0c985eea-158c-564c-8f3a-28255014d096 |  | button | • Attach Subcontractor’s QA | PASS,FAIL,N/A
button | 3083e88f-2c5c-50fd-ad8b-8051e682c546 |  | button | • Does Backfill material compl;y with Vicroad specs, Project specs and drawings? | PASS,FAIL,N/A
button | ded8d8bb-0b7e-5086-803e-f9c653f5b08d |  | button | • Were as Built completed? Attach report if applicable | PASS,FAIL,N/A
button | 07a52864-d970-5131-bd28-1657e0a2f3da |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | d91015a0-9131-52e2-8f09-3b40c9ec7701 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | e6a8e6c5-b137-58cb-bd1e-37fdcab3da1b |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
button | f6810378-0a9d-5e8f-89d2-82470b9a8e90 |  | button | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | PASS,FAIL,N/A
button | a362bc21-e509-589b-88d2-8f6dcc9308c5 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 6a619f7c-130d-549e-abb0-56c9ed4f4c8a |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-018 - Public Lighting (Rev A) |  |  |  |  | Yes | SYM-ITP-018 - Public Lighting (Rev A) | 2e8ff358-3769-4d14-b2c7-67c32b489f1d
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Has the lot been defined and marked up on lot map?
checkpoint-status |  |  | checkpoint | • Has the work area been set out as per IFC drawings?
checkpoint-group |  |  | section | 2.0 Public lighting Installation
checkpoint-status |  |  | checkpoint | • Has the public lighting been constructed in accordance with the IFC Drawings?
button | 94267335-a1c3-5d5f-8e34-46f945cd850c |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | e98f1d24-ad8f-5dac-94d9-57cb0e9372ac |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 2bcb1a82-7e7e-50ea-80ae-e9a4b7963b7a |  | button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has the public lighting passed all commissioning and testing?
button | dd01938d-e357-571a-88d1-f56abb623993 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 537dd96a-8c1b-5407-9702-68fb0732c178 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 6c66575a-2c13-5d38-a25f-d133a7a41e64 |  | button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Powercor inspection & approval provided?
text | b2d9ad1f-e925-5c46-95c8-a26de8aca4d5 |  | textbox | • Date:
label | dba53258-3322-5aff-9806-f6f77342b3fc |  | note | • Signature:
button | 34128da3-3d43-5f47-bde3-2511b7771362 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | d8be0454-db7f-5212-b0b9-15fb3ea43c2f |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 31c97f45-2c53-53f3-bce1-c241f8827217 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 Conformance check
checkpoint-status |  |  | checkpoint | • All Test reports and as builts received and reviewed? Attach Test reports
checkpoint-status |  |  | checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
checklist-sectioned |  |  | checklist | SYM-ITP-002 - Flexible Pavements (Rev A) |  |  |  |  | Yes | SYM-ITP-002 - Flexible Pavements (Rev A) | 37cb3fb8-5043-4d70-b5c2-2267cdf9c775
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Has the work area been set out for line and level?
checkpoint-status |  |  | checkpoint | • Has the previous layer passed acceptance criteria?
button | 5bd03641-c1c3-5a1a-b5b7-93259aaaf003 |  | button | • Approval to proceed? | PASS,FAIL,N/A
button | e004d9c9-5962-5264-b07b-0559decb6330 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 535c832f-44a6-5f02-8725-dd98fa59814c |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Is the correct material being used?
boolean | c9e2937a-65e1-5a66-8424-47d034323e56 |  | tickbox | Class 2
boolean | 12434c25-42e7-5466-ae4a-59d13400f0dc |  | tickbox | Class 3
boolean | 1e2c969f-8885-5f70-9e10-80cb13c0da66 |  | tickbox | CTCR
button | 15bf6b9b-72cd-5d41-b0d7-c58671d42e9f |  | button | • Has the material to be used been approved for use (Material certificates to be provided)? | PASS,FAIL,N/A
button | ef23da6e-3a93-57fe-b6f9-641e4a64bfd8 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 60c602a3-e727-55cc-8cc6-a704f486bed2 |  | button | REVIEW POINT - Signature by IR | Yes,No
button | 942bb58f-e079-560a-8a17-fbacf756cd2c |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • What is the lot size?
text | 41638282-7a02-5338-9163-05fa334be373 |  | textbox | • Lot Size |  |  | M2
label | 96c30c6a-aedb-5911-b8bc-909dcdea4ae2 |  | note | • Maximum lot size = 1 days production or 4000m2
checkpoint-group |  |  | section | 2.0 Pavement Construction
checkpoint-status |  |  | checkpoint | • Is the pavement intended to be Lower Subbase or Upper Subbase?
boolean | a9de76a5-7b4b-58e2-89e0-9d03ee0e02bd |  | tickbox | Lower subbase
boolean | 4eab7ac4-cc1c-5a3e-a268-dbf4be4293c3 |  | tickbox | Subbase
boolean | e4cc232a-0864-5c20-b5e8-0ddc26dde61a |  | tickbox | Base
checkpoint-status |  |  | checkpoint | • Transverse - Offset by not less than 2 m to any underlying pavement layers.
button | e88d499a-5b8e-5731-b3c7-956672e0b69e |  | button | • Longitudinal - Offset by not less than 150 mm to any underlying pavement layers. Located within 300 mm of the traffic lane lines or within 300 mm of the centre of a traffic lane. | PASS,FAIL,N/A
button | 8e5b7155-9f85-5111-ab2c-2256e6a1c989 |  | button | • Has all of the above been completed correctly and to a high standard? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Place and compact layers so that the surface finish is smooth and uniform.
button | d5c40799-dec6-55f0-b5de-01f24e2c0f57 |  | button | • The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line. | PASS,FAIL,N/A
button | 650b52cf-a28b-5f97-8714-93433ce1bcfe |  | button | • No point > 8 mm below a 3 m straight edge in any direction | PASS,FAIL,N/A
button | c012a4f1-9a24-5bd1-8f5f-8558d214b181 |  | button | • No point >10 mm below a 6 m straight edge in any direction | PASS,FAIL,N/A
button | b1d53594-1e4f-5c9a-a238-1d233739fbcf |  | button | • Has all of the above been completed correctly, to a high standard and approved? | PASS,FAIL,N/A
button | 069e39a4-2f55-531e-ac04-1d19950db139 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 67728596-e8d6-5647-ad04-40a2a517fcf8 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 82c65391-9642-5002-a7b1-797f17af2e35 |  | button | INSPECTION POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
checkpoint-status |  |  | checkpoint | • Area shall withstand test rolling without visible deformation or springing.
button | 1afde912-aa51-51f4-b720-4c8a44affa27 |  | button | • Has all of the above been completed correctly, to a high standard and approved by relevant authority? | PASS,FAIL,N/A
label | 90488946-f74d-5b69-a814-c628bf728d32 |  | note | If ‘no’ please see below
label | a7b3e41f-6854-5430-8ce5-8797321350c8 |  | note | If ‘yes’ please proceed to 2.7
button | ccf4b6e3-61b2-5436-b17f-4e6c00267cda |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | ec98c747-49db-599c-b683-63afbf5f5fd0 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | ea296c11-2b7f-58ba-935f-2b6aa3c52b63 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • What quantity of soft, wet or unstable material is present?
text | b6a48d73-11dd-53e5-a05d-46640bfb4113 |  | textbox | • Quantity |  |  | m2
text | 4f7b7902-2e84-50ff-82cb-bd40ffeb8020 |  | textbox | • Quantity |  |  | m3
checkpoint-status |  |  | checkpoint | • Has rectification process been submitted to VicRoads for Review?
text | ee3e468a-14a0-5430-b24b-a4c3bc574a19 |  | textbox | • What was the rectification process used?
button | be2ccab2-05ec-53d1-a5f4-075d23fcc627 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 15f2454b-4854-58f0-b10a-99026ffd89d9 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
button | 1cf45bd6-16c9-5f10-a6d6-90127cf7fac8 |  | button | • Has all of the above been completed? | PASS,FAIL,N/A
button | e1d0ace9-83cc-5e43-9d06-1137996f0382 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 8389e9c0-1b71-562f-8483-30bfd9d0272a |  | button | INSPECTION POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Testing
checkpoint-status |  |  | checkpoint | • Characteristic Density Ratio % (six tests per lot): Not less than 98.0% Modified (Scale A)
button | baa51b16-916a-5655-bbc7-5d62251bbef3 |  | button | • Characteristic Density Ratio % (six tests per lot): Not less than 97.0% Modified (Scale B) | PASS,FAIL,N/A
button | 99ba0f28-20c4-5010-91a4-b58e765de79a |  | button | • For layer directly beneath bituminous surface, not less than 100.0 for scale A and 98.0 for scale B | PASS,FAIL,N/A
button | aa7e0829-e75d-5a11-a9ea-9ce4cb69b63a |  | button | • Has all of the above been proven to meet and/or exceed minimum tested requirements? | PASS,FAIL,N/A
button | 7011124f-1660-545a-a4cb-7e1d7d98209b |  | button | REVIEW POINT - Signature by CYP D&C JV | Yes,No
button | 40d3cd40-d517-5267-8d3d-eb0a9da29f72 |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
button | d55f7e7a-30bf-502c-a399-f59864f601df |  | button | • For Subbase, one Characteristic Density Ration % (six tests) will be completed for every second lot. | PASS,FAIL,N/A
button | 52cf8fda-ba3f-5948-af0e-fe4dbd4db93d |  | button | • Testing will be completed at the minimum frequency until such time as a lot fails to achieve the specified requirements. After a failed result, all subsequent lots will be tested until three consecutive lots of like material and work have achieved the specified standard, at which time the frequency of testing may revert to the minimum frequency | PASS,FAIL,N/A
button | e7cdd572-c723-5c83-a5c3-aa9afc399674 |  | button | REVIEW POINT - Signature by CYP D&C JV | Yes,No
button | 76c38ced-8fa9-51df-a098-ff90b92a1d2c |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 Completion
checkpoint-status |  |  | checkpoint | • Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
button | d03bb4ee-7b48-5849-99fb-6790edbcc59b |  | button | • Surface level checked for compliance with 304.06: | PASS,FAIL,N/A
button | f88ec424-0315-5110-a3df-f5f35971b0f8 |  | button | ○ Mean +6 mm to -10 mm with a max std deviation of 10 mm (Scale A) | PASS,FAIL,N/A
button | 755bddec-bc1d-52fd-9f18-793542cfdf87 |  | button | ○ Min 80 measurements per lot (Scale A) | PASS,FAIL,N/A
button | 02674fae-2d99-5863-ae83-2c8218f56943 |  | button | ○ Mean +8 mm to -16 mm with a max std deviation of 15 mm (Scale B) | PASS,FAIL,N/A
button | 5c3e3caa-5901-5597-ae23-1a17e87fe306 |  | button | ○ Min 40 measurements per lot (Scale B) | PASS,FAIL,N/A
button | 9b93bab3-ecb7-5718-aa52-34acf27160dc |  | button | • Has all of the above been proven to meet and/or exceed requirements set out in contract? | PASS,FAIL,N/A
button | 5d9779bc-ee70-5448-8181-bf3a6c77a42a |  | button | REVIEW POINT - Signature by CYP D&C JV | Yes,No
button | f34763d1-3fda-58f1-8d81-62b74312884c |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 5.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | • All Test reports received and Reviewed as per Requirements for Testing and Acceptance of Surface Level Measurement, Compaction and Post-compaction Gradings and PIs (Clauses 304.06, 304.08, 304.10 and 304.11)
button | 47c9fe5e-dbd6-589e-b2b3-c2d235f54f66 |  | button | • Has all of the above been proven to meet and/or exceed minimum tested requirements? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
button | 221785de-2b61-584c-a050-f7ad36b89fb9 |  | button | • Has all of the above been proven to meet and/or exceed minimum tested requirements? | PASS,FAIL,N/A
checklist-flat |  |  | checklist | Bluestone Wastage Record |  |  |  |  | Yes | Bluestone Wastage Record | 43000787-9117-4bac-859c-453380f34eb7
checkpoint-status |  |  | checkpoint | Bluestone Wastage Record
text | 6e49080c-de36-591c-a22c-40cff299388d |  | textbox | 1. Bluestone Type
text | afda8780-79a9-5127-b1d8-185d96f492e3 |  | textbox | Wastage Amount - Unit
text | 00c859a1-5d4e-5744-811a-f20330870dcc |  | textbox | Zone
text | a9b2d2ae-fd55-587e-a4ad-f868d6932927 |  | textbox | Date
text | cac4af72-0b7e-5e49-9a1f-41d5f3eee25b |  | textbox | 2. Bluestone Type
text | c4ff7843-7730-5d3b-aea8-e2fc226eb289 |  | textbox | Wastage Amount - Unit
text | df487fb5-f034-5e0d-ae75-72eca1ccf16e |  | textbox | Zone
text | 0c624d2d-ad6f-51ea-856a-fb241db5aa0c |  | textbox | Date
text | 015a6c99-98b8-56a7-9f09-129e60b15d64 |  | textbox | 3. Bluestone Type
text | a7f00d06-9aac-50c3-9e0e-eb279120ee20 |  | textbox | Wastage Amount - Unit
text | 17e147dd-5881-5b2e-8fa8-7ba82261da88 |  | textbox | Zone
text | 809f2958-92c3-5630-9327-eaa408bb46b4 |  | textbox | Date
checkpoint-status |  |  | checkpoint | Sign-Offs Click to Attach Signature(s) below
button | 090b3cea-8000-508a-905b-89c90ee9bf80 |  | button | Signature by CYP D&C JV | Yes,No
button | 967f73d1-26ed-5c69-b78e-4a63f18ed6e0 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | REQUEST SIGN OFF
checklist-sectioned |  |  | checklist | SYM-ITP-016 - Gross Pollutant Trap & Diversion Structure PV-GPT-2 (RevA) |  |  |  |  | Yes | SYM-ITP-016 - Gross Pollutant Trap & Diversion Structure PV-GPT-2 (RevA) | 4451912e-0f27-4df0-970b-4078ef363d35
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-status |  |  | checkpoint | • Prepare the excavation for the Vortceptor separation chamber first.
button | 4bb0b0c1-edfa-50fc-904a-c608415e0c49 |  | button | • Did the excavation for the Diversion Chamber (the rectangular precast concrete chamber) follow afterwards the Vortceptor. | PASS,FAIL,N/A
button | 08e25337-492e-57e3-b15b-da2046d38518 |  | button | • Was the inlet pipe run would installed, within one or two pipe lengths prior to the diversion chamber. | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | 72096a40-d455-541e-b640-ec149e9ef8aa |  | textbox | • Zone
text | 87e4b5d2-ccd0-5367-a3c0-17fb90c03404 |  | textbox | • Stage
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
button | 1847fee0-79f6-5c5d-abb7-f07611298b85 |  | button | • Relevant permits have been signed and approved? Attach Completed Permits. | PASS,FAIL,N/A
button | 5f1a4198-4267-506f-b80f-0e4fa030abe4 |  | button | • Extents and levels correct to relevant drawings | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • 50mm Blinding to be placed as required to allow working surface and protect excavation.
text | b22f62f4-ec68-5e93-9cee-d318f94570ae |  | textbox | • Excavation for Vortceptor to a total depth of |  |  | mm
text | 2f53c86b-99e1-5f73-8b92-e0380ca90572 |  | textbox | • Excavation for Diversion Chamber to a total depth of |  |  | mm
button | 8bd19353-4ca1-5ff3-bce9-bdf75e3dcbac |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | df7d73dc-f195-5ab2-8bd8-b4572756c3ee |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Vortceptor Installation
checkpoint-status |  |  | checkpoint | • Were measurements checked on the Vortceptor prior to installation, and confirmd as per approved IFC
button | 0eeffa3d-2972-5cc1-880a-ea6fa88aaa3f |  | button | • The Vortceptor excavation should be no greater than required, this would be 1000mm oversized or to suit shield sizing. This is with due regard to the amount of backfill to be used under and around the tank. | PASS,FAIL,N/A
button | 090027e5-1265-5ba4-93cf-0eb256f58367 |  | button | • Were 150mm thick, compacted base of either a concrete blinding or compacted crushed rock layer installed. | PASS,FAIL,N/A
button | 79a9ee69-334c-5925-a9de-e91e0c62032a |  | button | • Was the Vortceptor lowered into the excavation with no rocks or sharp objects falling into the hole and no damage to the tank | PASS,FAIL,N/A
button | 5a57f913-98cd-5986-a626-1d76b87adb8c |  | button | • Were the levels of the Vortceptor adjusted to suit pipeworks and diversion chamber inlet void? | PASS,FAIL,N/A
button | b2c52f82-9d8f-5553-bc84-815798ac1e46 |  | button | • Fill the tank with water up to the invert of the inlet | PASS,FAIL,N/A
button | 566ae935-f4ae-5fa5-a35d-d97a71f76569 |  | button | • Encase & backfill the outside of Vortceptor as per project backfilling specs | PASS,FAIL,N/A
button | 7d810383-8187-57bf-94b9-70b944c43aef |  | button | • Is the take located in an area subject to high water table or trapped underground water? If yes, the tank must be completely encased in unreinforced concrete, up to the specified height above the Vortceptor base, and at the minimum specified width beyond the perimeter of the Vortceptor base. Refer to SPEL Stormwater for recommended concrete dimensions and volumes to withstand buoyancy forces. | PASS,FAIL,N/A
button | 7bb7b706-2ae8-5eb2-b968-f34d64585a66 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 83ecadd7-49c4-535b-95bb-93e7a70b8262 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | be960a85-e1b2-5f72-a5d6-a67d6df3bd69 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Were measurements checked on the Diversion Chamber prior to installation, and confirmd as per approved IFC
button | 12bd10b9-f9c2-57fd-a7fa-5112e653be09 |  | button | • Has the diversion chamber excavation pit been prepared as per Construction drawings | PASS,FAIL,N/A
button | ea2a7e56-4ce7-5967-8013-5057126d5a6b |  | button | • Is sufficient room left to install inlet pipe and pipe is angled to be fed into the diversion chamber? | PASS,FAIL,N/A
button | 2671d2c4-e9b9-5249-b285-f8f7d5e6f6ef |  | button | • Was the Diversion Chamber adjusted to a correct level so the rectangular opening matches the Vortceptor with the inlet and outlet block outs are to match the drainage line. | PASS,FAIL,N/A
button | 4352b27b-03ee-534b-ac4b-cefb89cd92ed |  | button | • Use the template provided with the Vortceptor to drill the bolt holes into the diversion chamber rectangular void. | PASS,FAIL,N/A
button | 311d7cba-eb48-5632-8fc3-6a55deb74889 |  | button | • Use Sikaflex or silicone to seal the Vortceptor to the Diversion Chamber, use 8.5mm 4 cutter SDS bit to drill the bolt holes. | PASS,FAIL,N/A
button | 22933089-36a1-59c8-94d8-b5da20456090 |  | button | • Use M8 x 100mm Galvanised screw bolts to fix the Vortceptor to the Diversion Chamber. | PASS,FAIL,N/A
button | 30fd3e42-a6bb-50d6-9e09-d6c1295a62aa |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | b80e82f1-1193-56ea-ad5e-4babf5ca2373 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | ec9795ea-46f7-55b8-9276-8b82fa90e72b |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Were upstream and downstream drainage pipework Installed?
button | 4d97cd35-ce70-5d66-8f6d-4ea81c738c9a |  | button | • Connect the pipework to the Diversion Chamber, concrete bandage the inlet and outlet pipes to the Diversion Chamber. | PASS,FAIL,N/A
button | 83c85ca7-ee7b-5076-8847-cc3f7b8135a6 |  | button | • Internally render the inlet and outlet pipework | PASS,FAIL,N/A
button | 02252e8c-f4c7-5749-8917-7e445812d807 |  | button | • Use low slump concrete to mass infill and bench the base of the diversion chamber and weir. This is to direct the flow and remove any dead zones in the diversion chamber. | PASS,FAIL,N/A
button | 282eefa8-9b70-557b-b7f0-ca2b0b51653a |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 0903ee0d-6758-5211-b9e6-9c27deac7379 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Use a Sikaflex bead around the rebate on the top of the Diversion Chamber to ensure a satisfactory seal between cover slab (Lid) and chamber.
button | bbf4093a-1598-5682-b591-52167acbf298 |  | button | • Lift and install cover slab, ensure manhole void / cover is on Vortceptor side of the chamber. | PASS,FAIL,N/A
button | 7ec2cf2c-1570-5c3f-b729-2b005e3dd41c |  | button | • Use Sikaflex and screw bolts to secure fibreglass manhole riser to cover slab | PASS,FAIL,N/A
button | 20fd42ab-0a31-5a7d-92f6-6c62a2d9479d |  | button | • Tie in the manhole covers as per lid manufacturers installation guidelines, to achieve Finished Surface level. | PASS,FAIL,N/A
button | 3bfe4a2f-9373-5916-8d2b-d42ecc90fc37 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 592343d1-cb42-5919-a2e1-54ec5eaf03c2 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-004 - Underscreed Concrete Pavement (Rev A) |  |  |  |  | Yes | SYM-ITP-004 - Underscreed Concrete Pavement (Rev A) | 45c320a6-edfc-4e03-aacd-fd2166ee853d
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Concrete mix design approved by the Superintendent and a registered mix and Material properties meet project specifications
text | 13040630-3987-53cd-a913-5182ee60f1f4 |  | textbox | • Concrete Strength
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?Attach Recent IFC Drawings
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
checkpoint-status |  |  | checkpoint | • Is edging constructed over Pavement layer?
checkpoint-status |  |  | checkpoint | • Where edgings are constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer.
checkpoint-status |  |  | checkpoint | • Is bedding for footpaths and surfaces compacted to 100mm thickness unless noted otherwise.
checkpoint-status |  |  | checkpoint | • Is bedding for SUPs, bedding compacted to 150mm thick unless noted otherwise.
checkpoint-status |  |  | checkpoint | • Bedding shall be moist but shall have no free water on the surface before concrete is placed
checkpoint-status |  |  | checkpoint | • Is bedding material used for cast in place concrete paving works compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
checkpoint-status |  |  | checkpoint | • Is bedding material for shared use paths compacted size 20 mm Class 3 crushed rock or Class 3 crushed concrete in accordance with Section 812 or 820 respectively, and Section 304.
checkpoint-status |  |  | checkpoint | • Are pavement lots tested for compliance with the specified compaction scale for moisture content no less than 85%
checkpoint-status |  |  | checkpoint | • Is fill material used below bedding tested to Table Compaction Requirements
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved.
text | 71fe94ff-9f36-50d8-a95f-25480bc6267e |  | textbox | • Excavation to a total depth of
text | 8ffd23af-c4c3-5cbf-848e-6d094dc7b264 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | a6ef61a6-647a-505a-bc0d-19e052ff6da9 |  | textbox | • Zone Reference
text | bf2d2a35-784c-5a9c-a0a7-72ea440e1f4b |  | textbox | • Stage Reference
text | f352dc63-3674-5986-9332-d7c105acd430 |  | textbox | • What is the Sub-Base Course layer Thickness
text | 57ccbb0a-34eb-5ccc-8a39-618dd0bce098 |  | textbox | • what is the Class of crushed rock or crushed concrete placed?
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 27dd6243-fc48-5260-8e7b-325fb88897be |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 2c325591-b1ee-505f-b529-ed50b9b5a311 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Under screed/Concrete Pavement Installation
checkpoint-status |  |  | checkpoint | • Formwork has been installed correctly and sufficiently braced.
checkpoint-status |  |  | checkpoint | • Formwork set out has been done as per latest design drawings and specifications
checkpoint-status |  |  | checkpoint | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed
checkpoint-status |  |  | checkpoint | • Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified/Sockets
checkpoint-status |  |  | checkpoint | • Mesh installed with 40mm top and sides cover and 50 mm Bottom Cover
checkpoint-status |  |  | checkpoint | • Tolerance - As per specifications and Australian Standard
checkpoint-status |  |  | checkpoint | • Steel is free of excess corrosion, loose millings, oil or other contaminants
checkpoint-status |  |  | checkpoint | • Required Connection Details - U Bars/ Z Bars/Cogs/Starter bars Verified
checkpoint-status |  |  | checkpoint | • Correct concrete cover and chairs on sides, bottom and top Verified
checkpoint-status |  |  | checkpoint | • Has steel reinforcement been placed correctly with adequate cover?
checkpoint-status |  |  | checkpoint | • Have tie bars and joints been installed at the correct intervals?
checkpoint-status |  |  | checkpoint | • Pour area is free of loose debris, oils, water
checkpoint-status |  |  | checkpoint | • Have any services/penetrations/blockout located within the Pavements been installed, surveyed and pinned down
checkpoint-status |  |  | checkpoint | • Concrete Testing Lab Representative will be available during concrete pour
checkpoint-status |  |  | checkpoint | • Sufficient vibrators are available during concrete pour
checkpoint-status |  |  | checkpoint | • CYP D&C JV informed of concrete pour date and start time
checkpoint-status |  |  | checkpoint | • Attach subcontractor ITPs
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | b90267ce-e465-5174-a3e9-e911558c61f7 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 6ffd57f7-a2da-5b44-a700-1967b9397c5e |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Placing, compacting and finishing concrete
checkpoint-status |  |  | checkpoint | • Is concrete temperature as per VR703. and not mixed when the air temperature is lower than 5°C or greater than 35°C.
checkpoint-status |  |  | checkpoint | • Is discharge Time 60 minutes unless mix design is approved by Proof Engineer for 90 minutes.
checkpoint-status |  |  | checkpoint | • Is concrete thoroughly compacted and works carried out as per Australian Standard & Project Drawings/ Specifications
checkpoint-status |  |  | checkpoint | • Are concrete samples taken in accordance with 610.16(b).
checkpoint-status |  |  | checkpoint | • Is specified slump tolerance within 610.16(c).
checkpoint-status |  |  | checkpoint | • Is concrete mixed for not less than a period of three (3) minutes prior to discharge.
checkpoint-status |  |  | checkpoint | • Is the maximum time lag between truck loads on site shall not exceeding 25 minutes if a continuous pour
checkpoint-status |  |  | checkpoint | • A minimum of one of vibrator used at all times while the concreting is in operation
checkpoint-status |  |  | checkpoint | • Were forms/cast in items monitored during the pour.
checkpoint-status |  |  | checkpoint | • Concrete Dockets Received
text | 0a26e172-ac3d-5bd8-ae2d-1ec6b017b44b |  | textbox | • Concrete quantity
text | b183beb4-2d3b-5d83-acad-0e930a1cfe41 |  | textbox | • Pour date
checkpoint-status |  |  | checkpoint | • Concrete Fall achieved as per latest IFC drawings
checkpoint-status |  |  | checkpoint | • Concrete pour record attached
checkpoint-status |  |  | checkpoint | • Concrete test results attached.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | fb1440cd-916e-5736-b837-4b7b5d0fbd14 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 0a6d6a33-8e31-5688-86a5-f510d7ecede7 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 Post Pour/ Finishing
checkpoint-status |  |  | checkpoint | • Did concrete achieve the required finish as per specifications
checkpoint-status |  |  | checkpoint | • Are hidden concrete surfaces of concrete paving have a Class 4 surface finish in accordance with AS 3610.
checkpoint-status |  |  | checkpoint | • Curing agent applies as per project specifications
checkpoint-status |  |  | checkpoint | • Concrete reached design strength to strip formwork. (Attach test results)
checkpoint-status |  |  | checkpoint | • Any identified defects after stripping rectified
checkpoint-status |  |  | checkpoint | • Were expansion joints placed at intervals less than 10m.
checkpoint-status |  |  | checkpoint | • As Built Survey completed and report attached.
checkpoint-status |  |  | checkpoint | • Concrete test results attached.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-group |  |  | section | 5.0 Backfilling
checkpoint-status |  |  | checkpoint | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
checkpoint-status |  |  | checkpoint | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checklist-flat |  |  | checklist | Document Upload Checklist |  |  |  |  | Yes | Document Upload Checklist | 53059a19-6c3d-4269-9379-28c3e49a2d77
checkpoint-status |  |  | checkpoint | Document uploaded below
checklist-sectioned |  |  | checklist | SYM-ITP-011 - LANDSCAPING (Rev A) |  |  |  |  | Yes | SYM-ITP-011 - LANDSCAPING (Rev A) | 54384f7e-b94e-4bbd-af32-a96fe5311843
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Have all relevant samples been provided to CYP and approved?
button | 3d7f05a3-2ae3-5382-a34c-be104ac4fc68 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | f3b7ed43-66ae-54c9-a15d-7c42505a2c30 |  | button | REVIEW POINT - Signature by IR | Yes,No
button | f1f34fba-3faf-569e-bd13-145d8ffaddce |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Pre-Construction Activities
checkpoint-status |  |  | checkpoint | • Have all plants been set out in garden beds prior to planting?
checkpoint-group |  |  | section | 3.0 Construction Activities
checkpoint-status |  |  | checkpoint | • Has cultivation been undertaken as specified?
checkpoint-status |  |  | checkpoint | • Has topsoil been placed in the manner specified, alongside to the depth specified in detail on drawing set?
button | abf2d314-4ca6-54d6-8d57-2f042fb70a0f |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 7d8f4a93-d90f-5c98-bf72-fdc2cc4ca670 |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has mulch been placed in the manner specified, alongside to the depth specified in detail on drawing set?
button | 683bb588-ea65-5656-8527-7adfa9d9ddb8 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 36d8ba4c-77e8-5b8d-8e35-bf0d37bd9124 |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has edging been placed in the manner specified, referencing both design standards, drawing details and manufacturers recommendations (where relevant)?
button | 7547ce5c-775b-532e-abd2-e446fcf7802d |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 296fdd14-6cb9-5ac1-bc3e-d19cab57390e |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Have all plants been placed / installed in the manner specified?
button | 2a4c4deb-1797-5acf-abce-7028a7419171 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 70829cff-3cbc-54fe-8652-31948bcae14b |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has turf been installed as per method described in section 3.17 ‘turfing’?
button | 92c31fb7-0109-5529-9e32-3dd8fbea79cc |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | ab30c9aa-b04e-5923-889c-5e56f54d3f6c |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-006 - Stormwater (Rev A) | itp |  |  |  | Yes | SYM-ITP-006 - Stormwater (Rev A) | 56d18076-dd36-4842-a224-6bcb6791a95c
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Lot shall be defined from pit to pit (or endwall, where applicable).
button | 5148170b-7467-5636-bd2c-ba6e226df061 |  | button | • Do survey boundaries clearly define the Underground Drainage Construction works? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Is the Box Culvert free of defects and to drawing dimensions?
checkpoint-status |  |  | checkpoint | • Is the Pipes free of defects and to drawing dimensions?
checkpoint-status |  |  | checkpoint | • Have proposed precast Covers, Grates, Lids and Pits been approved for use?
checkpoint-status |  |  | checkpoint | • Is material free from perishable matter and lumps?
button | d023e6b3-463a-5eb3-8d18-e4ff0d06a6cd |  | button | • Does the material comply with Table 701.091 & Table 701.092 below? Has the material been approved for use? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Pipe/Box Culver/PIT Size & Class
text | 94f2f88f-116e-5b53-bc3e-8243968d798b |  | textbox | • SIZE
text | 11c842d9-f201-5102-91e6-36e4a87b82bd |  | textbox | • CLASS
select | 7f472490-cab8-57f6-9f17-f9d6f70bc907 |  | dropdown | DIA | 150, 225, 300, 375, 450, 525, 1050
text | 0c199752-d2dd-585f-ad2d-3a703ffa0500 |  | textbox | • PIT REF
text | 81c1f74d-a84a-54fe-9484-6f65f9855462 |  | textbox | • PIT REF
text | 3ceb2e4c-bb83-5eac-a775-f8ed86236b50 |  | textbox | • PIT REF
checkpoint-status |  |  | checkpoint | • Stage/Zone
label | 72d355a6-6797-59e0-b34f-d52a2f1f51a7 |  | note | 1A / 1B/ 1C/ 1D / 1E / 1F / 1G / 2A / 2B / 2C / 2D / 2E / 2F / 2G / 3A / 3B / 3C / 4A / 4B / 4C / 5A / 5B / 5D / 6A / 6B
text | 63e48955-303c-529a-b275-813363832e08 |  | textbox | • Stage
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Excavation
checkpoint-status |  |  | checkpoint | • Is the trench clearance width between 300mm to 600mm?
button | 11ef4eec-b6d8-5daa-9374-0718c4683a40 |  | button | • Is the excavation at a sufficient depth for pipe/box culvert bedding? | PASS,FAIL,N/A
button | 7797bae4-3baf-5d92-bb10-e4398ffc8181 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 06b4021f-f4fc-5c5c-8a80-1a9b0713e815 |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | df4c5835-9dfa-5826-8f8e-26be22814b75 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Is the pit excavation not less than 400mm from external pit wall to side of excavation?
button | a036f99a-1208-53be-a9d0-dc0df69b850a |  | button | • Is the excavation at a sufficient depth for pit bedding? | PASS,FAIL,N/A
button | 20a7452c-3fbf-54a9-8dca-381e63d63908 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | fcfe1fe7-ef7f-5672-a903-cf7f5a53f0e3 |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | 0e52d2c3-9a07-53ec-9141-907c06c3d6bb |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Bedding
checkpoint-status |  |  | checkpoint | • Is the Pipe Diameter less than 1500mm? If so, has 100mm of bedding been placed?
button | dfc42d1c-01ba-554f-a302-e9bc73e3b776 |  | button | • Is the Pipe Diameter greater than 1500mm? If so, has 200mm of bedding been placed? | PASS,FAIL,N/A
label | 6e4f89df-215d-5e85-9656-8417f77978a8 |  | note | (D = Pipe Diameter/Culvert Width).
button | da15dc90-4f75-5fa5-be35-f1fd29867432 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 30d78d1b-8f3c-5dd6-ab71-fb9f4fa9ba4d |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | 39c599ba-394a-5105-9458-8bc6d3ec028a |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Has bedding been placed and compacted to a thickness not less than 80mm on clay foundation?
button | bd141bcd-4548-560f-aa9f-b751b3fb77b3 |  | button | • Has bedding been placed and compacted to a thickness not less than 150mm on a rock foundation? | PASS,FAIL,N/A
button | 56a69011-53c1-5c2f-b38d-f4a990fab09e |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | c610f2af-24b3-566f-a2a8-911288c206e1 |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | 9621d858-f6a1-5d85-a2c3-814abf95eb4d |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Has bedding been compacted to refusal?
button | d4d40598-ec62-5e81-b577-9f33c813c1b0 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 744372d8-4754-5f3f-a257-3fb40b265060 |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | 6f82b461-2ab6-557c-bff7-f30389cba33b |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0
checkpoint-status |  |  | checkpoint | • Are pipes being laid from downstream end?
button | d5d99c7a-fc08-5eb9-82a8-40b2d0ef4de8 |  | button | • Are socket ends of pipes being placed facing upstream and fully entered? | PASS,FAIL,N/A
button | de28b7ff-25a3-586c-837e-7608d83da496 |  | button | • Is the pipe in full contact with the bedding for the full length of each section? | PASS,FAIL,N/A
label | 7ff63b67-0102-5c98-93b2-575dd6e36b92 |  | note | ○ The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
button | 35900107-2521-5b6f-9170-85f18ee23895 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | b5ef85ef-c8f2-559c-9709-8a53a7c6ee1e |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | f9d2a1be-dd5f-5b9f-865d-e970a6f8b29c |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Have pre-cast pits been installed at the correct location and to the dimensions shown on the drawings?
button | 871166fe-f0c0-59ec-9917-9e0dd17df53a |  | button | • Have subsurface drainage connections been cored at appropriate dimensions? | PASS,FAIL,N/A
button | 331e0e23-9623-5878-a7c5-364de8050402 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 700c7819-f02b-5ecc-ad8a-04e48f1792ec |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | d84d913c-dcbc-568c-8089-5f5222d7f603 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Have pits greater than 1.0 meter been fitted with step irons?
label | 315c6cd0-be9c-51bf-9c26-cfa2e988c95e |  | note | ○ Step irons shall not obstruct openings or be fitted to a wall which has openings.
button | 53e79f96-1489-51f1-8e50-9a120928d9ea |  | button | • Have step Irons shall be installed in accordance with the manufacturer’s instructions and are an approved proprietary type? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Has the drainage pit floors been smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar?
label | 35a9be64-732e-5993-bd7e-261e964e668f |  | note | ○ Surfaces shall be finished uniform in appearance with a Class 2 surface finish in accordance with the requirements of Section 610.
checkpoint-status |  |  | checkpoint | • Has the joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar?
button | 205347e3-778a-5d16-9539-0bd5fb310fa9 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 9a316b89-8266-5ec4-ae3e-83a973fc88dd |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | 25cfaabe-4a53-5fce-830a-912491d4bf5e |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | Are rubber rings to be used on rubber ring joint pipes clean and free of debris?
button | ce79a7c0-c447-5602-b65f-f39e253fdc89 |  | button | Have all interlocking joint reinforced concrete pipes been jointed or wrapped with 200mm wide external joint rubber band? Has the rubber band been placed between the spigot and socket? | PASS,FAIL,N/A
button | 48650677-1de0-51bf-8564-105e9c3df2d9 |  | button | Have pipes with lifting holes been placed with lifting holes uppermost? Have lifting holes been plugged after pipe installation? | PASS,FAIL,N/A
button | 7737a86f-c67d-5eb5-8313-6aa95efe06f0 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 5f048756-7154-5a6e-b4f1-d9e5d3e52a7c |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | 92b54d0a-a334-5d6c-9259-81a15b677e6c |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Fitting of Covers
label | ed7c6467-d0b1-5351-8dff-8be4e85eaa01 |  | note | ○ Pit Downstream
text | 49746d4c-0c77-56ee-8fdb-9555fecd5180 |  | textbox | • Pit Number
text | 05f7cf2d-d03c-59ca-8101-109fd7aab5b0 |  | textbox | • Lid Class
text | 4e597baf-54ed-5b35-847e-a911bfc5a078 |  | textbox | • Lid Type
label | 3c45817f-a71b-5256-affe-c95a0c1c4bfe |  | note | ○ Pit Upstream
text | 6bf39a25-4406-5dfa-b38a-f02b79a0f2f7 |  | textbox | • Pit Number
text | b98f6fa8-dee4-5b39-96e6-a58222e8897e |  | textbox | • Lid Class
text | 603ec264-4bd6-5b5c-aba6-6c58ee7c4f3f |  | textbox | • Lid Type
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 5.0 Installation of Box Culverts
checkpoint-status |  |  | checkpoint | • Have consecutive sections of box culverts been firmly butted together?
button | bf5cd648-7745-5ff6-844f-22da8f2c7c7c |  | button | • Does the mortar have a minimum 28 day compressive strength of not less than 40MPa? Is it at least Type C Class? | PASS,FAIL,N/A
button | 93a9f304-c97b-5ac0-87d9-ad1780a64bf7 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 7c388bbf-2da1-5c45-a3b0-c4c1c8fc82cf |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | ac3da396-3789-5139-a4bf-29ac3dc51641 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 6.0 Backfilling
checkpoint-status |  |  | checkpoint | • Has the haunch zone been extended from top of bedding layer to 1/3 pipe diameter? Haunch zone material to be same as bedding layer. Haunch zone to be compacted to refusal in max 150mm layer.
button | 7e63a2f3-3042-5d71-916f-60be305df7cf |  | button | • Is the pipe to be backfilled in under an area to be paved? If so, has excavation below design subgrade level been backfilled with select backfill material? And within the pavement layer backfilled with appropriate pavement material? | PASS,FAIL,N/A
button | 1e77bdaf-ac3a-5be4-a6df-752b5552cc00 |  | button | • Is the pipe to be backfilled in under an area to be paved? If so, has excavation below design subgrade level been backfilled with select backfill material? And within the pavement layer backfilled with appropriate pavement material? | PASS,FAIL,N/A
button | 36366498-eb55-5908-8760-b8270b3f0430 |  | button | • Is the pipe to be backfilled in under an area not to be paved? If so, has the trench been backfilled with select backfill material to a level 0.3m above the top of the culvert? Ordinary backfill may be used above that level. | PASS,FAIL,N/A
button | 791a62c1-4b31-58fa-82ac-0a0b2eac5540 |  | button | • Has the backfill material been backfilled in max 150mm layers? | PASS,FAIL,N/A
button | 12d2925d-b01e-5037-b3c6-1f6ff747a120 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | ac38b706-e1a9-5337-96fa-3541b7ee2dbb |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | 5ff26cb3-b260-586f-8b83-9c98a3e5d932 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Has the pit been backfilled in layers not exceeding 300mm? Pit backfill to be compacted to refusal using hand held equipment.
button | 1514551a-f802-5720-9ba0-efc07d05fa9a |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 8a65a9fe-5fca-58c4-83d3-b487d1551803 |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | 8d526b51-6b17-5c38-8d74-b287387f0619 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Has the pipe been laid with adequate fall and invert levels within ±10mm of design?
button | 4194482c-1adf-5a22-804b-3bda75151159 |  | button | • Is the invert level of pipes at pipes ±50mm of design? | PASS,FAIL,N/A
button | 2fbd8da2-b1e8-58c7-910a-f6ac38ed7ccc |  | button | • Is the line of the pit cover been installed ±10mm of the design kerb line? | PASS,FAIL,N/A
button | c422a3c5-f880-5cb7-8a58-13446c964acb |  | button | • Is the pit cover level ±10 mm of the design level for that point? | PASS,FAIL,N/A
button | b990fc75-6a2d-5799-8cff-6243b5a7bdd9 |  | button | • Is the offset of entry pits within ±20 mm of kerbs/barriers? | PASS,FAIL,N/A
button | 5c8e4d7f-89b8-51cd-a34e-2ec56f5207ae |  | button | • Is the offset of entry pits within ±20 mm of kerbs/barries? | PASS,FAIL,N/A
button | 21da1a72-8dd9-525b-9c89-1e0a5a329838 |  | button | • Is the plan location of pits other than offsets to kerb lines or barriers ±100 mm? | PASS,FAIL,N/A
button | 2495e51b-35f8-576f-8423-d28aaaa92b6f |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 8b599479-ac6c-59ec-a1c4-a9f35046cbeb |  | button | REVIEW POINT/HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Has a total of 3 compaction tests taken place, per lot, inclusive of pit compaction, achieving 97% compaction?
button | d48734a2-534c-563b-97af-832088fa822d |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | faab7c21-506a-5575-8489-2908f8861e75 |  | button | REVIEW POINT/HOLD POINT - Signature by Symal Infrastructure | Yes,No
checkpoint-status |  |  | checkpoint | • Have all storm water lines been inspected by CCTV and found to be free of defects prior to placement of pavement?
button | 949c3d88-8e87-5086-8ea6-cf9f41610d2e |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 8e82be06-c260-56ac-a5e9-b7221b37aa3b |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | SYM-ITP-024 - Handrails & Balustrades (Rev A) |  |  |  |  | Yes | SYM-ITP-024 - Handrails & Balustrades (Rev A) | 574d3508-eab4-44d0-8074-02b4087cb41f
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | eb4982e4-f8dc-569e-8924-80d39dae8720 |  | textbox | • Handrail/Balustrade Reference
text | 3eb5e4d2-941b-57f2-9913-dbd377324fb8 |  | textbox | • Zone Reference
text | 5037d431-edbe-5d5e-8860-a6bf4a5b64cf |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved.
button | 8748e719-992d-5653-b88c-60a69df2d645 |  | button | • Extents and levels correct to relevant drawings | PASS,FAIL,N/A
button | 5614d78b-ae57-5c6e-a57b-cd59c9aae189 |  | button | • Are handrails and Balustrades compliant with DDA standards. | PASS,FAIL,N/A
button | bcd3ec3c-3855-5d1d-bb67-9563cdab97c2 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 3bb13fd2-8390-534c-88ce-54d11a0233ed |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Are handrails and Balustrades compliant with DDA standards.
button | 34ef5dac-90e6-534b-8405-39e237773aaa |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 5f1f46e6-ac8b-54b3-817a-d2765a331c04 |  | button | REVIEW POINT - Signature by IR | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Have the subcontractor ITP’s been completed and attached
button | f7ac3330-0a9e-5b34-a8c5-358618578209 |  | button | • Have handrail and Balustrades been installed as per approved shop drawings? | PASS,FAIL,N/A
button | 111f7b6f-f1d7-5289-8b5d-78d11f6eb793 |  | button | • All edges smoothed and final finish provided as per project specs? | PASS,FAIL,N/A
button | e40083f2-2a1f-5222-85e8-d76b338e87ae |  | button | REVIEW POINT - Signature by CYP D&C JV | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Were survey as-builts completed
checklist-sectioned |  |  | checklist | SYM-ITP-020 - Paving (Rev A) |  |  |  |  | Yes | SYM-ITP-020 - Paving (Rev A) | 591e1028-2d41-4c87-8c9b-4048071d8287
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-group |  |  | section | 2.0 Pre-Construction Activities
checkpoint-status |  |  | checkpoint | • Have pavers been set-out as per current drawings?
checkpoint-status |  |  | checkpoint | • Is the concrete slab free of any deposits or rubbish, projections/voids?
checkpoint-group |  |  | section | 3.0 Construction
checkpoint-status |  |  | checkpoint | • Has mortar been placed using type/method described in specification?
button | 07842402-52cf-5a78-9c12-2ef202f65db9 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | e6901a19-d1c7-5e83-a096-6992693422aa |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Where required, have been pavers been cut as described in specification?
button | 0d52ae74-6ae1-5cc9-88d1-583fc600b256 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | ce652d85-2a94-5d36-8e8d-e5d6f10a8d81 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Have pavers been laid as described in specification, considering specified tolerances?
button | 2d6f0afd-d22d-53be-bf6f-721623e576b7 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 0347f301-98c8-5d6a-9d25-fbab923aa7cf |  | button | WITNESS POINT - Signature by IR | Yes,No
button | ab1b26a1-a7b9-5dbf-9875-67d199a6459a |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Have joints been sealed as described in specification?
button | 074e5942-8ec5-547c-8ff0-5433e30536a4 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | d32a7895-ee15-5cdc-849d-0023e162d36e |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checklist-sectioned |  |  | checklist | SYM-ITP-012 - Stratavaults (Rev A) |  |  |  |  | Yes | SYM-ITP-012 - Stratavaults (Rev A) | 632b5e3c-5e56-46e7-8d64-3dd01bd86530
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-status |  |  | checkpoint | • Prepare the excavation for the Stratavaults
button | bf54d52a-8866-5e8b-ae60-d412a70b2372 |  | button | • Are all pipes extended for the startavault install | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | dc844e6b-6fc8-57fe-b1c7-bef9a681201d |  | textbox | • SV Reference
text | e5713396-1d49-5263-8c5d-b4ffe9af0ad8 |  | textbox | • Zone
text | a2175949-31d2-5400-8d8c-5cf2dd8c2cac |  | textbox | • Stage
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
button | b768c1d9-30c4-5816-8e29-c06368b06287 |  | button | • Relevant permits have been signed and approved. | PASS,FAIL,N/A
button | acd0ec0d-1afb-56b3-ab45-d1cc70cc4c60 |  | button | • Extents and levels correct to relevant drawings | PASS,FAIL,N/A
button | b75b15cd-1434-52a2-9561-11ea12497012 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 4fa68505-0c72-5341-9bd3-8909eb7f921a |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Stratavault Installation
checkpoint-status |  |  | checkpoint | • Are all stratavaults installed as per manufacturer specifications
button | 0658e99a-aa54-5056-8715-787983c2053c |  | button | • Manufacturer ITP’s completed and attached | PASS,FAIL,N/A
button | 1e8b1d28-8581-5183-8a67-45a3347e8c45 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 1d9f6e74-daec-533a-acdc-95fb036fc88a |  | button | WITNESS POINT - Signature by IR | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Soil testing and sampling completed as per manufacturer specification
checklist-sectioned |  |  | checklist | SYM-ITP-007 - Subsurface Drainage (Rev A) |  |  |  |  | Yes | SYM-ITP-007 - Subsurface Drainage (Rev A) | 720b45c8-5146-4f98-a475-fb5ac261b48e
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-status |  |  | checkpoint | • Material classification and source
button | 84ad74cb-2d6a-5047-a770-35b7a79107cf |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | a92c6321-a358-5f2a-a60f-9301b6db4668 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | b867b03a-57a0-55e7-a459-c5c5aa0e993f |  | textbox | • Subsurface drainage Reference
text | da9df771-59cc-5535-873d-3ff275c85388 |  | textbox | • Size of Lot |  |  | m
label | 1bd41f0c-1d72-58c9-966e-b29c2720d8a2 |  | note | • Days production or pit to pit
text | e238932f-0927-5493-9ef8-fa130423fd5b |  | textbox | • Zone Reference
text | 38544eb7-4300-57cb-8de8-52b80398aa55 |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Has the method of compaction shall be in accordance with the Contractor’s quality procedures been submitted for review by the Superintendent and approved?
button | d6168104-cd46-522e-9d65-9283cb7df87d |  | button | • Has no fines concrete been used as a filter material? | PASS,FAIL,N/A
button | 32ab46f7-0343-574c-a93e-48973d618cb0 |  | button | • Has No fines concrete been placed and compacted within 1 hour of mixing? | PASS,FAIL,N/A
button | acfa8776-c360-580a-9fc7-a04ee9bc0b99 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 12d9a723-13c0-5581-9c7e-787148fad716 |  | button | SURVEILLANCE - Signature by IR | Yes,No
button | 25a5e5ac-d4f8-5512-83ed-220e199cfdee |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
button | a13faca8-a668-5934-98d4-b25fff716426 |  | button | • Is the subsurface drainage pipe or the geocomposite invert level not exceeding 25 mm from the specified level and not more than 50 mm from the specified line. With changes of grade not at a rate exceeding 10 mm in any 3 m length. | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
button | 1fd49f99-b426-55c8-a232-8fafcc4096b6 |  | button | • Relevant permits have been signed and approved. | PASS,FAIL,N/A
button | 8234e2f8-01fd-5709-b39f-1dff56e4b02e |  | button | • Extents and levels correct to relevant drawings | PASS,FAIL,N/A
button | ff1342d0-f40d-5a41-b857-d37b055557a8 |  | button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | PASS,FAIL,N/A
button | f5587c13-3fa5-527b-875c-a0b1f5d78ce3 |  | button | • Has the trench been excavated to allow 300mm between top of capping and top of subsoil pipe? | PASS,FAIL,N/A
button | 52372511-808e-5cb9-b07f-a26a3771d8cd |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | d16aec0b-4d33-5736-bff3-edaa1c86c5bc |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Subsurface drainage materials and installation
checkpoint-status |  |  | checkpoint | • Attach As Built Report
checkpoint-status |  |  | checkpoint | • Has the Pipe Class and size been confirmed as per latest IFC drawings drawings and project Specs?
button | 2402cbb4-385e-5679-ae87-0b34f2bda905 |  | button | • Has the slotted pipe been placed centrally in the trench? | PASS,FAIL,N/A
button | e327c4a0-fc88-53cc-bcb2-b42ef2f9719f |  | button | • Have plastic pipes been kept away from sunlight and undamaged during delivery and installation? | PASS,FAIL,N/A
button | 8a05c26f-1f8d-596f-898b-53d4775a0aab |  | button | • Is the subsurface drainage pipe invert level not exceeding 25 mm from the specified level and not more than 50 mm from the specified line. With changes of grade not at a rate exceeding 10 mm in any 3 m length. | PASS,FAIL,N/A
button | b4639eb7-2dbc-5c5d-800b-d58716b1e363 |  | button | • Is the pipe grade not flatter than 1m in 250m? | PASS,FAIL,N/A
button | 46caa72f-2ea1-5224-a656-d52d49a07153 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 5d94ace8-8927-5738-bae5-5c9f55a2b4a3 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has the outer covering of the subsurface drain been covered in a geotextile surround if specified?
button | 774cb87d-2458-5281-9ae8-afd2911b6c45 |  | button | • Has the geotextile been placed without punctures or tears? | PASS,FAIL,N/A
button | 92ad0e4b-0be6-5a2c-8f6a-f4cd36f614f5 |  | button | • In expansive clays does the geotextile material extend to directly below the kerb line? | PASS,FAIL,N/A
button | 494c63a3-a063-576f-84e1-81a283e2c4fa |  | button | • Is the Geotextile material supplied and installed as per latest IFC drawings and project specifications? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Has material been placed in <300mm layers and compacted with minimal disturbance to pipe, geotextile and trench walls?
button | 985597ec-3929-59e6-850e-6658ba2c9ad4 |  | button | • Has no fines concrete ratios and specifications applied as per Table 702.051 and VR702.05(e) | PASS,FAIL,N/A
button | 2621568d-d782-57c7-af3c-9dd5c57d598d |  | button | • Has crushed rock/concrete ratios and specifications applied as per Table 702.052 and VR702.05(d) | PASS,FAIL,N/A
button | 18cc4e05-7c2c-5d5e-b882-e2b70249399a |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 88eab072-67d8-5413-b82b-f4d560eb13d5 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 16098283-9476-5622-be53-4ef551fb35ea |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Have access points installed at intervals of between 100m and 150 m?
checkpoint-status |  |  | checkpoint | • Has the pipe been flushed with water to remove any debris or blockages in the pipe and it’s working correctly with a smooth flow?
checklist-sectioned |  |  | checklist | SYM-ITP-017 - Traffic Signals (Rev A) |  |  |  |  | Yes | SYM-ITP-017 - Traffic Signals (Rev A) | 787b8648-7246-4579-a975-a208044cb52d
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Has the lot been defined and marked up on lot map?
checkpoint-status |  |  | checkpoint | • Has the work area been set out as per IFC drawings?
checkpoint-group |  |  | section | 2.0 Traffic Signals Installation
checkpoint-status |  |  | checkpoint | • Has signalised crossing been constructed in accordance with the IFC Drawings?
button | 8f0fb39f-a45e-568e-a2fa-649644b6dc0b |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | e8f9512e-fa78-5562-9d53-338d3aa5039f |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 8b1ffd89-74df-51a7-a361-b232913e6de0 |  | button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has Signalised crossing passed all commissioning and testing?
button | 3dc305a9-1020-596a-839a-66aa36a5faea |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | ca0b15f5-7164-5ec8-9769-ddc67b18ea9e |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 8606471c-68a2-512a-9f83-4f9d99fdef8f |  | button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • DOT inspection & approval provided?
text | 5870031c-d645-5914-b5e9-affcf98a7fdf |  | textbox | Date:
label | 5ac34f30-a915-5c15-b92e-5138f76138ef |  | note | Signature:
button | 38b052d0-7e48-5834-b176-b2607d7c9009 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 2c67b65b-5b4f-52c9-b71e-9641104a978e |  | button | WITNESS POINT - Signature by IR | Yes,No
button | c2f4cdfc-3e36-573b-b87a-d59978d89bfa |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 Conformance check
checkpoint-status |  |  | checkpoint | • All Test reports and as builts received and reviewed.
checkpoint-status |  |  | checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
checklist-sectioned |  |  | checklist | SYM-ITP-009 - Tactiles (Rev A) |  |  |  |  | Yes | SYM-ITP-009 - Tactiles (Rev A) | 7a890c8f-43a0-4bb3-9ac7-7c088da68d50
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-group |  |  | section | 2.0 Pre-Construction Activities
checkpoint-status |  |  | checkpoint | • Have tactiles/pavers been set-out as per current drawings?
checkpoint-status |  |  | checkpoint | • Is the concrete slab free of any deposits or rubbish, projections/voids?
checkpoint-group |  |  | section | 3.0 Stone TGSI’s (pavers)
checkpoint-status |  |  | checkpoint | • Has mortar been placed using type/method described in specification?
checkpoint-status |  |  | checkpoint | • Does the section require directional or horizontal TGSI’s, or both?
checkpoint-status |  |  | checkpoint | • Have pavers been laid as described in specification, considering specified tolerances?
button | f4950e7c-90cd-597d-9459-9397e1fa169f |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 6be81981-041b-5145-be55-92122ad605c5 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | b500f4aa-7ba5-539b-b33a-4582c7d3c778 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Have joints been sealed as described in specification?
button | 3bac20ff-c28c-53d5-abf4-04e2be417fa1 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 004d3cc2-0066-510e-b527-81c89cbbd6f1 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 Regular Tactiles
checkpoint-status |  |  | checkpoint | • Have tactiles been installed in accordance with manufacturer specifications?
button | 11626abf-5c70-5786-a2cb-9dd78de91683 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 30573403-5249-5c45-93dc-14db13508625 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | e7ed8ff0-ba36-5d57-b3d3-1f0632f841bc |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-003 - Asphalt Placement 1 (Rev A) |  |  |  |  | Yes | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 9000e36f-739e-4a97-804c-ed6d3efbe50f
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | • What is the lot size?
text | f5985580-0535-52d7-8b9d-a1c29aac94d2 |  | textbox | • Lot Size
label | 63e9e229-08db-5229-b093-1ce33e75671b |  | note | • Maximum Lot Size = per days production
checkpoint-status |  |  | checkpoint | • Is the asphalt mix design considered “General” and does it conform with VicRoads Section 407? Has mix design been approved by CYP D&C JV?
button | 3335aa18-43b7-557e-b4dc-483287fc09df |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 39ce453f-458e-523a-9c2d-6e494f8a8366 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has the previous layer passed acceptance criteria?
button | 06de1143-a7b9-5631-894f-e897f16d4de6 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | f18aa0e3-b6be-5d16-abfb-b5f066d2cf88 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • For intermediate and base courses surface to be above 5 degrees Celsius. For wearing course installation, surface to be greater then 10 degrees Celsius. Has the above criteria been met?
button | d095c788-144a-5be4-b8a7-aeff534a10ac |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | e9ddbce3-56c1-55f0-95de-5cdc26102714 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Have the existing pits been raised/lowered to meet the surface level of Asphalt?
checkpoint-group |  |  | section | 2.0 Hot Mix Asphalt Installation
checkpoint-status |  |  | checkpoint | • The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from CYP D&C JV.
button | 2d2aec9b-de0e-5409-ac5c-04ed5acb9845 |  | button | • Approval to proceed? | PASS,FAIL,N/A
button | 0b0336a2-1281-5438-824e-a293df7fec32 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | d8adc6c5-fbbd-514d-a5b9-a5e67b27e6d9 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • All transverse joints shall be offset from layer to layer by at least 2 m.
button | 5aee779e-5c5f-5803-b7b5-b2e36cc14dac |  | button | • Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines. | PASS,FAIL,N/A
button | 10933992-28fb-52a1-8011-a80712c18528 |  | button | • Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane. Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm. | PASS,FAIL,N/A
button | eedb59f0-0598-5f94-8ca4-2e06af1accb3 |  | button | • Has all of the above been completed? | PASS,FAIL,N/A
button | 3d362c5b-1964-53a9-a9da-82ce7902d2ef |  | button | INSPECTION POINT - Signature by CYP D&C JV | Yes,No
button | 10c29420-5373-565f-9a59-4c10957c86ab |  | button | INSPECTION POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
button | 4a9b79b6-f310-528e-bdcc-4d9042186119 |  | button | • Does new Asphalt Layer match the existing pavement surface with chases cut? | PASS,FAIL,N/A
button | 132e82b0-9c04-566f-817c-72a56740faa1 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | dd35cf79-b07b-5aa1-a515-0ac8df75e2d3 |  | button | INSPECTION POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings or specified. Asphalt shall be uniformly compacted Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
button | bb1c5486-5af3-5c6b-aeec-d54b48bbe7a2 |  | button | • Has all of the above been completed? | PASS,FAIL,N/A
button | e2a914e5-4ff6-57ac-b856-1612438ded69 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | ccc8597a-70d1-5e16-b5b5-72f02eed1b42 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 9ed8fd51-5743-5f07-a368-572cd020d3e5 |  | button | INSPECTION POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Completion and Compliance
checkpoint-status |  |  | checkpoint | • Thickness < 50 mm: 94.0% Characteristic Density Ratio
button | 10a4c141-f194-5fe3-b56f-d5307c796dfd |  | button | • Thickness > 50mm: 96.0% Characteristic Density Ratio | PASS,FAIL,N/A
button | 6727df81-558e-5058-9d92-fff28d22139d |  | button | • Has testing been completed and report received? Do results match requirements? | PASS,FAIL,N/A
button | ea5f0d11-1a8e-5345-8bfc-20a494c5d2ba |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 3ec7af79-8001-5b57-b65d-0521fe96e3b1 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 63281928-c337-582f-89a5-380f3ceedfd1 |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements (mean +/- 5mm, standard deviation 8mm)
button | d084dc7c-3e4a-58bc-842f-8ce320d3166a |  | button | • Rectification of surface levels shall not commence until approval to proceed is obtained from the Superintendent. | PASS,FAIL,N/A
button | 4697ca11-d67c-500b-b039-e64951127882 |  | button | • Is finished surface level acceptable and survey conformance report received? Attach Reports. | PASS,FAIL,N/A
button | d6925358-9415-503a-bba3-f006fa962ff0 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | c71926a7-6b98-5d2b-b988-6de974998e4d |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Surface finish - Uniform in appearance, free of dragged areas, cracks, open textured patches, and roller marks.
button | 063723a9-2011-58b8-9f56-e3633319db3b |  | button | • Kerb & Channel - Flush or not more than 5mm above lip of channel | PASS,FAIL,N/A
button | ad51b483-7e70-5fc3-895b-79095b531c0f |  | button | • Shape – For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm, respectively. | PASS,FAIL,N/A
button | 9a6b7b18-da94-5d0e-a188-6dcb412a0c79 |  | button | • Alignment - Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside. | PASS,FAIL,N/A
button | c542e868-6fb8-5356-8fe6-a7cc7d191f6d |  | button | • Width - Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm. | PASS,FAIL,N/A
button | 21d46550-1311-5e18-ab40-b2836a028402 |  | button | • Have the above requirements been met and surface is acceptable? | PASS,FAIL,N/A
checklist-sectioned |  |  | checklist | SYM-ITP-008 - Insitu Concrete Elements (Rev A) |  |  |  |  | Yes | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | aac05857-f42a-406a-ae4b-76c27d08fa45
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-status |  |  | checkpoint | • Is Mix design approved prior to placemen and material properties meet project specification, AS 3600, AS 1379.
text | 50e30571-f2bb-5c0f-91b6-8409ce73ac74 |  | textbox | • Concrete Strength |  |  | MPA
button | 8c14012d-969f-5f13-acac-aff386b25bdf |  | button | REVIEW POINT - Signature by CYP D&C JV | Yes,No
button | ca070233-1bbb-569e-b869-cfb6b4bb2d12 |  | button | REVIEW POINT - Signature by IR | Yes,No
button | d0576df3-36c4-5052-a12b-94c5b5c8630f |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | 9f865fac-6ada-5ded-ab58-145745abe572 |  | textbox | • Wall/Footing Reference
text | 23e655c5-2a24-5166-b17c-e5f4f28449ba |  | textbox | • Zone
text | 202a9765-dadf-5607-babe-3221efa4648a |  | textbox | • Stage
text | bc6048aa-e12b-56eb-a0af-da6cae533dd5 |  | textbox | • Element Description
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
button | 66b28c7b-8b5b-5704-afaf-d08cdc4290f2 |  | button | • Relevant permits have been signed and approved. | PASS,FAIL,N/A
button | dd323ee7-848f-57dc-b23e-58be22a7f34f |  | button | • Extents and levels correct to relevant drawings | PASS,FAIL,N/A
button | fe20e2a9-2a81-5578-a1b9-9c78643f8a72 |  | button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | PASS,FAIL,N/A
text | 30b6b0ca-769f-5b69-81ec-0b44e33fc53a |  | textbox | • Excavation to a total depth of |  |  | mm
button | 963195d0-8983-5224-b76e-60f8ed442a34 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 4222d561-74d1-574c-b04c-b7b2d84858d5 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Insitu concrete Element
checkpoint-status |  |  | checkpoint | • Is the fill and base of the foundation compacted to achieve at least 98% and achieving Geotechnical strength as per the design requirements.
button | d4c61633-e45f-5b1e-b3b7-63faf811a28b |  | button | • Has the surface shall be thoroughly moistened with water and excess surface water removed prior to placing concrete. | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Formwork has been installed correctly and sufficiently braced.
button | 6073c8bf-0f9d-5120-a53f-5ed5944a4d4b |  | button | • Formwork set out has been done as per latest design drawings and specifications | PASS,FAIL,N/A
button | 6a539a0a-05fb-57c8-aa01-e414f5388bed |  | button | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed | PASS,FAIL,N/A
button | 765541ed-f497-5fe2-bf08-b0ada3cff6cd |  | button | • Any Backfill/ Underlay Material as per drawings & specifications | PASS,FAIL,N/A
button | cba6cd89-feed-59cb-89ae-d0eed2b77f86 |  | button | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified | PASS,FAIL,N/A
button | 9012374b-075d-5ff9-8020-4e10a213311f |  | button | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval? | PASS,FAIL,N/A
button | 4022eeb1-4d51-56dc-bcbe-42002b980baa |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 21819c42-f6ea-5a2d-810d-ec14ca8f9405 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
button | cb4d67a5-a280-5002-8f5e-c0bae855e440 |  | button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | PASS,FAIL,N/A
button | 86299675-f567-58b7-b351-f7bb68e6e4ef |  | button | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars | PASS,FAIL,N/A
button | ea5d5f42-f3a8-5d3d-8cc8-411796ac9aa6 |  | button | • Correct concrete cover and chairs on sides, bottom and top Verified | PASS,FAIL,N/A
button | 724bbd5d-afdb-5ba2-b09a-0af65565f57b |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 91cc71d5-f8a8-59f9-9782-3414b03fd3cc |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 81e1a274-1897-5bc9-922d-9751eb15643a |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has steel reinforcement been placed correctly with adequate cover?
button | 9a0673ba-d2b1-54d3-9998-72dec788c0b5 |  | button | • Have tie bars and expansion joints been installed at the correct intervals? | PASS,FAIL,N/A
button | 96621dff-82e1-5a29-abe1-e7976b2deedc |  | button | • Pour area is free of loose debris, oils, water | PASS,FAIL,N/A
button | aab68134-e810-56a0-9baa-5f20d5a024fe |  | button | • Have any services located within the slab been installed, surveyed and pinned down | PASS,FAIL,N/A
button | 89f045b6-f82e-5c00-9a49-a7cb1902e8d6 |  | button | • Concrete Testing Lab Representative will be available during concrete pour | PASS,FAIL,N/A
button | 11efbe9d-c360-5a42-abb7-82c387545c56 |  | button | • CYP D&C JV informed of concrete pour date and start time | PASS,FAIL,N/A
button | cb50562a-6d31-5b25-8a7b-d2cf12dba67a |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | aa51316a-99e5-57dd-82ea-009b3ed4601b |  | button | WITNESS POINT - Signature by IR | Yes,No
button | c8330d2a-8d61-57e8-a969-6e4c055cff81 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials and air temp within 5 to 35 degrees C
button | 381e4431-0614-5836-b985-1b39b4a49cad |  | button | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects. | PASS,FAIL,N/A
button | 06c02005-687d-5cf7-ace9-7b13579edfd9 |  | button | • Has a minimum of one of vibrator used at all times while the concreting is in operation | PASS,FAIL,N/A
button | 8f1be9b3-5427-5ae7-a83f-bbef7fde9ea6 |  | button | • Ensure monitoring forms/cast in items during the pour | PASS,FAIL,N/A
button | ccfccbf4-e9ab-51a9-8b98-f4ac0d719788 |  | button | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy | PASS,FAIL,N/A
button | c3c7e204-78a0-5e5e-a09e-90e4a94deb06 |  | button | • Concrete Dockets Received, Attach last Docket | PASS,FAIL,N/A
text | 1683212e-2d58-5b1a-b90c-8a9d52eb5d7c |  | textbox | • Pour date
text | 87979f08-6fa2-5c88-b81d-019d280d12a4 |  | textbox | • Total pour Concrete quantity |  |  | M3
button | 8a1bed7d-00f4-5582-94cc-a1ca63d6892b |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | f65067a2-4752-5416-86f8-8506e41b2a66 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Was Curing agent applies as per project specifications
button | abb6dc44-3e05-51a2-a721-ca618deeb18a |  | button | • Concrete reached design strength to strip formwork | PASS,FAIL,N/A
button | 5d217394-6cec-58ad-b270-5c26a2036116 |  | button | • Any identified defects after striping rectified | PASS,FAIL,N/A
button | 52c7226e-d0d8-50ee-ac97-fe4398f3ac6f |  | button | • Attach Subcontractor’s QA | PASS,FAIL,N/A
button | 1a3f6292-7a09-5559-9243-cd2a22bd792d |  | button | • Does Backfill material comply with Vicroad specs, Project specs and drawings? | PASS,FAIL,N/A
button | 61afd8a7-43bb-58e4-88d6-853fd226ff40 |  | button | • Were as Built completed? Attach report if applicable | PASS,FAIL,N/A
button | 46ad69f6-95ee-563d-b758-46bf7e653f2e |  | button | • Concrete reached design strength to strip formwork. (Attach test results) | PASS,FAIL,N/A
button | 6f62b234-63a7-5fa6-af4f-02c8fe29eb81 |  | button | • Were expansion joints placed at intervals less than 10m. | PASS,FAIL,N/A
button | 92ad3452-3283-5a05-a6b1-d06973b355b1 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 1165d75c-2c64-58c0-8ea9-bff51a77fa74 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 42968d0b-ee91-52bb-9a25-d8e312c42c06 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
button | 2b85e2e2-c828-5075-bd92-8747c9d306f6 |  | button | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | PASS,FAIL,N/A
button | 10050a1f-7bf9-57c5-a03a-af3856a0f31d |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 74876307-b318-5b09-8305-73f373e5b833 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 451177d1-3efe-557b-ad6a-0aff44de2214 |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | SYM-Proof Roll Record |  |  |  |  | Yes | SYM-Proof Roll Record | bbee9def-c005-4635-8b35-3e323c8d24a3
checkpoint-no-status |  |  | checkpoint | Details
text | fa50faab-eed8-5982-8ecd-eb113a0b4b76 |  | textbox | Lot ID:
text | 5fa62e1a-4915-5ed3-8415-0afa6a2b8834 |  | textbox | Stage/ Zone:
text | cec5b3ad-b9a6-508e-a00e-6d6e8b895d07 |  | textbox | Material Type:
text | 62b1bd6f-cb38-51bd-a9b0-43483e901261 |  | textbox | Plant/ Vehicle:
text | 5db54670-9023-5047-96ea-3b8154270b50 |  | textbox | Date:
text | cabb3314-0002-533b-950c-ccaad18068c3 |  | textbox | Road Name:
text | 8db7e848-0181-5906-acb9-057a1ce2e15b |  | textbox | Zone Reference:
text | 05ca693f-0478-510a-986d-af7c153b10dd |  | textbox | Stage Reference:
text | 40ad35ab-8bb1-56ad-9d9a-e0b9a50689ae |  | textbox | Layer Name:
text | 4c5d2043-5075-5602-bf0c-e2e5877bd7d1 |  | textbox | No. Passes:
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | e3d4e33b-7582-5369-ae90-78362638118f |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | a16a271f-091a-5c42-8b8e-4ec19cf2bc1c |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-027 - Furniture Install |  |  |  |  | Yes | SYM-ITP-027 - Furniture Install | c6b3127a-8deb-4905-bd9a-a62c591ef234
checkpoint-group |  |  | section | 1.0 Furniture Installation
checkpoint-status |  |  | checkpoint | • Have the locations of all footings been clearly marked out
text | 4b67e986-5f3b-54e5-abf4-28b0cc0f8d85 |  | textbox | • Handrail/Balustrade Reference
text | 49752d17-40f9-5e1c-acd7-3fef81382661 |  | textbox | • Zone Reference
text | ed01f84b-441f-54f4-b19d-f93a1c68b87e |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Attach Recent IFC Drawings
checkpoint-status |  |  | checkpoint | • Attach Shop Drawings
checkpoint-status |  |  | checkpoint | • Is all furniture compliant with all drawings, specifications, and standards
button | d6239e58-4d15-5bfc-a7e7-b747eabb8ef6 |  | button | • Have all furniture items been built as per approved shop drawings? | PASS,FAIL,N/A
button | a327c7ea-c6bf-59a4-9309-171604fdc88b |  | button | REVIEW POINT - Signature by IR | Yes,No
button | 2235b28c-ab11-58f9-b2a5-e74e0f310b08 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved.
button | 9762c1d2-71b5-50d3-a6cf-06f1a517455e |  | button | • Extents and levels correct to relevant drawings | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Have all footings been excavated as per drawings and specifications?
checkpoint-status |  |  | checkpoint | • Have all furniture items been installed as per project drawings, specifications, and shop drawings
checkpoint-status |  |  | checkpoint | • Were survey as-builts completed
checkpoint-status |  |  | checkpoint | • Attach survey Report
checklist-sectioned |  |  | checklist | SYM-ITP-001 - Subgrade Preparation (Rev A) |  |  |  |  | Yes | SYM-ITP-001 - Subgrade Preparation (Rev A) | cb206814-12b4-44da-ad93-10120602de86
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • What is the lot size?
text | c9027125-18cb-5418-99e8-73e5436fc488 |  | textbox | • Lot Size |  |  | m2
label | 398c8943-758d-55c1-b352-34134c03d6e4 |  | note | • Maximum lot size = 1 days production or 4000m2
checkpoint-status |  |  | checkpoint | • Has the work area been set out for line and level?
button | a5beee10-b447-55a2-893f-f1803a061a24 |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | bfb648b5-c805-5a43-9cc5-230bb3050916 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has the material being excavated been inspected with category agreed upon by Superintendent?
button | 38f792a1-bf1a-51e4-97ed-47413cca1245 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 4f534ad4-65ec-5a91-8bee-669791da0875 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has the material to be used been approved by CYP D&C JV?
button | 6a0d5942-a88e-5472-8efb-f56e2c47e1af |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 5c687fab-027b-5966-aa1d-058ddbb7dadb |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
checkpoint-status |  |  | checkpoint | • 1A / 1B/ 1C/ 1D / 1E / 1F / 1G / 2A / 2B / 2C / 2D / 2E / 2F / 2G / 3A / 3B / 3C / 4A / 4B / 4C / 5A / 5B / 5D / 6A / 6B
text | cf4a7338-f749-59d5-be00-a77cae391724 |  | textbox | • Stage Reference
button | 32badea1-ddf6-5d1a-bf7c-b6db629f37c3 |  | button | REVIEW POINT - Signature by CYP D&C JV | Yes,No
button | 9f463f7d-25b9-5370-b19a-244a2caaf12f |  | button | REVIEW POINT - Signature by IR | Yes,No
button | 7b8e01be-067f-519b-b002-80bb4798a0f1 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Bulk earthworks - cut
checkpoint-status |  |  | checkpoint | • Has the cut surface been trimmed to an even surface free from lose material?
button | f673e384-6eaf-5c4f-ab05-b0dd846ce4e9 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 5e4e3245-c22b-5034-bb49-327a519c0d7d |  | button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • If groundwater or seepage is encountered, notify the Superintendent and create a course of proposed action. Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
button | 9843b71e-2843-58cc-aadf-63677e63da3a |  | button | • Approval to proceed? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm. Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with approved material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
button | 77df0261-f27f-501a-a739-04a10bfff8ad |  | button | • Has all of the above been completed? | PASS,FAIL,N/A
button | 87fae0a2-98ed-5c70-9125-578759113d0d |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 9eba2653-5218-5fed-8b64-c04c8bf07506 |  | button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Compaction Scale B, CBR and Swell Testing per lot (3 tests per lot). Has the subgrade been adequately compacted achieving a mean value density ratio of 98% Standard?
button | 5823f615-279f-5dca-8700-34606966c6a7 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 2fcafde0-c673-5fbc-9d80-d4dbe6fe7c69 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 2a734ca8-7452-5088-a568-4f0b6c857db1 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Does the layer withstand test rolling without visible deformation or springing?
label | 3d1be044-7aa5-5352-a6a5-970e39158eb8 |  | note | If ‘no’ please see below.
label | dde5d9ad-a52e-5612-9484-75712b4547c0 |  | note | If ‘yes’ please proceed.
button | 769346b5-1920-50e9-b1c2-afd5c9386d50 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 3b32c040-3e51-5f95-b3f7-51060ee052e3 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 72eb1575-4b68-53d0-a50e-1358e8457d0d |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • What quantity of soft, wet or unstable material is present?
text | 3c08b880-6054-5031-b7b9-19f0d0254c17 |  | textbox | • Quantity |  |  | m3
checkpoint-status |  |  | checkpoint | • Has rectification process been submitted to the Superintendent for review?
text | 4a43ef92-2628-5a9c-8996-fd7610a46d81 |  | textbox | • What was the rectification process used?
button | 2e77143d-7bb7-5286-af60-d25987ca71d7 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 8ae709ed-595d-50ea-ba85-8279696d97d8 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Visual inspection to confirm that surface is a smooth, hard, tightly bound surface, free from depressions capable of holding water. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
button | a87fd1ac-ecf7-5097-88ef-5f5e8dd4a880 |  | button | • Has all of the above been completed? | PASS,FAIL,N/A
button | 1b6722b3-e284-5e82-a7ac-8ff82569697b |  | button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | 15e8d29d-283a-5c01-8b9b-7c2a817a0cfa |  | button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Bulk earthworks - fill
checkpoint-status |  |  | checkpoint | • Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
label | 6637207a-3ddb-53e7-af5e-5908396ea4af |  | note | If ‘no’ please see below.
label | 305690df-951c-5187-a4eb-1dc3a9fb6cd7 |  | note | If ‘yes’ please proceed to item 3.2
button | 2d3dcbdf-eef7-5945-9a07-7735bb4208c5 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 3f5d85a5-dd5a-53df-96b7-85886e4077d5 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 0afc729b-aad1-5434-b066-0152b7585acd |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • What quantity of soft, wet or unstable material is present?
text | c90fdf75-dbaa-5187-afb2-800aa0c6461b |  | textbox | • Quantity |  |  | m3
checkpoint-status |  |  | checkpoint | • Has rectification process been submitted to the Superintendent for review?
text | a373d4ea-854b-523b-9ae5-7e83142d04cf |  | textbox | • What was the rectification process used?
button | 562de446-7c53-5779-88a2-f9fe7a0aef0a |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 0cb39bb3-efcb-57dd-af3d-3b8ef4e8d71d |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
checkpoint-status |  |  | checkpoint | • Has fill been placed in maximum 200mm compacted layer thickness?
button | 5b5c06ec-d5f0-588a-99e6-601cd5c7629d |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | f6c7dda9-0ec3-5a3d-b230-8c1150b44ed6 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 537bca54-6f86-58be-b0e0-494c696a4f37 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has the material maintained at optimum moisture content (>80%), with additional water being added if required during compaction?
checkpoint-status |  |  | checkpoint | • Compaction Scale B (6 tests per lot) Has the layer been adequately compacted achieving a mean value density ratio of 98% Standard?
button | 64d2be16-724b-510b-9582-5ac03f8dc943 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 0f5c0b6a-a8ae-5282-9db9-1e0baa984e47 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 43ea0474-e0c9-5578-a24e-1b2863e25f44 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has the material properties testing (CBR / Swell / Grading / PI / LL / Permeability) been undertaken for the first lot of material placement and satisfies the VicRoads requirements as per Table 204.041? If the first lot of each fill satisfies the specified post compaction requirements, every second lot of like material and work will be tested
button | 06f74fe8-49fc-50f3-9def-f106e8a3032d |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | dc4f717e-4a43-58b6-8072-2efc62562689 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Does the layer withstand test rolling without visible deformation or springing?
label | 20b373ed-f5aa-5bfe-821d-f9fbeec032af |  | note | If ‘no’ please see below
label | 9615b316-0942-547f-931e-7cfb7c8a9905 |  | note | If ‘yes’ please proceed to fill construction
button | 5e8b556f-c9de-51f6-8974-1da08de7387b |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 3201b127-c81d-561a-a188-6b5c45a96913 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 8cd2fe94-212e-539c-bc0b-2cc2b9cdef1d |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • What quantity of soft, wet or unstable material is present?
text | 09a3a111-ea89-57a6-af6c-00df951d43c1 |  | textbox | • Quantity |  |  | m3
checkpoint-status |  |  | checkpoint | • Has rectification process been submitted to the Superintendent for review?
text | dbf4096a-3fad-5bff-96b2-845a9b2fccc8 |  | textbox | • What was the rectification process used?
button | 2f0b8172-176b-5073-bcb6-22b489450ed3 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 73192244-3205-5c88-a7b5-0cda2473a1dd |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 Conformance check
checkpoint-status |  |  | checkpoint | • Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | 570ea40f-2907-5973-a12b-66de12259c22 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 8a4c74a5-bea0-51e0-a3e0-21bec413b8d2 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | c03f2188-5c66-50bf-b542-562cce9fe75c |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has the prepared subgrade been surveyed in accordance with and verifying specified requirements? Mean Range: +5mm to -25mm Standard Deviation: Maximum 15mm
button | d415d4e9-baed-514b-89f1-9204d85f213a |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 073cc0dd-f108-55af-bd7c-87e53885f69b |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 75e5ab9a-e4e9-57dd-b06d-db8eac9bb2c1 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • All Test reports received and reviewed.
button | 023141dd-9403-5848-aef6-44bedb6cef3c |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | fb76b289-a984-5342-8b7c-10ec3cd8ddd3 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | b6389069-52b4-5923-a2f3-04883d6fecf1 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
button | cfd3d846-2cfb-52f6-ad85-3558ad8fbd5f |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 4f7182ab-78b7-5c01-a8f7-a716dd04689b |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 1a0df079-5950-5711-baf6-3373fc83531f |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-005 - Insitu Kerb and Channel (Rev A) |  |  |  |  | Yes | SYM-ITP-005 - Insitu Kerb and Channel (Rev A) | cf900e03-730d-487a-89de-e853a70a24da
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | • One lot per days production. To be marked up on lot map.
checkpoint-status |  |  | checkpoint | • Concrete used in kerb extrusion machines shall have a minimum cementitious material content in the finished concrete as follows:
label | 8ef404ce-df88-58b2-b4da-cf279eb68f5c |  | note | ○ A minimum of 320 kg of cementitious material for traffic routes
label | 1c7d737d-56cc-5d57-aaf7-33afdc77c5e0 |  | note | ○ A minimum of 280kg of cementitious material for local streets
button | 291321f5-884a-5e8f-a610-2bc590e5b842 |  | button | • Concrete mix designs approved by CYP D&C JV? | PASS,FAIL,N/A
button | 770ab72f-b91a-5ecb-b1b6-5db9aee560fa |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | d5a71cf4-6cb5-57b5-843b-31cec841138c |  | button | REVIEW POINT - Signature by IR | Yes,No
button | 0cd5d73c-ee34-5df9-af52-d5d94d7dc1e6 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • All works shall be set out in accordance with the drawings and as specified.
button | f7d01c1b-4a85-5798-9ca0-3f488c63a589 |  | button | • The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. | PASS,FAIL,N/A
button | 61176a98-e66b-589d-b307-fbc1b2321861 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 2d09d029-8fec-5807-bf3c-31a3e2ddb9f9 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Construction
checkpoint-status |  |  | checkpoint | • Concrete shall be fed to the machine at a uniform rate. Surfaces shall be free from surface pitting larger than 5 mm diameter.
checkpoint-status |  |  | checkpoint | • Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre. Transitions between different profiles shall be made in accordance with the drawings.
button | 50ac6d83-9d8d-5e2f-84e1-2fd4fe1a7237 |  | button | • Are the profile transitions acceptable? | PASS,FAIL,N/A
button | 8a4afb63-4e3e-52a5-b28e-308ed5873e38 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 827c5840-88e5-51e8-91eb-0f6517e205a9 |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • All edgings shall be rendered and have a steel trowel finish. Visible concrete surfaces to have class 3 finish. Hidden surfaces may have a class 4 finish.
button | 10c2a1c6-9625-5290-9ea6-b9b9650aa8b3 |  | button | • Is the surface finish acceptable? | PASS,FAIL,N/A
button | 1bb1c7da-daf8-5a4b-ab8d-5ef4996910b3 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | d691323c-df96-584a-9ef8-940904cf1af6 |  | button | INSPECTION POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Transverse joints shall be constructed at regular intervals not exceeding 2.5 m. The resultant slot in the edging shall be tooled to a depth of 20 mm to produce a neat groove not less than 5 mm wide on the exposed surfaces.
button | 755e09f0-b789-5e4c-ad10-4e5de20456d3 |  | button | • Expansion joints shall be placed at junctions with bridges and shall be 15 mm wide and filled with cork or bituminous impregnated particle board strip extending for the full width and full depth of the edging. | PASS,FAIL,N/A
button | 21185088-ee86-5a6b-bae6-a303ce030650 |  | button | • Are joints installed and comply with all specifications? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Freshly finished exposed concrete surfaces shall be protected from rain or damage from other sources, until hard set has occurred.
button | c64b2eeb-48a0-5d57-a9d5-ebdf03c91852 |  | button | • All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause. | PASS,FAIL,N/A
button | 07cf42b0-ffee-556d-a392-8a6b95770074 |  | button | • Are finished curbs protected and free from damage? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • For damaged kerb and channel and edgings, a length of at least 1 m shall be removed and the replacement section shall be:
button | b145dc98-4733-5f99-a268-87740344b33d |  | button | (a) Constructed on compacted bedding; | PASS,FAIL,N/A
button | f357d2f5-b0d8-5e8b-87e2-dbdfbee85d4d |  | button | (b) Dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and | PASS,FAIL,N/A
button | 9639a0bf-c02a-5486-9b76-119d2987192d |  | button | (c) Shaped and finished with curved trowels to match the profile and surface finish of adjoining sections | PASS,FAIL,N/A
button | 3635b17e-6004-5293-8468-544d1447892a |  | button | • Is all damage to curbs repaired in line with specifications? | PASS,FAIL,N/A
button | 895beed1-ca95-5858-953b-2a2c96535bc7 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 707dabd8-57e4-5f26-9705-04562b4916c5 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 9aaa94d9-8a32-50d5-8d37-5e6715e7d4b9 |  | button | INSPECTION POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Concrete paving including footpaths, edgings, other surfaces and shared use paths shall be shaped to match existing fixtures, e.g. pit covers, edgings and vehicle crossings, within 5 mm.
button | b24e01d6-1f83-5c17-a229-9c991a82f3bf |  | button | • Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point. | PASS,FAIL,N/A
button | 0a3cf609-c181-510a-84f1-17dd5fa86aee |  | button | REVIEW POINT - Signature by CYP D&C JV | Yes,No
button | 884818dd-1c27-5bd2-858d-2313c4ca40d0 |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
checklist-sectioned |  |  | checklist | SYM-ITP-021 - Precast Concrete Elements (Rev A) |  |  |  |  | Yes | SYM-ITP-021 - Precast Concrete Elements (Rev A) | df234f4a-a8a3-41d7-9a51-b7841b39a202
checkpoint-group |  |  | section | 1.0 Preliminaries, Pre-delivery
checkpoint-status |  |  | checkpoint | • Has the pre-pour check been completed?
button | 54c39bd9-7d74-52f4-8ce1-02e16a1f38b5 |  | button | • Has the ITP been completed supplied? | PASS,FAIL,N/A
button | f4b818dd-5753-5fd6-a7be-9307950b072f |  | button | • Have the concrete test certificates been supplied? | PASS,FAIL,N/A
button | 6e22f4ae-6eb0-5196-a89c-2576cfead9de |  | button | • Has the certificate of compliance been supplied? | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Has the concrete reached its 28-day compressive strength Prior to Transport and not transported before 7 days after casting?
button | 2ce3b1f4-be84-5cf2-bc4d-9b0973e4504c |  | button | • Any defects (Cracks, chips, honeycomb etc) identified. | PASS,FAIL,N/A
checkpoint-status |  |  | checkpoint | • Precast element/s
text | ca01f981-d659-54aa-8014-95ecce1b480e |  | textbox | • Reference/Type/s
text | 16895605-e037-5917-a08e-72ee5ad04fb0 |  | textbox | • Zone
text | bd390594-c49e-5e06-9bf6-c7b109b47f54 |  | textbox | • Stage
checkpoint-group |  |  | section | 2.0 Installation of Precast Element
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
button | 58226fdc-fdea-5613-9264-0c318d57594f |  | button | • Relevant permits have been signed and approved. | PASS,FAIL,N/A
button | c190c5a0-03ed-54b5-8ce3-5d887d0fe46e |  | button | • Extents and levels correct to relevant drawings | PASS,FAIL,N/A
button | 7ccfa398-d998-5d03-bef6-38719926c285 |  | button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | PASS,FAIL,N/A
text | 204004fd-04d3-5a89-bf00-1f8b716c4662 |  | textbox | • Excavation to a total depth of |  |  | mm
button | 826b7c70-be01-54d3-aae4-f662f2560f6f |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 5f807b74-4a2d-5595-9de4-2fea711ad182 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Has survey set out points identified and existing condition of location checked to ensure suitability of install.
button | 9ae12fec-2ead-5371-b4ac-998338e78545 |  | button | • Has the Precast element been constructed in accordance with the IFC drawings? | PASS,FAIL,N/A
button | 0433b9fd-6b53-5d5f-b7b1-162267617229 |  | button | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | PASS,FAIL,N/A
button | 08ea9a40-5b45-5c2e-aa6f-3e24f4c765a7 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 83b8faed-c58d-5451-8e80-6fe419e8f19e |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 5481e7b9-42d4-5f20-9772-b58d9b60d84f |  | button | REVIEW POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-026 - Structural Soil (Rev A) |  |  |  |  | Yes | SYM-ITP-026 - Structural Soil (Rev A) | e93c6ca6-3ce5-4f3c-ad0c-cec62f00b8f3
checkpoint-group |  |  | section | 1.0 Excavation and Setouts
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Have all relevant samples been provided to CYP and approved?
button | 7a4982a2-cd31-55ff-a2cf-d842c9a7c9c7 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 5d059177-5317-5703-b73a-9b2f69b954cd |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Prepare the excavation for the Structural Soil (Setout) as per latest IFC drawings specified dimensions
button | 62dc33fa-a117-5ac6-bf75-c7da22901d8b |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | e9064655-bd7b-5f45-846b-9e71cb78261a |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth.
button | bd6bf44e-18f0-5baf-bb71-8fd6302df8d1 |  | button | • Relevant permits have been signed and approved. | PASS,FAIL,N/A
button | 87c72c1e-08f3-5c1b-ab30-846874be185e |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 5bb26428-aa68-51e1-82e9-b842590f9a33 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | b45135c8-be25-5236-828d-34c136393731 |  | textbox | • Zone Reference
text | 534bbe62-09b9-5106-bfcc-1853b7956a61 |  | textbox | • Stage Reference
checkpoint-group |  |  | section | 2.0 Construction Activities
checkpoint-status |  |  | checkpoint | • Are all pipes extended for the structural Soil install?
button | 99ea99a4-f132-5d2c-b24b-7b549175ecc2 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 47be15ea-e7ad-5524-af83-0e9317c14c95 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | a9c0a165-4691-59a5-a87e-ef24e188315e |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Granular layer installed as per drawings?
button | 0662b7fa-1df5-5526-b830-656a374739b2 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | f30addb1-9ef8-5260-9dee-78a54adf1213 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 73b3c0e6-d587-5c21-a0bd-10e846dca345 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | • Structural Soil fill completed as per specified levels and quantities.
button | 9c738ab5-016e-5113-adf9-ea6d54540a85 |  | button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | 762313d2-f38c-5472-8adc-f059855293b9 |  | button | WITNESS POINT - Signature by IR | Yes,No
button | 8999c146-024c-5139-abc8-d70d818cc5a1 |  | button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint |  |  | signoff | Request Sign Off