## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-001 - Subgrade Preparation (Rev A) | itp |  |  |  | Yes | SYM-ITP-001 - Subgrade Preparation (Rev A) | cb206814-12b4-44da-ad93-10120602de86
section | 1.0 Preliminaries
checkpoint | • What is the lot size?
text | • Lot Size |  |  | m2
label | • Maximum lot size = 1 days production or 4000m2
checkpoint | • Has the work area been set out for line and level?
button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Has the material being excavated been inspected with category agreed upon by Superintendent?
button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Has the material to be used been approved by CYP D&C JV?
button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
checkpoint | • 1A / 1B/ 1C/ 1D / 1E / 1F / 1G / 2A / 2B / 2C / 2D / 2E / 2F / 2G / 3A / 3B / 3C / 4A / 4B / 4C / 5A / 5B / 5D / 6A / 6B
text | • Stage Reference
button | REVIEW POINT - Signature by CYP D&C JV | Yes,No
button | REVIEW POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
section | 2.0 Bulk earthworks - cut
checkpoint | • Has the cut surface been trimmed to an even surface free from lose material?
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • If groundwater or seepage is encountered, notify the Superintendent and create a course of proposed action. Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
button | • Approval to proceed? | PASS,FAIL,N/A
checkpoint | • The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm. Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with approved material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
button | • Has all of the above been completed? | PASS,FAIL,N/A
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Compaction Scale C, CBR and Swell Testing per lot (3 tests per lot). Has the subgrade been adequately compacted achieving a mean value density ratio of 95% Standard?
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Does the layer withstand test rolling without visible deformation or springing?
label | If ‘no’ please see below.
label | If ‘yes’ please proceed.
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • What quantity of soft, wet or unstable material is present?
text | • Quantity |  |  | m3
checkpoint | • Has rectification process been submitted to the Superintendent for review?
text | • What was the rectification process used?
button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Visual inspection to confirm that surface is a smooth, hard, tightly bound surface, free from depressions capable of holding water. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
button | • Has all of the above been completed? | PASS,FAIL,N/A
button | SURVEILLANCE - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
section | 3.0 Bulk earthworks - fill
checkpoint | • Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
label | If ‘no’ please see below.
label | If ‘yes’ please proceed to item 3.2
button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • What quantity of soft, wet or unstable material is present?
text | • Quantity |  |  | m3
checkpoint | • Has rectification process been submitted to the Superintendent for review?
text | • What was the rectification process used?
button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
checkpoint | • Has fill been placed in maximum 200mm compacted layer thickness?
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Has the material maintained at optimum moisture content (>80%), with additional water being added if required during compaction?
checkpoint | • Compaction Scale C (3 tests per lot) Has the layer been adequately compacted achieving a mean value density ratio of 95% Standard?
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Has the material properties testing (CBR / Swell / Grading / PI / LL / Permeability) been undertaken for the first lot of material placement and satisfies the VicRoads requirements as per Table 204.041? If the first lot of each fill satisfies the specified post compaction requirements, every second lot of like material and work will be tested
button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Does the layer withstand test rolling without visible deformation or springing?
label | If ‘no’ please see below
label | If ‘yes’ please proceed to fill construction
button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • What quantity of soft, wet or unstable material is present?
text | • Quantity |  |  | m3
checkpoint | • Has rectification process been submitted to the Superintendent for review?
text | • What was the rectification process used?
button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
section | 4.0 Conformance check
checkpoint | • Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • Has the prepared subgrade been surveyed in accordance with and verifying specified requirements? Mean Range: +5mm to -25mm Standard Deviation: Maximum 15mm
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • All Test reports received and reviewed.
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off
checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
button | WITNESS POINT - Signature by CYP D&C JV | Yes,No
button | WITNESS POINT - Signature by IR | Yes,No
button | HOLD POINT - Signature by Symal Infrastructure | Yes,No
holdpoint | Request Sign Off