## Breakdown
William Sanders (Devonport)
B05
Ground Floor
|  |  | Car Park wall Grid 2-3 | FC - S - STO Poren Products
FC - S - Soffits
FC - S - External Plaster - Nibs & Beams
|  |  | Lobby/Nibs | FC - S - STO Poren Products
FC - S - Soffits
FC - S - External Plaster - Nibs & Beams
Apartments
|  |  | A54 | As Above
|  |  | A55 | As Above
|  | Level 1 |  | As Above
|  |  | Corridor Grid 2-3 | As Above
|  |  | B54 | As Above
|  |  | B55 | As Above
|  |  | B56 | As Above
|  |  | B57 | As Above
B05 - Completion documents-BCO10332878 |  |  |  | CST - S - Completion Documents

## checklist
checklist-flat | FC - S - STO Poren Products
checkpoint-no-status | Type of Product used
dropdown | STO Poren Plaster, STO Poren Panel
checkpoint | Moisture Barrier installed with correct fixings & fixing pattern, checked and acceptable
checkpoint | All joints/penetrations/openings taped as per specs, checked and accurate
checkpoint | All windows installed, with air barrier sealant applied, checked and accurate
checkpoint | All head flashings are installed 3mm past end of window and acceptable
checkpoint | Foot tray, windows flashings and battens installed, checked and acceptable
checkpoint | Appropriate fixings used at correct centres for poren cladding, checked and acceptable
checkpoint | All cladding works completed and acceptable
checkpoint | Mesh Coat to plaster, banding installed, true and flat and acceptable
checkpoint | Topcoat and paint works completed and acceptable
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | FC - S - Soffits
section | Pre-Installation Checks
checkpoint | Wiring in and anchored down for downlights, checked and accurate
checkpoint | Air Conditioning pre wire and pipe completed and acceptable
checkpoint | Fire sprinklers droppers installed and acceptable
section | Soffits works checks
checkpoint | Framing completed, checked and accurate including sheet joins/blocking
checkpoint | Framing centre correct at 600mm centres, including set out to allow all sheets joints to be fully supported
checkpoint | Villaboard installed, stopped and painted, checked and acceptable
checkpoint | Plaster installed as per spec and painted and acceptable
checkpoint | All soffits completed and acceptable
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
FC - S - External Plaster - Nibs & Beams
checkpoint | All nibs/ beams prepared for plaster checked and acceptable
checkpoint | Saddle flashing installed to deck ends, checked and accurate
checkpoint | Falls set to 5 degrees as per plan - 20mm Fall over 200mm checked and accurate
checkpoint | Corner and drip edge flashings installed correctly and acceptable
checkpoint | Plaster installed as per spec and painted, checked and acceptable
checkpoint | All cladding works completed and acceptable
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
CST - S - Completion Documents
checkpoint | PS3s(BCO10332878), warranties, user manuals and any other documents attached
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS