## Breakdown
William Sanders (Devonport)
QA
B05
Ground Level
Apartments
[5 empty] | A54 | Prepopulate | FC - S - Balustrades Installation
[5 empty] | A55 | Prepopulate | FC - S - Balustrades Installation
Level 1
Apartments
[5 empty] | B54 | Prepopulate | FC - S - Balustrades Installation
[5 empty] | B55 | Prepopulate | FC - S - Balustrades Installation
[5 empty] | B56 | Prepopulate | FC - S - Balustrades Installation
[5 empty] | B57 | Prepopulate | FC - S - Balustrades Installation
|  |  | Stairwell |  |  | Prepopulate | POST - S - Handrails
| Completion documents BCO10332878 |  |  |  |  | pre-populate | Completion Documents

## Checklist
checklist | FC - S - Balustrades Installation
section | Pre-Installation Checks
checkpoint | Pre Fit - Studding completed & setout checked
checkpoint | Waterproofing to pre-fit studs completed and acceptable
section | Installation Checks
checkpoint | Balustrade height is compliant
checkpoint | No Gaps Larger than 100 mm
checkpoint | All bolts installed tightened to specification
checkpoint | Endcaps in place and acceptable
checkpoint | Any paint touch ups completed
checkpoint | All Balustrade works completed, reviewed and approved and protection installed
section | Third Party Chemset Post Bolt Pull Testing
checkpoint-no-status | Third Party Inspection Company Name
input | Third Party Inspection Company Name
checkpoint | Pass to confirm understanding of contractual test requirements.
label | Upload a copy of the contractual requirements
checkpoint | Overall Inspection Results
label | Upload all correspondence if rework or additional testing was needed.
checkpoint | Test certificates uploaded (pass when uploaded)
checkpoint | All balustrade inspections completed and results provided to Ryman Foreman
input | Name of Ryman personnel issued with test results.
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
section | Post Lateral Load Test
checkpoint | Pass to confirm understanding of contractual test requirements.
label | Upload a copy of the contractual requirements
checkpoint | Overall Inspection Results
label | Upload all correspondence if rework or additional testing was needed.
checkpoint | Test certificates uploaded (pass when uploaded)
checkpoint | All balustrade inspections completed and results provided to Ryman Foreman
input | Name of Ryman personnel issued with test results.
holdpoint | CLICK AND SEND EMAIL TO RYMAN FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | POST - S - Handrails
checkpoint | Area & substrate acceptable
checkpoint | All handrails install completed correctly within tolerance in respective area
holdpoint | Raise Remedial/ Main Contractor Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | Completion Documents
checkpoint | PS3s(BCO10332878), warranties, user manuals and any other documents attached
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS