## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 | [5 empty] | C | Check | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | M2F |  |  | Lot ID Number: |  |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[7 empty] | E | Examine | QE | Quality Engineer | Lyssa Gatehouse | LG
ITP Number: | SH58-ITP-C-008 Drainage Swales |  |  | Version: | 1 |  | H | Hold Point | QM | QA Manager | Diliban Sengottian | DS
ITP Description: | Swale construction | [5 empty] | I | Inspection | SV | Surveyor | Jim Robbins | JR
Discipline: | Civil | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | John Masters | JM
Specification: | MCIP SH58 East of Moonshine Road to Transmission Gully- Project Specification | [5 empty] | O | Operation | ST | Superintendent | Craig Maloney | CM
[7 empty] | R | Review | PE | Project Engineer | Dehan Erasmus | DE
Drawings: | 80510096-02B-900-C217 Rev 1 | [5 empty] | S | Subcontractor | SE | Site Engineer | Tyrese Dickson | TD
[7 empty] | V | Visual Verification | EM | Environmental Manager | Ross Glubb | RG
Prepared By: (Name) | Tyrese Dickson |  |  | Date: | 2025-08-27 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2025-09-03
Downer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Material
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[7 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
3.1 | Material Compliance - Top soil | Cl 20.1.14 | The Contractor shall allow for the orderly clearing and salvage of material for re-use on site. This includes primarily rocks and topsoil Any topsoil used on site, whether existing or imported shall be tested at a New Zealand Laboratory to ascertain the quality is fit for purpose | ConQA Approval | Prior to work | Document review | H | ER
3.2 | Plant Mix | 80510096-02B-900-C217 Rev 1 | Plant Mix type 7 (Hydroseed) to be used on top of topsoil as per 80510096-02B-900-C217 Rev 1 | Manufacturers specification | Prior to work | Document review | W | SE

## Construction
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Specification/Drawing Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Topsoil stripping | Project Specification Cl15.3.4 | Prior to commencing any clearance, the Contractor shall set up a site meeting with the Engineer to agree on the approach and any further site specific requirements The nominal depth to be stripped varies but shall be confirmed on site, depending on the actual depths available. If required, another method of measurement can be agreed with the Engineer. | CONQA Hold point approval | Prior to to topsoil stripping | Hold Point | H | ER
4.2 | Excavation | 80510096-02B-900-C217 Rev 1 | Slope batter to be 1:3 on the roadside of swale and 1:1max on opposite batter as per 80510096-02B-900-C217 Rev 1 | As-builts | during construction | Witness Point | W | SE
4.3 | Topsoil placement | Project Specification Cl 20.1.14 | The minimum topsoil depths for landscape planting areas (as required by NZTA P39) are as follows: * In grassed areas 100mm *On fill batters (3H: 1V or steeper) 300mm | Photos As-builts | during construction | Witness Point | W | SE
4.4 | Plant Mix | 80510096-02B-900-C217 Rev 1 | Plant mix type 7 on top of topsoil as per drawing | Photos | during construction | Witness Point | W | SE
4.5 | Tolerances | Project Specification Cl15.3.11 | Earthworks shall be constructed to the following tolerance: *Finished level ± 50 mm | As-builts | At completion | Witness Point | W | SV