## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DS2681-SH58-ITP-C-008 Drainage Swales | itp |  |  |  |  | DS2681-SH58-ITP-C-008 Drainage Swales
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Compliance - Top soil
label | Specification/Drawing Reference - Cl 20.1.14
label | Acceptance Criteria - The Contractor shall allow for the orderly clearing and salvage of material for re-use on site. This includes primarily rocks and topsoil
label | ○ Any topsoil used on site, whether existing or imported shall be tested at a New Zealand Laboratory to ascertain the quality is fit for purpose
label | Verifying Document - ConQA Approval
label | Frequency - Prior to work
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Plant Mix
label | Specification/Drawing Reference - 80510096-02B-900-C217 Rev 1
label | Acceptance Criteria - Plant Mix type 7 (Hydroseed) to be used on top of topsoil as per 80510096-02B-900-C217 Rev 1
label | Verifying Document - Manufacturers specification
label | Frequency - Prior to work
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - W
label | Inspection: By - SE
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Topsoil stripping
label | Specification/Drawing Reference - Project Specification Cl15.3.4
label | Acceptance Criteria - Prior to commencing any clearance, the Contractor shall set up a site meeting with the Engineer to agree on the approach and any further site specific requirements
label | ○ The nominal depth to be stripped varies but shall be confirmed on site, depending on the actual depths available. If required, another method of measurement can be agreed with the Engineer.
label | Verifying Document - CONQA Hold point approval
label | Frequency - Prior to to topsoil stripping
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Excavation
label | Specification/Drawing Reference - 80510096-02B-900-C217 Rev 1
label | Acceptance Criteria - Slope batter to be 1:3 on the roadside of swale and 1:1max on opposite batter as per 80510096-02B-900-C217 Rev 1
label | Verifying Document - As-builts
label | Frequency - during construction
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By - SE
checkpoint | 4.3 - Topsoil placement
label | Specification/Drawing Reference - Project Specification Cl 20.1.14
label | Acceptance Criteria - The minimum topsoil depths for landscape planting areas (as required by NZTA P39) are as follows:
label | ○ In grassed areas 100mm
label | ○ On fill batters (3H: 1V or steeper) 300mm
label | Verifying Document - Photos, As-builts
label | Frequency - during construction
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By - SE
checkpoint | 4.4 - Plant Mix
label | Specification/Drawing Reference - 80510096-02B-900-C217 Rev 1
label | Acceptance Criteria - Plant mix type 7 on top of topsoil as per drawing
label | Verifying Document - Photos
label | Frequency - during construction
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By - SE
checkpoint | 4.5 - Tolerances
label | Specification/Drawing Reference - Project Specification Cl15.3.11
label | Acceptance Criteria - Earthworks shall be constructed to the following tolerance:
label | ○ Finished level ± 50 mm
label | Verifying Document - As-builts
label | Frequency - At completion
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By - SV