## ITP-012
|  |  | Inspection and Test Plan - Precast Pit Install | [7 empty] | Document # ITP-005
Revision : 1
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Cornish St, Ballarat |  | Precast Pit Install |  | Name: Jesse Pinge |  |  |  |  | Name:
Job No: |  | 7ABE0340 |  | Specifications: VicRoads Standard Specification Section 705 and Drawings
|  |  |  | Structure / Component: Drainage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Great Ocean Road |  | Date : 04/09/2025 |  |  |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencement | All drawings are the latest revision; drawing register is complete and matches site documentation | Project Drawings, Drawing Register | Visual inspection | Signed ITP | HP | Site Engineer / Contractor | N/A |  | N/A
1.2 | Excavation clearance and bedding |  | Each pit | ≥400 mm clearance; bedding thickness: 80 mm (clay), 150 mm (rock); bedding material complies with Section 701 | Sec705.05(b), Sec701 | Visual inspection | Signed ITP | HP | Site Engineer / Superintendent | N/A |  | N/A
1.3 | Precast pit configuration |  | Each pit | Precast base and riser units match design; knockouts only in required walls; no thinned wall sections | Sec705.04(a), Drawings | Visual inspection | Signed ITP | IP | Site Engineer |  |  | N/A
1.4 | Fibre content verification (FRC pits only) |  | 1 per 5 batches | Fibre content within ±1% of approved mix design | RC 377.01, Sec705.08(d) | Wash-out test | Test Report | TP | Site Engineer
1.5 | Prototype testing (FRC pits only) |  | Initial design or major change | Load test per AS 5100; meets vertical load (210 kN), lateral pressure (≥25 kPa), and reinforcement equivalence (≥150 mm²/m) | AS 5100, Sec705.08(b) | Load test | Test Report | TP | Precast Supplier / Superintendent | N/A |  | N/A
2 | Construction Works
2.1 | Stormwater connection openings |  | Each pit | Openings are saw cut only; epoxy coating on exposed reinforcement; hole diameter within 50 mm of pipe | Sec705.11 | Visual inspection | Signed ITP | WP | Superintendent | N/A |  | N/A
2.2 | Segment alignment and rebating |  | Each pit | Rebated joints ≥15 mm; alignment correct; no horizontal movement | Sec705.09(c) | Visual inspection | Signed ITP | IP | Contractor |  |  | N/A
2.3 | Step irons installation (if >1.0 m deep) |  | Each pit | Installed per AS 1657; positioned to avoid water discharge; epoxy mortared if cast-in | Sec705.12, AS 1657 | Visual inspection | Signed ITP | WP | Superintendent | N/A |  | N/A
2.4 | Surface finish and jointing |  | Each pit | Class 2 surface finish; joints cleaned, wetted, and mortared; cured ≥48 hours before backfill | Sec705.14, Sec705.15 | Visual inspection | Signed ITP | IP | Superintendent | N/A |  | N/A
2.5 | Cover fitting and alignment |  | Each pit | Covers bedded on 5 mm mortar; level and kerb line within ±10 mm of design | Sec705.17 | Visual inspection | Signed ITP | IP | Contractor | N/A |  | N/A
2.6 | Backfilling |  | Each pit | Backfill placed in ≤300 mm layers; compacted to refusal using handheld mechanical equipment | Sec705.18 | Visual inspection | Signed ITP | IP | Contractor | N/A |  | N/A
2.7 | Final inspection and sign-off |  | Completion | All installation elements conform to drawings and specifications; no defects or non-conformities | Sec705 | Visual inspection | Signed ITP | AP | Superintendent |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.