## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-004 - Precast Pit Install | itp |  |  |  |  | ITP-004 - Precast Pit Install Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: All drawings are the latest revision; drawing register is complete and matches site documentation
label | REFERENCE DOCUMENTS: Project Drawings, Drawing Register
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / Contractor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Excavation clearance and bedding
label | FREQUENCY: Each pit
label | ACCEPTANCE CRITERIA: ≥400 mm clearance; bedding thickness: 80 mm (clay), 150 mm (rock); bedding material complies with Section 701
label | REFERENCE DOCUMENTS: Sec705.05(b), Sec701
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Precast pit configuration
label | FREQUENCY: Each pit
label | ACCEPTANCE CRITERIA: Precast base and riser units match design; knockouts only in required walls; no thinned wall sections
label | REFERENCE DOCUMENTS: Sec705.04(a), Drawings
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Fibre content verification (FRC pits only)
label | FREQUENCY: 1 per 5 batches
label | ACCEPTANCE CRITERIA: Fibre content within ±1% of approved mix design
label | REFERENCE DOCUMENTS: RC 377.01, Sec705.08(d)
label | INSPECTION/TEST METHOD: Wash-out test
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Prototype testing (FRC pits only)
label | FREQUENCY: Initial design or major change
label | ACCEPTANCE CRITERIA: Load test per AS 5100; meets vertical load (210 kN), lateral pressure (≥25 kPa), and reinforcement equivalence (≥150 mm²/m)
label | REFERENCE DOCUMENTS: AS 5100, Sec705.08(b)
label | INSPECTION/TEST METHOD: Load test
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Precast Supplier / Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Stormwater connection openings
label | FREQUENCY: Each pit
label | ACCEPTANCE CRITERIA: Openings are saw cut only; epoxy coating on exposed reinforcement; hole diameter within 50 mm of pipe
label | REFERENCE DOCUMENTS: Sec705.11
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
checkpoint | 2.2 - Segment alignment and rebating
label | FREQUENCY: Each pit
label | ACCEPTANCE CRITERIA: Rebated joints ≥15 mm; alignment correct; no horizontal movement
label | REFERENCE DOCUMENTS: Sec705.09(c)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Contractor
date | Date Completed:
checkpoint | 2.3 - Step irons installation (if >1.0 m deep)
label | FREQUENCY: Each pit
label | ACCEPTANCE CRITERIA: Installed per AS 1657; positioned to avoid water discharge; epoxy mortared if cast-in
label | REFERENCE DOCUMENTS: Sec705.12, AS 1657
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
checkpoint | 2.4 - Surface finish and jointing
label | FREQUENCY: Each pit
label | ACCEPTANCE CRITERIA: Class 2 surface finish; joints cleaned, wetted, and mortared; cured ≥48 hours before backfill
label | REFERENCE DOCUMENTS: Sec705.14, Sec705.15
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
checkpoint | 2.5 - Cover fitting and alignment
label | FREQUENCY: Each pit
label | ACCEPTANCE CRITERIA: Covers bedded on 5 mm mortar; level and kerb line within ±10 mm of design
label | REFERENCE DOCUMENTS: Sec705.17
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Contractor
date | Date Completed:
checkpoint | 2.6 - Backfilling
label | FREQUENCY: Each pit
label | ACCEPTANCE CRITERIA: Backfill placed in ≤300 mm layers; compacted to refusal using handheld mechanical equipment
label | REFERENCE DOCUMENTS: Sec705.18
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Contractor
date | Date Completed:
checkpoint | 2.7 - Final inspection and sign-off
label | FREQUENCY: Completion
label | ACCEPTANCE CRITERIA: All installation elements conform to drawings and specifications; no defects or non-conformities
label | REFERENCE DOCUMENTS: Sec705
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Signed ITP
label | AP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP