## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP007 - Unbound Pavements | [5 empty] | ITP007 - Unbound Pavements
section | 1.0 Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | Frequency: Prior to works
label | Acceptance Criteria:
label | • Current revision drawing is being used including the subcontractors copy.
label | • Current Revision to be obtained via Principal’s Representative
label | Reference Documents: ACONEX
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: Current drawings
label | HP*
label | Responsibility: Fulton Hogan
text | Date Completed:
checkpoint | 1.2 - ITP and Construction procedure documentation
label | Frequency: Prior to works
label | Acceptance Criteria: ITP and Construction procedure for unbound pavement material placement to be provided to Principal’s Representative for review.
label | Inspection/ Test Method: Verify
label | Record of conformity: Approved Work procedure report
label | HP
label | Responsibility: Fulton Hogan Principal’s Representative
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Material classification
label | Frequency: Prior to works
label | Acceptance Criteria: Proposed material source information and samples to be submitted to Principal’s Representative.
label | Reference Documents: VicRoads section 812
label | Inspection/ Test Method: Verify
label | Record of conformity: Approved rock mix design report
label | HP
label | Responsibility: Fulton Hogan Principal’s Representative
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Production testing
label | Frequency: Prior to works
label | Acceptance Criteria: Supply of information with respect to production testing.
label | Reference Documents: VicRoads section 812
label | Inspection/ Test Method: Verify
label | Record of conformity: Approved production testing results
label | TP
label | Responsibility: Fulton Hogan Principal’s Representative
text | Date Completed:
checkpoint | 1.5 - Implementation of all measures and controls.
label | Frequency: Prior to works
label | Acceptance Criteria: All necessary measures and controls are being implemented including:
label | • PSP, EMP, TMP, SWMS and WP.
label | Reference Documents:
label | • PSP
label | • EMP
label | • TMP
label | • SWMS
label | • WP
label | Inspection/ Test Method: Visual inspection
label | Record of conformity: Site inspection
label | HP*
label | Responsibility: Fulton Hogan
text | Date Completed:
checkpoint | 1.6 - Plant and Equipment
label | Frequency: Prior to works
label | Acceptance Criteria: Plant and Equipment used in the works are appropriate to achieve specification requirements.
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: Finalised ITP
label | HP*
label | Responsibility: Fulton Hogan
text | Date Completed:
checkpoint | 1.7 - Stockpile material on site
label | Frequency: Prior to works
label | Acceptance Criteria: Material stockpile locations approved by the Principal’s Representative.
label | Reference Documents: Stockpile Map
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: Material receivables checklist (Dockets)
label | AP
label | Responsibility: Fulton Hogan
text | Date Completed:
section | 2.0 Placement of crushed rock base and sub-base
checkpoint | 2.1 - Commencement of construction of the base (Class 3/4/profiling) and sub base (Class 3/4/profiling).
label | Frequency: Each lot
label | Acceptance Criteria:
label | • The underlying layer shall be clean of all foreign matter. All edges of previously placed material must be water conditioned prior to placement continuation.
label | Reference Documents:
label | • VicRoads section 204
label | Inspection/ Test Method: Visual inspection
label | Record of conformity: Site Inspection
label | HP*
label | Responsibility: Fulton Hogan
text | Date Completed:
checkpoint | 2.2 - Placing Crushed rock
label | Frequency: Each lot
label | Acceptance Criteria:
label | • The maximum lot size for surface levelling is to be half the size of the working area.
label | • Surface tolerances per layer is as follows;
label | ○ Class 3/4 Crushed Rock/profiling: +0, -10mm
label | ○ Crushed Rock Working Platform: +0, -10mm
label | • Pavement layer thickness tolerances as follows;
label | ○ Class 3/4 rock/profiling (Base): -10mm. The average thickness over every 100m shall be no less than the specified thickness. Max thickness of any base layer shall not exceed 200mm and be no less than 80mm.
label | ○ Class 3/4 rock/profiling (subbase): -15 mm. Max thickness of any subbase layer shall not exceed 150mm and be no less than 80mm.
label | ○ The combined thickness of subbase and base course shall be no less than the specified thickness by more than 15mm.
label | Reference Documents: VicRoads section 304
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: Survey day and Visual inspection
label | HP*
label | Responsibility: Fulton Hogan
text | Date Completed:
checkpoint | 2.3 - Compaction and Post Compaction Testing
label | Frequency: Each Lot
label | Acceptance Criteria:
label | • Full compaction of each course shall be achieved in all areas including the interfaces between successively placed lanes and sections;
label | • Compaction is achieved whilst material is within desired moisture range.
label | • Compaction to be completed with a 16T smooth roller.
label | • Compaction testing requirements and frequency as per Table 304.082.
label | • Material requirements as per Tables 820.072, 820.041.
label | • Nominated frequency of testing for Compaction, Post-compaction Grading and PI, once per lot (section 304.11).
label | • Result requirements to conform to VicRoads section 304.
label | Reference Documents: VicRoads section 304, 820
label | Inspection/ Test Method: Testing
label | Record of conformity: Test result certificate
label | TP
label | Responsibility: Fulton Hogan
text | Date Completed:
checkpoint | 2.4 - Proof rolling
label | Frequency: Each Lot
label | Acceptance Criteria:
label | • Proof Roll will occur once compaction has been completed, as part of the final sequence of compaction.
label | • Proof Roll to be systematic and in a manner that covers the entire area.
label | • Vibrating Plant travel at speed less than 4km/h and less than 6 km/h for pneumatic rollers;
label | • Rollers operated as close as practicable to unsupported edges.
label | • Contractor shall provide for the Principal's Representative to be present after all test rolling.
label | • Proof rolling of the Crushed Rock Working Platform to be completed with a watercart or smooth drum.
label | Reference Documents: VicRoads section 173
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: Visual inspection and mapping data
label | WP / HP*
label | Responsibility: Fulton Hogan Principal's Representative
text | Date Completed:
checkpoint | 2.5 - Identification and treatment of unsuitable areas.
label | Frequency: Each Lot
label | Acceptance Criteria:
label | • Should any area crushed rock be disturbed or become unstable during proof rolling, the Principal’s Representative should be advised immediately and proof rolling of the area ceased.
label | • Any areas of crushed rock layer that rut, yield or become unstable under the proof rolling must be investigated in the presence of the Principal’s Representative.
label | Reference Documents: Spec cl 3.6.3. & VicRoads Section 204
label | Inspection/ Test Method: Visual Inspection
label | Record of conformity: Site Inspection
label | HP
label | Responsibility: Fulton Hogan Principal's Representative
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Print Name:
text | Position:
text | Date: