## Breakdown
J T Paasi Constraction
QA
B09
Appartments
|  |  |  | 32 | Prepopulate | Exterior Timber Framing
[5 empty] | Prepopulate | RAB
[5 empty] | Prepopulate | Windows, Sliders and Sealants
[5 empty] | Prepopulate | Flashing installation
[5 empty] | Prepopulate | Gutters
[5 empty] | Prepopulate | Nogs
[5 empty] | Prepopulate | Tapes and VaproShield
[5 empty] | Prepopulate | Lintels
[5 empty] | Prepopulate | Timber Framing
[5 empty] | Prepopulate | Internal door installation
[5 empty] | Prepopulate | Fire door installation
[5 empty] | Prepopulate | Insulation
[5 empty] | Prepopulate | Skirting/ Architraves & Trims
|  |  |  | 30 | Prepopulate | Exterior Timber Framing
[5 empty] | Prepopulate | RAB
[5 empty] | Prepopulate | Windows, Sliders and Sealants
[5 empty] | Prepopulate | Flashing installation
[5 empty] | Prepopulate | Gutters
[5 empty] | Prepopulate | Nogs
[5 empty] | Prepopulate | Tapes and VaproShield
[5 empty] | Prepopulate | Lintels
[5 empty] | Prepopulate | Timber Framing
[5 empty] | Prepopulate | Internal door installation
[5 empty] | Prepopulate | Fire door installation
[5 empty] | Prepopulate | Insulation
[5 empty] | Prepopulate | Skirting/ Architraves & Trims
|  |  |  | 28 | Prepopulate | Exterior Timber Framing
[5 empty] | Prepopulate | RAB
[5 empty] | Prepopulate | Windows, Sliders and Sealants
[5 empty] | Prepopulate | Flashing installation
[5 empty] | Prepopulate | Gutters
[5 empty] | Prepopulate | Nogs
[5 empty] | Prepopulate | Tapes and VaproShield
[5 empty] | Prepopulate | Lintels
[5 empty] | Prepopulate | Timber Framing
[5 empty] | Prepopulate | Internal door installation
[5 empty] | Prepopulate | Fire door installation
[5 empty] | Prepopulate | Insulation
[5 empty] | Prepopulate | Skirting/ Architraves & Trims
|  |  |  | 26 | Prepopulate | Exterior Timber Framing
[5 empty] | Prepopulate | RAB
[5 empty] | Prepopulate | Windows, Sliders and Sealants
[5 empty] | Prepopulate | Flashing installation
[5 empty] | Prepopulate | Gutters
[5 empty] | Prepopulate | Nogs
[5 empty] | Prepopulate | Tapes and VaproShield
[5 empty] | Prepopulate | Lintels
[5 empty] | Prepopulate | Timber Framing
[5 empty] | Prepopulate | Internal door installation
[5 empty] | Prepopulate | Fire door installation
[5 empty] | Prepopulate | Insulation
[5 empty] | Prepopulate | Skirting/ Architraves & Trims
|  |  |  | 24 | Prepopulate | Exterior Timber Framing
[5 empty] | Prepopulate | RAB
[5 empty] | Prepopulate | Windows, Sliders and Sealants
[5 empty] | Prepopulate | Flashing installation
[5 empty] | Prepopulate | Gutters
[5 empty] | Prepopulate | Nogs
[5 empty] | Prepopulate | Tapes and VaproShield
[5 empty] | Prepopulate | Lintels
[5 empty] | Prepopulate | Timber Framing
[5 empty] | Prepopulate | Internal door installation
[5 empty] | Prepopulate | Fire door installation
[5 empty] | Prepopulate | Insulation
[5 empty] | Prepopulate | Skirting/ Architraves & Trims

## Checklist
checklist-flat | FC - S - Exterior Timber Framing
checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint | All frames have been installed square, straight and plumb
checkpoint | DPC installed (if required) correctly
checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | FC - S - RAB
checkpoint | Fixing and spacings checked in accordance with manufacturers specs
checkpoint | White MS sealant for air seals between RAB board and concrete horizontal and vertical joints
checkpoint | 3M taping around windows and external corners and vertical joints and horizontal flashing checked
checkpoint | Vaproshield to interfloor installed after vertical taping
checkpoint | Bracing checked and accurate
checkpoint | Penetrations and punctures sealed with flashing tape
checkpoint | Sealing joints over internal and external joints
checkpoint | Battern on RAB Board for cladding fixings
checkpoint | All RAB board installation completed to specification & within tolerance in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | FC - S - Windows, Sliders and Sealants
checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint | Check taping around, before installing the windows and sliders
checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint | Jambs level and straight for finishing lines on the side
checkpoint | Door and window jambs flush to GIB Board
checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint | All joints detailed as per attached Detail Document
checkpoint | All framing completed correctly within tolerance in respective area
checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | FC - S - Flashing installation
checkpoint | Head flashing installed with sealant at windows and doors (STO system)
checkpoint | Rainshield installed between joinery and lintel (brick)
checkpoint | DPC and WANZ bar installed at the bottom of the joinery (see fixing) as per manufacturer's spec
checkpoint | Aluminium window jamb side flashings are installed
checkpoint | All flashing installed at windows and doors to specification & within tolerance in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | FC - S - Gutters
checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint | All frames have been installed square, straight and plumb
checkpoint | DPC installed (if required) correctly
checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Checklist | PRE - S - Nogs
Section | Service Nogs Toilet
checkpoint | Wall Vanity nogs installed
checkpoint | Handrail and Toilet roll holder Nogs installed
Section | Bathroom
checkpoint | Mirror cabinet nogs installed
checkpoint | Wall Vanity nogs installed
checkpoint | Toilet: Handrail nogs Installed
checkpoint | Shower: Handrails nogs (3 areas) installed
checkpoint | Wall Mounted Heater nog installed
checkpoint | Towel rail nogs installed
checkpoint | Shower head nog installed
checkpoint | Shower mixer nog installed
Section | Laundry
checkpoint | Dryer nogs installed
checkpoint | Cupboard nogs installed
Section | Service Nogs General
checkpoint | Nogs / Service Nogs installed correctly as per plan
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | FC - R - Tapes and VaproShield
checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint | Trades QA received, attached, reviewed and approved
holdpoint | Raise remedial / Request Signoff
checkpoint | Tapes/VaproShield works completed and acceptable
checklist-flat | FC - R - Lintels
checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint | Trades QA received, attached, reviewed and approved
holdpoint | Raise remedial / Request Signoff
checkpoint | Lintels completed and acceptable
checklist-flat | ST - S - Timber Framing
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square / Frames are plumb and level
checkpoint | Fixings are correct
checkpoint | Installed in correct level, plumb, correct pitch and braced
checkpoint | Any bracing requirements installed
checkpoint | All framing completed correctly within tolerance in respective area
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | POST - S - Internal door installation
checkpoint | Door Number(s) / Location checked and accurate
checkpoint | Floor clearance - Adequate for proposed floor coverings
checkpoint | Fixings - Consider Jamb/Hinges/Door Packer, all installed & secure (Size & type)
checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
checkpoint | Door opening as required & is plumb
checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | POST - S - Fire door installation
checkpoint | Door Number(s) / Location checked and accurate
checkpoint | Floor clearance - Adequate for proposed floor coverings
checkpoint | Services/Mechanisms & FRR/Acoustic requirements considered & applied (where applicable)
checkpoint | Fixings - Consider Jamb/Hinges, all installed & secure (Size & type)
checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
checkpoint | Door opening as required & is plumb
checkpoint | Door tags installed
checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | PRE - S - Insulation
checkpoint | All materials checked & aligning with consented design & specifications prior to install
checkpoint | Correct product & R value as per specification
checkpoint | All Insulation completed correctly to specification & within tolerance in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | POST - S - Skirting/ Architraves & Trims
checkpoint | Architraves/ skirtings & trims are the correct size and profile
checkpoint | Skirting boards have been properly scribed, sanded, glued and mitred
checkpoint | Architraves/skirtings & trims have been installed with consistent even margins
checkpoint | Skirting/Architraves & trim work completed - specified level of finish achieved
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS