## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-011-CIV-Horizontal Directional Drilling-SEW
ITP Description: |  | Camms Road Horizontal Directional Drilling-SEW
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2022-10-19
ITP created by: |  | Michelle Lim
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | Check list for Camms Road Project only
Inspection & Test Plan - Horizontal Directional Drilling
[9 empty] | Revision: | 0
[9 empty] | Date: | 2022-10-19
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings: MRP-052-C-SME-DRG-64-MPK-CUT-1041 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminary Works-Materials
2.1 | Encasing Pipe | IFC Drawings: MRP-052-C-SME-DRG-64-MPK-CUT-1041 | All pipes must meet project specification DN 450 PE100 WSA PS-207 PN12.5 Reference: Material approval in Teambinder: | Document Review | Prior to commencement | HP | PE/SPE | Material compliance certificate
2.2 | Carrier Pipe | IFC Drawings: MRP-052-C-SME-DRG-64-MPK-CUT-1041 | All pipes must meet project specification DN 280 PE100 WSA PS-207 PN16 Reference: Material approval in Teambinder: | Document Review | Prior to commencement | HP | PE/SPE | Material compliance certificate
2.3 | Grout | IFC Drawings: MRP-052-C-SME-DRG-64-MPK-CUT-1041 | Review and approval of grout specification Reference: Material approval in Teambinder: | Document review | Prior to commencement | HP | PE/SPE | Material compliance certificate
3 | Preliminary Works-Procedures and Documents
3.1 | PE Welders Qualifications |  | PE welders are to be pre-Qualified Reference:Teambinder Hold point release number: | Document review | Prior to commencement | HP | SE/PE | Teambinder approval number
3.2 | Check that current revision drawings are being used | IFC Drawings: MRP-052-C-SME-DRG-64-MPK-CUT-1041 | Drawing revison must be confirmed with the design manager | Document review | Prior to commencement | HP* | SE/PE/SPE | Design drawings.
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set-out | AS 4799-2000 IFC Drawings:MRP-052-C-SME-DRG-64-MPK-CUT-1041 DBYD Asset owners responses and requirements. MTM: L1-INF-PRO-001 | Set out line and level of drilling works. Survey to mark out existing services. Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
4.2 | Pipe welding | IFC Drawings:MRP-052-C-SME-DRG-64-MPK-CUT-1041 | Joints are to be butt welded. Butt Welding records to be supplied. ATTACH: Welding Record | Document review | All Joints | IP | SE/Site Supervisor/Survey | Sign ITP Butt Welding Records
5 | Construction / Installation Activities
5.1 | Drill rig setout | Drill Shot Plan | Location as per current Drill shot plans | Visual | Prior to commencement | SP | SE | This ITP
5.2 | Installation of Pipeline (Trenchless method) | IFC Drawings:MRP-052-C-SME-DRG-64-MPK-CUT-1041 | Drill to be installed as per the survey setout. Bore longs to be supplied. ATTACH: Bore Logs | Document review | During pilot bore | IP | SE/Site Supervisor | Bore logs
5.3 | Mixing of grout | Grout Manufacturer Technical Data Sheet | Mixing and proportioning of grouting to take place as per Technical Data Sheet provided with product. Only whole bags of product shall be used. Grouting shall not commence when temperature is below 5 degrees Celsius or above 35 degrees Celsius Grout mixture should be mixed adequately and free from lumps [FREE TEXT BOX]: Grout Volume Used | Document review/Measure | During grouting process | IP | SE | Sign ITP.
5.4 | Clean surrounding faces and remove excess grout |  | Area free of excess grout and spillage | Visual | Each shaft | WP | SE | Sign ITP
5.5 | Curing | Grout Manufacturer Technical Data Sheet | Curing in accordance with TDS | Document review | All pipe | IP | SE | Sign ITP
5.6 | Auditing | IFC Drawings | Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts. ATTACH: Audit report | Record and Review | Prior to backfill of exit/entry shafts | HP | Nominated Authority (SEW) | Sign ITP Auditing Report
5.7 | Reinstatement | IFC Drawings:MRP-052-C-SME-DRG-64-MPK-CUT-1041 MRWA-W-201 Table 201-A & 201-B | REINSTATEMENT OF BORE SHAFTS SHALL FOLLOW MRWA BACKFILL SPECIFICATION MRWA-W-201 Table 201-A & 201-B; Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified. | Visual | Each shaft | IP | SE/Site Supervisor | Sign ITP
5.8 | Subcontractor ITP | NA | Acceptance and closeout of subcontractor ITP ATTACHED: Completed and Signed Subcontractor ITP | Document review | Each element | HP* | SE/SPE | Subcontractor Signed ITP Completed
6 | Post-construction / Post-installation Activities
6.1 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
6.2 | As-built Survey | IFC Drawings:MRP-052-C-SME-DRG-64-MPK-CUT-1041 | Survey as built report to be compiled. Borelog obtained from subcontractor Autocad and PDF reports are to be supplied. ATTACH: Survey As-Built Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | Survey As Report
6.3 | Red-line / As-constructed IFC Drawings | MRPA Quality Management Plan | All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar. | Document Review | Once, after construction of the design package | WP | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /