## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-011-CIV-Horizontal Directional Drilling-SEW | itp |  |  |  |  | ITP-011-CIV-Horizontal Directional Drilling-SEW Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-011-CIV-Horizontal Directional Drilling-SEW
note | ITP Description: Camms Road Horizontal Directional Drilling-SEW
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): CIV
note | Revision Number: 0
note | Revision Date: 19/10/2022
note | ITP created by: Michelle Lim
note | ITP approved for use by: Victor Mira
note | 1.1 - Non Dependent
note | Reference Documents:
note | • IFC Drawings:
note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
section | Preliminary Works-Materials
checkpoint | 2.1 Encasing Pipe
note | REFERENCE:
note | IFC Drawings:
note | MRP-052-C-SME-DRG-64-MPK-CUT-1041
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All pipes must meet project specification
note | • DN 450 PE100 WSA PS-207 PN12.5
textbox | Reference: Material approval in Teambinder:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencement
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Material compliance certificate
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Carrier Pipe
note | REFERENCE:
note | • IFC Drawings:
note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All pipes must meet project specification
note | • DN 280 PE100 WSA PS-207 PN16
textbox | Reference: Material approval in Teambinder:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencement
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Material compliance certificate
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Grout
note | REFERENCE:
note | IFC Drawings:
note | MRP-052-C-SME-DRG-64-MPK-CUT-1041
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Review and approval of grout specification
textbox | Reference: Material approval in Teambinder:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencement
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Material compliance certificate
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminary Works-Procedures and Documents
checkpoint | 3.1 PE Welders Qualifications
note | ACCEPTANCE CRITERIA:
note | • PE welders are to be pre-Qualified
textbox | Reference:Teambinder Hold point release number:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencement
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Teambinder approval number
note | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.2 Check that current revision drawings are being used
note | REFERENCE:
note | • IFC Drawings:
note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Drawing revison must be confirmed with the design manager
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencement
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Design drawings.
note | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set-out
note | REFERENCE:
note | • AS 4799-2000
note | • IFC Drawings:MRP-052-C-SME-DRG-64-MPK-CUT-1041
note | • DBYD Asset owners responses and requirements.
note | • MTM: L1-INF-PRO-001
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Set out line and level of drilling works.
note | • Survey to mark out existing services.
note | • Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Surveyor
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
note | Date Completed:
checkpoint | 4.2 Pipe welding
note | REFERENCE:
note | • IFC Drawings:
note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Joints are to be butt welded.
note | • Butt Welding records to be supplied.
note | • ATTACH: Welding Record
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: All Joints
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor/Survey
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
note | • Sign ITP
note | • Butt Welding Records
note | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Drill rig setout
note | REFERENCE: Drill Shot Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Location as per current Drill shot plans
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencement
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: SP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
note | Date Completed:
checkpoint | 5.2 Installation of Pipeline (Trenchless method)
note | REFERENCE:
note | • IFC Drawings:
note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Drill to be installed as per the survey setout.
note | • Bore longs to be supplied.
note | • ATTACH: Bore Logs
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: During pilot bore
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Bore logs
note | Date Completed:
checkpoint | 5.3 Mixing of grout
note | REFERENCE: Grout Manufacturer Technical Data Sheet
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Mixing and proportioning of grouting to take place as per Technical Data Sheet provided with product.
note | • Only whole bags of product shall be used.
note | • Grouting shall not commence when temperature is below 5 degrees Celsius or above 35 degrees Celsius
note | • Grout mixture should be mixed adequately and free from lumps
textbox | Grout Volume Used
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review/Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: During grouting process
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Sign ITP.
note | Date Completed:
checkpoint | 5.4 Clean surrounding faces and remove excess grout
note | ACCEPTANCE CRITERIA: Area free of excess grout and spillage
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each shaft
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: WP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Sign ITP
note | Date Completed:
checkpoint | 5.5 Curing
note | REFERENCE: Grout Manufacturer Technical Data Sheet
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Curing in accordance with TDS
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: All pipe
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Sign ITP
note | Date Completed:
checkpoint | 5.6 Auditing
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
note | • ATTACH: Audit report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Record and Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to backfill of exit/entry shafts
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority (SEW)
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
note | • Sign ITP
note | • Auditing Report
note | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.7 Reinstatement
note | REFERENCE:
note | • IFC Drawings:
note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
note | • MRWA-W-201 Table 201-A & 201-B
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • REINSTATEMENT OF BORE SHAFTS SHALL FOLLOW MRWA BACKFILL SPECIFICATION MRWA-W-201 Table 201-A & 201-B;
note | • Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each shaft
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Sign ITP
note | Date Completed:
checkpoint | 5.8 Subcontractor ITP
note | REFERENCE: N/A
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Acceptance and closeout of subcontractor ITP
note | • ATTACHED: Completed and Signed Subcontractor ITP
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
note | • Subcontractor Signed ITP
note | • Completed
note | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
note | Date Completed:
checkpoint | 6.2 As-built Survey
note | REFERENCE:
note | • IFC Drawings:
note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Survey as built report to be compiled.
note | • Borelog obtained from subcontractor
note | • Autocad and PDF reports are to be supplied.
note | • ATTACH: Survey As-Built Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Surveyor
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Survey As Report
note | Date Completed:
checkpoint | 6.3 Red-line / As-constructed IFC Drawings
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, after construction of the design package
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: WP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
note | Date Completed:
checkpoint | Metropolitan Roads Program Alliance Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP