## PROJECT STRUCTURE
Folder Structure |  |  |  | Checklists
FLAT BUSH SCHOOL
EXTERIOR
SITE WORKS
|  |  | UNDERGROUND SERVICES | UNDERGROUND SERVICES
INTERIOR
|  |  | CONTAINMENT | CONTAINMENT
|  |  | FIRST FIX | FIRST FIX
|  |  | SECOND FIX | SECOND FIX
|  | DISTRIBUTION | EXISTING MSB | MAIN SWITCHBOARD
COMMISSIONING - MAIN SWITCHBOARD
|  |  | NEW CLASSROOM DB | DISTRIBUTION BOARD
COMMISSIONING - DISTRIBUTION BOARD
BONDING
|  |  | STRUCTURAL BONDING | BUILDING STRUCTURAL BONDING

## CHECKPOINTS
TYPE | NAME
CHECKLIST | SITE WORKS - UNDERGROUND SERVICES
CHECKPOINT | CORRECT QUANTITIES OF PIT INSTALLED AS PER UPDATED ELECTRICAL DRAWINGS
CHECKPOINT | CORRECT QUANTITIES OF DUCTING INSTALLED AS PER UPDATED ELECTRICAL DRAWINGS
CHECKPOINT | DUCTING INSTALLED BETWEEN MAIN EARTHING PEGS
CHECKPOINT | DUCTING INSTALLED TO BOLLARD LIGHTS.
CHECKPOINT | COMMS DUCT INSTALLED TO LIGHT POLE FOR CCTV IN CARPARK GRID BF
CHECKPOINT | COMMS DUCT INSTALLED TO LIGHT POLE FOR CCTV IN CARPARK GRID AA
CHECKPOINT | MAG SLAB AND DANGER TAPE INSTALLED ABOVE POWER DUCTING AND MEETS SPECIFICATION
CHECKPOINT | COMMS DUCTING INSTALLED INCLUDING DANGER TAPE
CHECKPOINT | DRAW TAPE INSTALLED AS REQUIRED
CHECKPOINT | SUFFICIENT FINES/SAP 7 IS LAID OVER DUCTING AND MEETS SPECIFICATION
CHECKPOINT | UNDERGROUND PITS INSTALLED, LEVELLED AND DUCTING IS SEALED
CHECKPOINT | NEW MAINS CABLING INSTALLED
CHECKPOINT | RELOCATION OF EXISTING SUBMAINS REROUTED TO NEW MSB
CHECKLIST | CONTAINMENT
CHECKPOINT | WOOD EYE ANCHORS INSTALLED AND CORRECTLY FIXED ONTO TIMBER/CONCRETE WALLS
CHECKPOINT | SUFFICIENT CATENERY WIRE SUPPORTS INSTALLED
CHECKPOINT | CATENRY WIRES INSTALLED AT HIGH LEVEL AND MEETS CLEARENCE FROM OTHER SERVICES
CHECKPOINT | TURNBUCKLES IS TIGHTENED AND CATENERY WIRE IS WELL SECURED
CHECKPOINT | CABLE TRAY INSTALLED AS PER DRAWINGS
CHECKPOINT | CABLE TRAY IS BONDED AND MEETS SPECIFICATION
CHECKPOINT | ALL CONDUIT SECURELY FIXED AND SUPPORTED APPROPIATELY
CHECKPOINT | ALL CONDUIT IS GLUED
CHECKLIST | FIRST FIX
CHECKPOINT | SETOUT + FLUSHBOXES INSTALLED/COMPLETE AS PER ARCHITECTURAL/SC SET OUT
CHECKPOINT | SUB-CIRCUIT CABLES INSTALLED AS PER ELECTRICAL DRAWING
CHECKPOINT | ALL SUBMAINS INSTALLED AND TIED BACK
CHECKPOINT | ALL LIGHTING CABLING INSTALLED
CHECKPOINT | ALL EMERGENCY LIGHTING CABLING INSTALLED
CHECKPOINT | ALL LIGHTING CONTROL CABLING INSTALLED
CHECKPOINT | ALL GENERAL POWER CABLING INSTALLED
CHECKPOINT | ALL HEATING AND VENTIALATION POWER INSTALLED
CHECKPOINT | ALL WINDOW CABLING INSTALLED
CHECKPOINT | ALL EARTHING AND BONDING INSTALLED
CHECKPOINT | ALL CABLES IDENTIFIED AT BOTH ENDS
CHECKPOINT | ALL CABLE ENDS TAPED TOGETHER AT FLUSH BOX
CHECKLIST | SECOND FIX
CHECKPOINT | ALL LIGHT FITTING SOCKET OUTLETS INSTALLED
CHECKPOINT | ALL LIGHT FITTINGS INSTALLED
CHECKPOINT | ALL EMERGENCY LIGHT FITTINGS AND EXIT LIGHTS INSTALLED
CHECKPOINT | ALL LIGHT SWITCHES INSTALLED AND COMPLETED
CHECKPOINT | ALL SENSORS INSTALLED
CHECKPOINT | ALL GENERAL POWER OUTLETS INSTALLED
CHECKPOINT | ALL FANS INSTALLED
CHECKPOINT | ALL HEATERS INSTALLED
CHECKPOINT | ALL MECHANICAL CONTROLS INSTALLED
CHECKPOINT | ALL BONDING INSTALLED
CHECKPOINT | ALL WINDOW SWITCHES INSTALLED
CHECKPOINT | ALL WINDOW ACTUATORS CONNECTED
CHECKPOINT | ALL WINDOW CONTROLS COMPLETED
CHECKPOINT | ALL SEISMIC RESTRAINTS FOR LIGHTING COMPLETE
CHECKPOINT | ALL SEISMIC RESTRAINTS FOR FANS COMPLETE
CHECKPOINT | ALL SESIMIC RESTRAINTS FOR HEATERS COMPLETE
CHECKPOINT | SUB-MAINS POST-LIVENING CHECK COMPLETED AND ADDED TO DROP BOX
CHECKPOINT | AS-BUILT UPDATED AND COMPLETED
CHECKLIST | DISTRIBUTION BOARD - MAIN SWITCHBOARD
CHECKPOINT | MAIN SWITCHBOARD INSTALLED ON TIMBER PLINTH AND SECURED
CHECKPOINT | COMPRESSION GLANDS INSTALLED AND SECURE FOR CABLE ENTRY
CHECKPOINT | NEW MAINS CABLE INSTALLED,LUGGED, TERMINATED.
CHECKPOINT | SUB-MAINS CABLE INSTALLED,LUGGED, TERMINATED
CHECKPOINT | MAIN EARTH CABLE LUGGED,BOLTED AND HAS A MAIN EARTH TAG INSTALLED
CHECKPOINT | MEN LINK IS INSTALLED AND CONFIMED
CHECKPOINT | SUFFICIENT EARTH STAKE INSTALLED AND MAIN EARTH GROUND READING IS GOOD
CHECKPOINT | MAIN EARTH INSPECTION PITS INSTALLED AND AT CORRECT HEIGHT AND COMPLETED
CHECKPOINT | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD.
CHECKPOINT | MAIN SWITCHBOARD IS CLEAN OF ALL DEBRI AND MARKS
CHECKLIST | DISTRIBUTION BOARD - DISTRIBUTION BOARD
CHECKPOINT | DISTRIBUTION BOARD INSTALLATION COMPLETED AND SECURELY MOUNTED
CHECKPOINT | SUB-MAINS CABLE TERMINATED
CHECKPOINT | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD.
CHECKPOINT | SUB-CIRCUITS CABLE TERMINATED
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED
CHECKPOINT | CLEAN OF ALL DEBRI AND MARKS
CHECKLIST | COMMISSIONING - DISTRIBUTION - MAIN SWITCHBOARD
CHECKPOINT | MAIN SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED, INSTALLED AND ADDED TO DROPBOX
CHECKPOINT | MAIN DISTRIBUTION BOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | MAIN SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | MAIN SWITHCBOARD DISTRIBUTION BOARD CHECK SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | MAIN EARTHING TEST SHEET COMPLETED
CHECKPOINT | MAIN EARTH PITS INSTALLED
CHECKPOINT | MEN LINK INSTALLATION CONFIRMED
CHECKPOINT | BOARD FREE FROM DEBRI, NO MARKS, ALL ACCESSORIES INSTALLED
CHECKPOINT | AS-BUILT UPDATED AND COMPLETED
CHECKLIST | COMMISSIONING - DISTRIBUTION BOARD
CHECKPOINT | SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED, INSTALLED INTO DB AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD CHECK SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EARTHING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | TIMECLOCK TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | BOARD FREE FROM DEBRI, NO MARKS, ALL ACCESSORIES INSTALLED
CHECKPOINT | LABELLING COMPLETED ON ALL FIELD OUTLETS, SWITCHES AND ISOLATORS ETC
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | AS-BUILT UPDATED AND COMPLETED
CHECHLIST | STRUCTURAL BONDING
CHECKPOINTS | BUILDING STRUCTURAL BOND INSTALLED AND COMPLETED TO AS/NZS 3000;2007
CHECKPOINTS | RISER CABLE TRAY BONDED AND COMPLETED TO AS/NZS 3000:2007
CHECKPOINTS | SPRINKLER PIPE BONDED AND COMPLETED TO AS/NZS 3000;2007
CHECKPOINTS | PLUMBERS COPPER PIPE BONDED AND COMPLETED TO AS/NZS 3000;2007