## Floor Handover
Sero Apartments QA - Check Sheet
Check list: | Floor Handover
Main Contractor Handover | Inspection Status | Note
CMP Handover Doc Recd | Pass / Fail
CMP Opening Survey Recd | Pass / Fail
Opening position within tolerance | Pass / Fail
Grid Line clearly marked on floor | Pass / Fail
Master RL Provided | Pass / Fail
All timber framing completed and waterproofed | Pass / Fail
Concrete opening completed and waterproofed | Pass / Fail
Has Allwin team checked and accepted against received marked up floor plan? | Pass / Fail

## Aluminum Fins
Sero Apartments QA - Check Sheet
Check list: | Louver Fins
Pre-Installation QA Check | Inspection Status | Note
Handover Recd | Pass / Fail
Have the aluminum fins & Brackets been received without damage? | Pass / Fail
Are the aluminum fins received in the correct color, size, and quantity based on the fabrication and TAG drawings? | Pass / Fail
Installation QA Check | Inspection Status | Note
Has the bracket been installed with correct Anchors bolts? | Pass / Fail
Has The EDPM Seperator been Installed | Pass / Fail
Has the Fin been installed with the correct nuts, bolts and washers per the drawing? | Pass / Fail
Has the bolt been tightened. | Pass / Fail
Have the fins been installed, line, and leveled? | Pass / Fail

## Alum Cladding Flashing
Sero Apartments QA - Check Sheet
Check list: | Alum. Cladding Panel / Flashing
Pre-Installation QA Check | Inspection Status | Note
Have the aluminum panels / flashing been received without damages? | Pass / Fail
Has the aluminum panels / flashing received in the correct color, sizes and quantity based on the fabrication drawing and TAG drawings? | Pass / Fail
Installation QA Check | Inspection Status | Note
Is The Structure Handed Over | Pass / Fail
EPDM membranes/under flashings installed and sealed? | Pass / Fail
Alum cladding installed line and leveled | Pass / Fail
Has the PEF rod installed as per the standard | Pass / Fail
Has the silicon applied without bubbles and sealed neatly | Pass / Fail

## Seismic Frame
Sero Apartments QA - Check Sheet
Check list: | Seismic Frame
Pre-Installation QA Check | Inspection Status | Note
Is the seismic frame the correct size and quantity? | Pass / Fail
Does the seismic frame have the correct gaskets and mohair. | Pass / Fail
Have you got sufficient sleeves | Pass / Fail
Installation QA Check | Inspection Status | Note
Sill Tray bolts sealed to Structure | Pass / Fail
Sill tray packers Installed around all bolts. | Pass / Fail
Sill Tray splices sealed | Pass / Fail
Sill tray end dams fitted and sealed | Pass / Fail
Have all the bolt/ screw heads been sealed | Pass / Fail
Is sill installed level | Pass / Fail
Is Head and Jamb Installed Level | Pass / Fail
Are Head/Jamb fixing heads sealed | Pass / Fail
Are Head/Jamb sleeves fitted and sealed | Pass / Fail
Are Head/Jamb corner splice fitted. | Pass / Fail
Is Head/Jamb face of Mitre sealed | Pass / Fail
Is Head/Sill/Jamb External Backing rod installed | Pass / Fail
Is Head/Sill/Jamb external seal 6mm- 20mm | Pass / Fail
Is Head/Sill/Jamb Internal seal 6mm- 20mm | Pass / Fail
Is Head/Jamb External Rainshield fitted | Pass / Fail
Is internal sill cover fitted | Pass / Fail

## Panels
Sero Apartments QA - Check Sheet
Check list: | CW Panels
Panel Installation QA Check | Inspection Status | Note
Glass and alum panels installed line and leveled | Pass / Fail
Are all beads installed and have wedge rubber | Pass / Fail
Back Of Mullion silicone seal in place | Pass / Fail

## BLU CW Panels (hidden)
Joe's House QA - Check Sheet
Check list: | Balustrade CW Panels
Pre-Installation QA Check | Inspection Status | Note
CW bracket (dead load& windload) installed within tolerance. | Pass / Fail
CW Glass/ Alum panel received in good condition, no glass breakage/missing or aluminium dented or scratched | Pass / Fail | If brokent at site NCR No:
1234
Installation QA Check | Inspection Status | Note
Glass and alum panels installed line and leveled | Pass / Fail
Sleeve been installed and sealed | Pass / Fail
Rockwool installed with Z angle | Pass / Fail
Side steel brackets installed on top of the panel and steel sleeve (horizontal - D016) installed. (Applicable to Level 4 and 5 on Balcony 1,2,3,4) | Pass / Fail
top cover installed and screwed
1.5 Solid alum sheet installed | Pass / Fail
Has the waterproof installed by main contractor. | Pass / Fail | Safari to install waterproof after Allwin installed 1.5 alum sheet
Once waterproof completed and handed over from Safari, Allwin team to continue install 3mm solid alum sheet | Pass / Fail
Pass / Fail

## BAL Panels (hidden)
Joe's House QA - Check Sheet
Check list: | Balcony CW Panel
Pre-Installation QA Check | Inspection Status | Note
Has the frames and jambs been installed | Pass / Fail
Has the bolts and screws been of frame and sill been sealed | Pass / Fail
BAL panel received in good condition, and no glass break /missing or aluminium dented or scratched | Pass / Fail | If brokent at site NCR No:
BAL panel received with all gaskets, beads, sealed well | Pass / Fail
Has the door frame received damage free, all mohair and gasket in place | Pass / Fail
Installation QA Check | Inspection Status | Note
Glass and alum panels installed line and leveled | Pass / Fail
Has the outter bead installed | Pass / Fail
Has the sliding door frame installed | Pass / Fail
Has the door panels been installed as per shop drawing, all wheels working. | Pass / Fail
Has the wedge rubber been installed to the frame | Pass / Fail
Installed BAL Panel glass or alum cladding has any damages/ broken or scratches? | Pass / Fail
Has the Head flashing installed | Pass / Fail
Has the screw cover angle been installed to the sill | Pass / Fail
Has the door stopper/pusher installed | Pass / Fail

## Hinged Door (hidden)
LQ Parnell QA - Check Sheet
Check list: | Doors - Hinged
Pre-Installation QA Check | Inspection Status | Remarks
Has the seismic frame installed | Pass / Fail
Has the bolts and screws head been sealed | Pass / Fail
Door and its accessories been checked against fabrication drawing | Pass / Fail
Door has all mohair and gaskets | Pass / Fail
Hinged Door QA Check | Inspection Status | Remarks
Door frame installed line leveled | Pass / Fail
Door installed with 4 heavy duty hinges | Pass / Fail
Door closing smoothly without scratching floors and head. | Pass / Fail
Door hardware installed and working: (handle and lock) | Pass / Fail
Has the door closure installed and functioning | Pass / Fail

## SF Panels (hidden)
LQ Parnell QA - Check Sheet
Check list: | SF Panel
Pre-Installation QA Check | Inspection Status | Note
Has the frames and jambs been installed | Pass / Fail
Has the bolts and screws of frame and sill been sealed | Pass / Fail
SF panel glass received in good condition, and no break /missing or aluminium dented or scratched | Pass / Fail | If brokent at site NCR No:
SF panel received with all gaskets, beads, sealed well | Pass / Fail
Has the hinged/pivot door frame received damage free, all mohair and gasket in place | Pass / Fail
Installation QA Check | Inspection Status | Note
SF panels installed line and leveled | Pass / Fail
Has the outter bead installed | Pass / Fail
Has the pivot/hinged door frame installed | Pass / Fail
Has the door leaf been installed as per shop drawing | Pass / Fail
Has the wedge rubber been installed to the frame | Pass / Fail
Installed SF Panel (glass or alum cladding) has any damages/ broken or scratch free | Pass / Fail
Has the Head flashing installed | Pass / Fail

## Hinge Door
Sero Apartments QA - Check Sheet
Check list: | Doors - Hinged
Hinged Door QA Check | Inspection Status | Remarks
Are all beads installed and have wedge rubber | Pass / Fail
Door frame installed in-line & leveled | Pass / Fail
Door installed with 3 hinges per side | Pass / Fail
Door closing smoothly without scratching floors and head. | Pass / Fail
Door Handle Installed and Tight
Door Lock installed and working | Pass / Fail
Shoot Bolts Working Correctly | Pass / Fail
Door closure installed and functioning | Pass / Fail

## Sash Window
Sero Apartments QA - Check Sheet
Check list: | Sash Window
Sash Window QA Check | Inspection Status | Remarks
Are all beads installed and have wedge rubber | Pass / Fail
Sash frame installed in-line & leveled | Pass / Fail
Sash Hinges installed | Pass / Fail
Sash Stay Installed with 100mm gap | Pass / Fail
Sash Handle Installed and Tight | Pass / Fail
Sash Lock Working Correctly | Pass / Fail
Pass / Fail
Pass / Fail

## Sliding Window
Sero Apartments QA - Check Sheet
Check list: | Sliding Windows
Sash Window QA Check | Inspection Status | Remarks
Are all beads installed and have wedge rubber | Pass / Fail
Sliding Window frame installed In-line & leveled | Pass / Fail
Fixed Panel wedge gasket installed | Pass / Fail
Wheels installed and adjusted to height | Pass / Fail
Sliding Window Stopper Installed | Pass / Fail
Infill Sliding window stopper installed | Pass / Fail
Handle Installed and Tight | Pass / Fail
Lock Installed and Working | Pass / Fail
Infills installed | Pass / Fail

## Final Handover
Sero Apartments QA - Check Sheet
Check list: | Final Handover
Final Handover | Inspection Status | Remarks
All works Complete | Pass/Fail
List Outstanding Work, if any | Pass/Fail
Handover Sent to CMP | Pass/Fail
Handover confirmation Received from CMP | Pass/Fail

## Document Upload
Sero Apartments QA - Check Sheet
Check list: | Document Upload
Document Upload | Inspection Status | Remarks

## Glass BLU (hidden)
LQ Parnell QA - Check Sheet
Check list: | Glass Balustrade
Pre-Installation QA Check | Inspection Status | Note
Concrete wall water proof applied by Main Contractor | Pass / Fail
Aluminium cladding been installed externally | Pass / Fail
Balustrade brackets been installed and sealed the side. | Pass / Fail
Glass balustrade received in good condition. All bolt holes in correct location | Pass / Fail
Installation QA Check | Inspection Status | Note
Balustrade installed line and leveled | Pass / Fail
Has the top cover been installed | Pass / Fail
Balustrade bracket installed and cover fixed | Pass / Fail
Any balustrade glass broken or scratched. | Pass / Fail | NCR No: