## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Handover
section | Main Contractor Handover
checkpoint | CMP Handover Doc Recd
checkpoint | CMP Opening Survey Recd
checkpoint | Opening position within tolerance
checkpoint | Grid Line clearly marked on floor
checkpoint | Master RL Provided
checkpoint | All timber framing completed and waterproofed
checkpoint | Concrete opening completed and waterproofed
checkpoint | Has Allwin team checked and accepted against received marked up floor plan?
checklist | Louver Fins | [5 empty] | QA - Louver Fins
section | Pre-Installation QA Check
checkpoint | Handover Recd
checkpoint | Have the aluminum fins & Brackets been received without damage?
checkpoint | Are the aluminum fins received in the correct color, size, and quantity based on the fabrication and TAG drawings?
section | Installation QA Check
checkpoint | Has the bracket been installed with correct Anchors bolts?
checkpoint | Has The EDPM Seperator been Installed
checkpoint | Has the Fin been installed with the correct nuts, bolts and washers per the drawing?
checkpoint | Has the bolt been tightened.
checkpoint | Have the fins been installed, line, and leveled?
checklist | Alum. Cladding Panel / Flashing | [5 empty] | QA - Alum. Cladding Panel / Flashing
section | Pre-Installation QA Check
checkpoint | Have the aluminum panels / flashing been received without damages?
checkpoint | Has the aluminum panels / flashing received in the correct color, sizes and quantity based on the fabrication drawing and TAG drawings?
section | Pre-Installation QA Check
checkpoint | Is The Structure Handed Over
checkpoint | EPDM membranes/under flashings installed and sealed?
checkpoint | Alum cladding installed line and leveled
checkpoint | Has the PEF rod installed as per the standard
checkpoint | Has the silicon applied without bubbles and sealed neatly
checklist | Seismic Frame | [5 empty] | QA - Seismic Frame
section | Pre-Installation QA Check
checkpoint | Is the seismic frame the correct size and quantity?
checkpoint | Does the seismic frame have the correct gaskets and mohair.
checkpoint | Have you got sufficient sleeves
section | Installation QA Check
checkpoint | Sill Tray bolts sealed to Structure
checkpoint | Sill tray packers Installed around all bolts.
checkpoint | Sill Tray splices sealed
checkpoint | Sill tray end dams fitted and sealed
checkpoint | Have all the bolt/ screw heads been sealed
checkpoint | Is sill installed level
checkpoint | Is Head and Jamb Installed Level
checkpoint | Are Head/Jamb fixing heads sealed
checkpoint | Are Head/Jamb sleeves fitted and sealed
checkpoint | Are Head/Jamb corner splice fitted.
checkpoint | Is Head/Jamb face of Mitre sealed
checkpoint | Is Head/Sill/Jamb External Backing rod installed
checkpoint | Is Head/Sill/Jamb external seal 6mm- 20mm
checkpoint | Is Head/Sill/Jamb Internal seal 6mm- 20mm
checkpoint | Is Head/Jamb External Rainshield fitted
checkpoint | Is internal sill cover fitted
checklist | CW Panel | [5 empty] | QA - CW Panels
section | Panel Installation QA Check
checkpoint | Glass and alum panels installed line and leveled
checkpoint | Are all beads installed and have wedge rubber
checkpoint | Back Of Mullion silicone seal in place
checklist | Hinge Door | [5 empty] | QA - Doors - Hinged
section | Hinged Door QA Check
checkpoint | Are all beads installed and have wedge rubber
checkpoint | Door frame installed in-line & leveled
checkpoint | Door installed with 3 hinges per side
checkpoint | Door closing smoothly without scratching floors and head.
checkpoint | Door Handle Installed and Tight
checkpoint | Door Lock installed and working
checkpoint | Shoot Bolts Working Correctly
checkpoint | Door closure installed and functioning
checklist | Sash Window | [5 empty] | QA - Sash Window
section | Sash Window QA Check
checkpoint | Are all beads installed and have wedge rubber
checkpoint | Sash frame installed in-line & leveled
checkpoint | Sash Hinges installed
checkpoint | Sash Stay Installed with 100mm gap
checkpoint | Sash Handle Installed and Tight
checkpoint | Sash Lock Working Correctly
checklist | Sliding Window | [5 empty] | QA - Sliding Windows
section | Sash Window QA Check
checkpoint | Are all beads installed and have wedge rubber
checkpoint | Sliding Window frame installed In-line & leveled
checkpoint | Fixed Panel wedge gasket installed
checkpoint | Wheels installed and adjusted to height
checkpoint | Sliding Window Stopper Installed
checkpoint | Infill Sliding window stopper installed
checkpoint | Handle Installed and Tight
checkpoint | Lock Installed and Working
checkpoint | Infills installed
checklist | Final Handover
section | Final Handover
checkpoint | All works Complete
checkpoint | List Outstanding Work, if any
checkpoint | Handover Sent to CMP
checkpoint | Handover confirmation Received from CMP
checklist | Document Upload
section | Document Upload
checkpoint-no-status | Upload Documents