## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-006 - Riprap | itp
section | Riprap
checkpoint | 1 - Site Preparation
label | ACTIVITY TASK - Site Clearance
label | ACCEPTANCE CRITERIA - Site clear of debris and vegetation
label | FREQUENCY - Once
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 2 - Material (1)
label | ACTIVITY TASK - Filter Cloth
label | ACCEPTANCE CRITERIA - Approved filter cloth with class 1 filtration and class C strength class - Bidim A49 or equivalent
label | FREQUENCY - Prior to placing order
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Material (2)
label | ACTIVITY TASK - Rock Boulders criteria
label | ACCEPTANCE CRITERIA - According to WDC Physical work Section E.6. Rip Rap Specification Section 2 page 856
label | FREQUENCY - Prior to placing order
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Material (3)
label | ACTIVITY TASK - RIP-RAP grading
label | ACCEPTANCE CRITERIA - According to WDC Physical work Section E.6. Rip Rap Specification Section 3 page 856
label | FREQUENCY - Upon delivery of material
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3 - Initial set out
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - As per drawings and provided design model
label | FREQUENCY - Prior to subgrade preparation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Subgrade Prep (1)
label | ACTIVITY TASK - Trim subgrade to suit
label | ACCEPTANCE CRITERIA - As per drawing and provided design model
label | FREQUENCY - Prior to placing Geotextile
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey – As-built surface
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 4 - Subgrade Prep (2)
label | ACTIVITY TASK - Place Geotextile
label | ACCEPTANCE CRITERIA - As per drawings and specification.
label | FREQUENCY - Prior to placing RIP- RAP material
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Photos
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 5 - RIP-RAP Placement
label | ACTIVITY TASK - Install RIP-RAP stones
label | ACCEPTANCE CRITERIA - According to WDC Physical work Section E.6. Rip Rap Specification Section 4 page 856 with approved machinery.
label | FREQUENCY - During and Upon completion of work
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey As-built topography Photos, Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Maintenance
label | ACTIVITY TASK - Maintain RIP RAP protection until accepted by Engineer
label | ACCEPTANCE CRITERIA - As required
label | FREQUENCY - Upon completion of the works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 7 - As-Built Plans
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - As accepted by the Engineer
label | FREQUENCY - Upon completion of the works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-built plans
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R