## Road Marking
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.01 | Site Requirements
01.01.01 | Construction Pack | Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence | Downer | Construction Pack | Prior to Works | H | PE
01.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
01.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 2 – ENGINEERS HOLD POINTS
2.01 | Engineer Nominated Hold Points (Engineer’s inspections)
02.01.01 | Pavement Marking Inspection | After set-out and prior to installation of signs and pavement markings. | PS - 2.2.16 | Hold Point Release | Min 48h Notice | HP | ENG
SECTION 3 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – ROADMARKING
3.01 | Roadmarking
03.01.01 | Approval of Road Marking Materials | Paint shall comply with NZTA M/7 – Specification for Road Marking Paints | MOTSAM | Certificate | Before Marking | R | SE
SECTION 04 – CONSTRUCTION ACTIVITY – ROADMARKING
4.01 | Roadmarking
04.01.01 | Pavement Marking Inspection | After set-out and prior to installation of signs and pavement markings. | PS - 2.2.16 | Hold Point Release | Min 48h Notice | HP | ENG
04.01.02 | Pavement Marking | The design and location of the markings shall be in accordance with MOTSAM and the details on the Drawings. Markings shown on the Drawings shall have precedence over any MOTSAM details however the Contractor shall advise the Engineer of any ambiguities prior to setting out. | MOTSAM | Site Notes | Before Marking | R | SE
04.01.03 | Surface Prep | The surface to be marked must be swept and cleaned so not to have any dirt, loose chip or detritus sitting on top of it. The surface must be checked and accepted by the Engineer prior to any marking being carried out. | PS - 8.4 | Site Notes | Before Marking | R | SE
04.01.04 | Removal of existing pavement marking | Removal of existing pavement marking shall be carried out in accordance with The New Zealand Road markers Federation Line Removal Guide (http://www.nzrf.co.nz). The method selected shall ensure that old markings are not visible, especially in the wet. | PS - 8.4 | Methodology | Before Works | R | SE