## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Road Marking | itp |  |  |  |  | ITP - Road Marking
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 01.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 01.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 2 – ENGINEERS HOLD POINTS
checkpoint | 02.01.01 - Pavement Marking Inspection
label | Acceptance / Conformance Criteria - After set-out and prior to installation of signs and pavement markings.
label | Standard / Specification - PS - 2.2.16
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 3 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – ROADMARKING
checkpoint | 03.01.01 - Approval of Road Marking Materials
label | Acceptance / Conformance Criteria - Paint shall comply with NZTA M/7 – Specification for Road Marking Paints
label | Standard / Specification - MOTSAM
label | Verifying Document - Certificate
label | Frequency - Before Marking
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | SECTION 04 – CONSTRUCTION ACTIVITY – ROADMARKING
checkpoint | 04.01.01 - Pavement Marking Inspection
label | Acceptance / Conformance Criteria - After set-out and prior to installation of signs and pavement markings.
label | Standard / Specification - PS - 2.2.16
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 04.01.02 - Pavement Marking
label | Acceptance / Conformance Criteria - The design and location of the markings shall be in accordance with MOTSAM and the details on the Drawings. Markings shown on the Drawings shall have precedence over any MOTSAM details however the Contractor shall advise the Engineer of any ambiguities prior to setting out.
label | Standard / Specification - MOTSAM
label | Verifying Document - Site Notes
label | Frequency - Before Marking
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 04.01.03 - Surface Prep
label | Acceptance / Conformance Criteria - The surface to be marked must be swept and cleaned so not to have any dirt, loose chip or detritus sitting on top of it. The surface must be checked and accepted by the Engineer prior to any marking being carried out.
label | Standard / Specification - PS - 8.4
label | Verifying Document - Site Notes
label | Frequency - Before Marking
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 04.01.04 - Removal of existing pavement marking
label | Acceptance / Conformance Criteria - Removal of existing pavement marking shall be carried out in accordance with The New Zealand Road markers Federation Line Removal Guide (http://www.nzrf.co.nz). The method selected shall ensure that old markings are not visible, especially in the wet.
label | Standard / Specification - PS - 8.4
label | Verifying Document - Methodology
label | Frequency - Before Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature