## 03.36
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | 0 | 0 | 0 | "Description" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | Gabion Protection | [13 empty] | 0 | 0 | 0 | "Description" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Gabion Protection
[9 empty] | Logan City Council Blackspots Project | [16 empty] | Doval Project No. |  |  |  |  | 24019 |  |  |  | Inspection & Test Plan
[26 empty] | Client Project No. |  |  |  |  | CE08, CE14, CE09
[9 empty] | Lot Number |  |  | Description |  |  |  | "Description" | [14 empty] | Date Opened
[9 empty] | 0 | 0 | 0 | [19 empty] | Date Started |  |  |  | MRTS03 (July 2021) ITP 03.36 Rev 0 |  |  |  | Gabion Protection
| Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Client/Rep
| 1 |  | Steel-wire gabions shall be manufactured from galvanised, hexagonally woven, steel-wire mesh having a wire diameter not less than 2.7 mm and a mesh opening of 80 mm across the flats of the hexagon. Selvedge wire shall have a diameter not less than 3.4mm and binding wire shall have a diameter not less than 2.2mm. All wire shall comply with AS 2338 and AS 2423. | [12 empty] | Visual | [7 empty] | Check Item
MRTS03 Cl36.2
| 2 |  | Rock shall be sound igneous or metamorphic rock that shall not disintegrate in water or when exposed to the weather. | [12 empty] | Visual | [7 empty] | Check Item
MRTS03 Cl36.2
| 3 |  | Rock used for filling shall be of size not less than 120 mm and not greater than 200 mm. The rock shall be uniformly graded, and not less than 80% by number shall be of size greater than 150 mm. | [12 empty] | Visual | [7 empty] | Check Item
MRTS03 Cl36.2
| 4 |  | Gabion panels and diaphragms shall be selvedged. The selvedge wire shall be woven integrally with the mesh or fastened to the mesh either by binding the edges of the mesh about the selvedge wire or by stainless steel clips, all in accordance with the manufacturer’s recommendations. | [12 empty] | Visual | [7 empty] | Check Item
MRTS03 Cl36..3
| 5 |  | Steel-wire gabion protection shall be constructed in the locations and in accordance with the drawings. | [12 empty] | Visual | [7 empty] | Check Item
MRTS03 Cl36..3
| 6 |  | The areas on which gabions are to be positioned shall be trimmed to the shapes specified within a tolerance of ± 50 mm. Trimmed surfaces shall be free of roots, stumps, brush, rocks and like protrusions. | [12 empty] | Visual | [7 empty] | Check Item
MRTS03 Cl. 36.4
| 7 |  | The gabion shall have a dense, evenly distributed filling with minimum voids, and shall not be significantly distorted in shape | [12 empty] | Visual | [7 empty] | Check Item
MRTS03 Cl. 36.4.3
| 8 |  | Gabions shall be closed as soon as practicable after filling. All lids shall be securely bound to edges and diaphragms in accordance with the manufacturer’s recommendations. | [12 empty] | Visual | [7 empty] | Check Item
MRTS03 Cl. 36.4.4
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| Schedule No. |  |  |  | Description | [15 empty] | QTY |  |  | Unit |  |  | Comments
General Comments
|  | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification | [20 empty] | Project Manaager Verify that the Above has been Constructed according to Specification
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date