## ITP Cover Page
Retaining Wall 4 - Enabing works - Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - TEMP-010 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | TEMP-010
Project Number: |  |  | DN1210 - SP2 |  |  |  |  | ITP Status: |  |  | Draft
ITP Description: |  |  | Retaining Wall 4 Enabling works |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA8287 |  |  |  |  | Drawing Sets: |  |  | Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1RW4 Sheetpile Geometry - Elevation - DN1210-05-DRW-001 REV A.4 Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1RW4 Sheetpile Geometry - Elevation - DN1210-05-DRW-035 REV A.4
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract Specification
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-12 | [7 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Draft for Approval | 2024-12-04 | [7 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler Brown | [5 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)
Note on P9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mohammed Said , as discussed int he meeting yesterday we need to give this a CWP/ITP number - maybe say TEMP-010 i am not sure how you guys want to number the temp works, check with Nick but I would keep the same CWP number as the permanent and just add the word TEMP in front of it

## ITP Master Body
Retaining Wall 4 - Enabing works - Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - TEMP-010 - Rev 1
Item No. | Inspection and Test Point | Standard/Specification/Detail | Acceptance / Conformance Criteria | Test Frequency | Verifying Document/QA Record | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
1.1 | IFC Drawings and Specification | Drawings to be issued by DNZ Temporary Works team - IFC stamped | A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction | Once | N/A | HP | SE
1.2 | Method Statement & JSEA Development | The Downer Standards (TDS) | Prior to construction: document review. | Once | Method Statement & JSEA Completed & signed by site crew | HP | SE
1.3 | Slope Stability | N/A | Geotechnical check on slope stability for a 35t excavator tracking along sheet pile wall alignment. Completed a minimum 2 weeks before commencement of works | Once | Temporary works signoff | HP | SE
1.4 | Permit to Dig | DN-ZH-ST043 Ground Disturbance SP03-ST-3150 | Prior to construction, all services shall be located ahead of construction. Permit in the work package. | Permit issued each week | Permit number …................ | HP | SE
1.5 | Survey Model | N/A | Model Review. | Once | Visual Inspection & measurement Survey Check set out as per design | HP | SE
1.6 | Lift Plan | DG-ZH-ST047 Cranes and Lifting Equipment Standard | Prior to construction. For lifting of sheet piles with Excavators. | Prior to Construction when required | Permit number …................ | HP | SE
1.7 | Hot Works | DG-ZH-ST041 Hot Work Standard | Prior to construction,for welding, gas cutting, grinding etc a Hot work permit shall be in place ahead of construction. Permit in the work package.. | Prior to Construction when required | Permit number …................ | HP | SE
1.8 | Working at Heights | DG-ZH-ST042 Working at Heights Standard | Prior to construction, permit in work package. | Prior to Construction when required | Permit number …................ | HP | SE
1.9 | Assess geotech reports and confirm driveability for sheet piling | WSP Geotech Report | Prior to construction: document review. | Prior to Construction when required | Visual Inspection & discussion with operator on ground resistance profile | HP | SE
2 | Underground utilities | Diversion of underground utilities | Confirm underground utilities have been diverted from the alighment of the sheet piles | Prior to installation | Visual inspection of diverted known services | HP | SE
2.1 | Sheet Piles | NZGS Spec SPERW | Sheet Piles are in good condition, free from rust and debris. Leading edges cut to assist driving 40mm lifting eyes cut in side wall of sheets, lengths as per IFC drawings | Prior to installation | Visual Inspection | I | SE
2.2 | Driving Gates | N/A | Position gates to wall alignment | Prior to installation | Visual Inspection | I | SE
SECTION 2 – CONSTRUCTION ACTIVITIES
2.2 | Pile set out | DWG details to be provided | Before commencing sheet piling operations, survey set out wall alignment based on model. Set out to include offset. | 10m chainage | As-Built | HP | SE
2.3 | Driving Gates | N/A | Position gates to wall alignment | 10m chainage | As-Built | I | SE
2.4 | Install sheet piles | Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1RW4 Sheetpile Geometry - Elevation - DN1210-05-DRW-001 REV A.4 Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1RW4 Sheetpile Geometry - Elevation - DN1210-05-DRW-035 REV A.4 | Sheet piles driven to the required depths / embedment | As required | Written record, sheet length and embedment depth | I | SE
SECTION 3 – AS-BUILTS/REDPEN MARKUP
3.1 | As-Builts | As-Built records and drawings shall accurately record the layout and extent of all the work and locations of sthe installed sheet piles | As-Built records and drawings shall accurately record the layout and extent of all the work and locations of sthe installed sheet piles | PS 16.7.6 | Survey Records/ Redpen markups | HP | SV