## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-000 ITP Retaining Wall 04 Enabling works | itp |  |  |  |  | DN1210-000 ITP Retaining Wall 04 Enabling works Rev 1
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 1.1 - IFC Drawings and Specification
label | Standard/Specification/Detail - Drawings to be issued by DNZ Temporary Works team - IFC stamped
label | Acceptance / Conformance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | Test Frequency - Once
label | Verifying Document/QA Record - N/A
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Method Statement & JSEA Development
label | Standard/Specification/Detail - The Downer Standards (TDS)
label | Acceptance / Conformance Criteria - Prior to construction: document review.
label | Test Frequency - Once
label | Verifying Document/QA Record - Method Statement & JSEA Completed & signed by site crew
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Slope Stability
label | Standard/Specification/Detail - N/A
label | Acceptance / Conformance Criteria - Geotechnical check on slope stability for a 35t excavator tracking along sheet pile wall alignment.
label | ○ Completed a minimum 2 weeks before commencement of works
label | Test Frequency - Once
label | Verifying Document/QA Record - Temporary works signoff
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Permit to Dig
label | Standard/Specification/Detail - DN-ZH-ST043 Ground Disturbance SP03-ST-3150
label | Acceptance / Conformance Criteria - Prior to construction, all services shall be located ahead of construction.
label | ○ Permit in the work package.
label | Test Frequency - Permit issued each week
textbox | Verifying Document/QA Record - Permit number
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Survey Model
label | Standard/Specification/Detail - N/A
label | Acceptance / Conformance Criteria - Model Review.
label | Test Frequency - Once
label | Verifying Document/QA Record - Visual Inspection & measurement Survey Check set out as per design
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Lift Plan
label | Standard/Specification/Detail - DG-ZH-ST047 Cranes and Lifting Equipment Standard
label | Acceptance / Conformance Criteria - Prior to construction. For lifting of sheet piles with Excavators.
label | Test Frequency - Prior to Construction when required
textbox | Verifying Document/QA Record - Permit number
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Hot Works
label | Standard/Specification/Detail - DG-ZH-ST041 Hot Work Standard
label | Acceptance / Conformance Criteria - Prior to construction,for welding, gas cutting, grinding etc a Hot work permit shall be in place ahead of construction.
label | ○ Permit in the work package..
label | Test Frequency - Prior to Construction when required
textbox | Verifying Document/QA Record - Permit number
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Working at Heights
label | Standard/Specification/Detail - DG-ZH-ST042 Working at Heights Standard
label | Acceptance / Conformance Criteria - Prior to construction, permit in work package.
label | Test Frequency - Prior to Construction when required
textbox | Verifying Document/QA Record - Permit number
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Assess geotech reports and confirm driveability for sheet piling
label | Standard/Specification/Detail - WSP Geotech Report
label | Acceptance / Conformance Criteria - Prior to construction: document review.
label | Test Frequency - Prior to Construction when required
label | Verifying Document/QA Record - Visual Inspection & discussion with operator on ground resistance profile
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Underground utilities
label | Standard/Specification/Detail - Diversion of underground utilities
label | Acceptance / Conformance Criteria - Confirm underground utilities have been diverted from the alighment of the sheet piles
label | Test Frequency - Prior to installation
label | Verifying Document/QA Record - Visual inspection of diverted known services
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Sheet Piles
label | Standard/Specification/Detail - NZGS Spec SPERW
label | Acceptance / Conformance Criteria - Sheet Piles are in good condition, free from rust and debris.
label | ○ Leading edges cut to assist driving
label | ○ 40mm lifting eyes cut in side wall of sheets, lengths as per IFC drawings
label | Test Frequency - Prior to installation
label | Verifying Document/QA Record - Visual Inspection
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.2 - Driving Gates
label | Standard/Specification/Detail - N/A
label | Acceptance / Conformance Criteria - Position gates to wall alignment
label | Test Frequency - Prior to installation
label | Verifying Document/QA Record - Visual Inspection
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 2 – CONSTRUCTION ACTIVITIES
checkpoint | 2.2 - Pile set out
label | Standard/Specification/Detail - DWG details to be provided
label | Acceptance / Conformance Criteria - Before commencing sheet piling operations, survey set out wall alignment based on model. Set out to include offset.
label | Test Frequency - 10m chainage
label | Verifying Document/QA Record - As-Built
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Driving Gates
label | Standard/Specification/Detail - N/A
label | Acceptance / Conformance Criteria - Position gates to wall alignment
label | Test Frequency - 10m chainage
label | Verifying Document/QA Record - As-Built
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.4 - Install sheet piles
label | Standard/Specification/Detail - Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1RW4 Sheetpile Geometry - Elevation - DN1210-05-DRW-001 REV A.4
label | ○ Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1RW4 Sheetpile Geometry - Elevation - DN1210-05-DRW-035 REV A.4
label | Acceptance / Conformance Criteria - Sheet piles driven to the required depths / embedment
label | Test Frequency - As required
label | Verifying Document/QA Record - Written record, sheet length and embedment depth
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 3 – AS-BUILTS/REDPEN MARKUP
checkpoint | 3.1 - As-Builts
label | Standard/Specification/Detail - As-Built records and drawings shall accurately record the layout and extent of all the work and locations of sthe installed sheet piles
label | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extent of all the work and locations of sthe installed sheet piles
label | Test Frequency - PS 16.7.6
label | Verifying Document/QA Record - Survey Records/ Redpen markups
label | Verification Activity: Activity - HP
label | Verification Activity: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature