## Master List Templates
Id | Type | Name | Values | Prompting Name
8a4bfb74-04d2-47d1-9d9c-4e0e45c8e71f | checklist | Documents |  | Documents
d27e664b-b8db-4dae-8ce3-cc3995597fdf | section | Details
9483f8e0-de31-4f34-b59b-8778c5e33994 | checkpoint | Document attached
71311430-12af-4de5-b2e1-320343a3d7c5 | checklist | Test ITP | itp | Test ITP
20380797-825e-43d5-b636-1e28953acadd | section | Preliminary Works
107e3d9c-f945-48ad-a893-382139576ad3 | checkpoint | 3.1 Pre-construction Photos
955645e1-125c-52ac-a36d-9f7aaf64fd68 | note | Inspection Point: Quality Control Activity - Photos of worksite including vehicle access points.
de815be8-ff5b-5bbf-8fcf-b6a74f875d15 | note | ○ Photos of any existing defects/damage.
f629ba35-c6c9-5e84-afb6-f12afe19ba50 | note | Acceptance Criteria - Coverage of whole site
b343e756-6236-534e-a04c-adde741f9cf9 | note | Verifying Document - Photos saved
487d2c77-26c6-574d-9f8c-69197b900e60 | note | Reference: Contract Specs/Standards - D1.4
aa7dcc23-975c-5d3e-90f1-e46ecef13a8e | note | Inspection Point/Signature & Date - PM
441f8f47-9e59-4e93-af48-52ea9db74b4f | checkpoint | 3.2 Verify Construction Drawings
5979cb19-48d2-5a0f-8a4a-18a2495e019b | note | Inspection Point: Quality Control Activity - Verify Construction Drawings that are in the site folder are the latest revision.
77adfc3c-637c-5532-a2de-de99b4eb0801 | note | Acceptance Criteria - Latest drawings approved
2e7272cf-1b67-5992-8aea-1c720473b1e1 | note | Verifying Document - Drawings Register
91384230-7de8-55b8-b9f0-cf3094b4e632 | note | Reference: Contract Specs/Standards -
53f92b21-b0f6-50b0-9a66-65c339b74caa | note | Inspection Point/Signature & Date - PM
92a4d361-6a90-4261-aacc-b17a70c5ba02 | checkpoint | 3.3 Road Authority Notifications
a5905a4b-3c67-5ea9-9f5c-3f49ad93a559 | note | Inspection Point: Quality Control Activity - Corridor access Permit.
0158a33e-7ce3-58a8-babd-2c00a85ada9b | note | ○ Block by block Temporary Traffic Management Plans.
c980e384-1324-5a31-ad80-c5f42c7f2909 | note | Acceptance Criteria - Permit & Traffic Plan approved
670802ca-5daf-518d-ba40-b11f61b8bba8 | note | Verifying Document - Work Access Permit & TMP
ae04fd1d-8285-5e71-9dc0-6c451b22a24a | note | Reference: Contract Specs/Standards - C1.09, D1.4
afbe1801-0461-5ff9-9968-d71d709c4667 | note | Inspection Point/Signature & Date - PM
d39f31d1-9f41-49b3-8e2e-f1d32ae48a60 | checkpoint | 3.4 Management Plan
dacc70c9-2410-5db2-bd45-66d975547e52 | note | Inspection Point: Quality Control Activity - H&S Plan
c98cf114-7fba-5cd7-9f75-05f14d1dc0c4 | note | ○ Environmental Plan
ff8ca60d-7b07-570e-837e-2ea6f5924d22 | note | ○ Quality Assurances
6ad36c2d-187f-596a-87f1-b024ccfeeffd | note | Acceptance Criteria - Plans & Safety Measures in place
d5f70aa4-3aed-5da0-b07e-f5410907778d | note | Verifying Document - H&S Plan, Method Statement
79d6f9d4-a271-5202-907c-58e7835bcb83 | note | Reference: Contract Specs/Standards - D1.3
7f636cf1-81e6-5b8d-8b3a-e415c151f5d7 | note | Inspection Point/Signature & Date - PM, CR
5d595464-2779-423b-add8-0d8127f9cada | checkpoint | 3.5 Public Notification
3a84e0b1-0335-5dc4-bb53-a8236469f1e8 | note | Inspection Point: Quality Control Activity - Notice of works to properties in the construction zone in each block
111ac031-f06c-52e2-8d36-657040eef63d | note | ○ Notification to Rubbish collection contractor.
6425c7b3-a4a7-5fc9-b4d2-348fb03ae6aa | note | ○ Project Signage
1fb132d3-92db-5038-aa91-124209dd7f89 | note | Acceptance Criteria - 48 hours prior notification
6a28c857-a4f5-59ec-8a55-c083caf0c3a7 | note | Verifying Document - Letter to residents
c926fb82-add6-5d96-9893-e1996f955a14 | note | Reference: Contract Specs/Standards - D1.10
bdbcb526-3a1e-5e5d-86ef-0a808ab8369e | note | Inspection Point/Signature & Date - PM
83d17dff-2396-439e-955c-8f1f727f65ed | checkpoint | 3.6 Shutdown/Isolation
6ea865c2-ca78-5854-8fa3-2264bf699993 | note | Inspection Point: Quality Control Activity - Shutdown/Isolation process verified in each block closure
1555c1d5-29de-5a42-a7d4-8b3739287984 | note | Acceptance Criteria - Shutdown process verified
cd7f89f3-8fdf-5085-8c83-7bb9094c8b0a | note | Verifying Document - Notification letters
ef26b893-83e8-5557-854d-c80eb7263938 | note | Reference: Contract Specs/Standards - C1.16, D2.7.8
28d7be85-39af-58e3-9302-9376a974da67 | note | Inspection Point/Signature & Date - PS
d167c212-b415-420c-a15c-45c677294de6 | checkpoint | 3.7 Construction Set Out
742868c8-23f0-5452-9b92-ba186649d8d7 | note | Inspection Point: Quality Control Activity - Correctly mark out the position of the new pipelines for construction.
9e97b2cc-ba1a-5815-b8f9-fbfc1eb1d305 | note | Acceptance Criteria - Construction Plans checked
5b2e22e1-e5ff-5dc0-99bf-61f23b16df05 | note | Verifying Document - Construction Plans
62386f7d-45bf-5fb2-8ee5-5645b5fb6848 | note | Reference: Contract Specs/Standards - D2.7.1
d58502cb-242d-55dc-b860-3551207f6eba | note | Inspection Point/Signature & Date - PS, CR
a5600e25-383f-46d4-8512-0c264c1e449f | checkpoint | 3.8 Pre-Excavation Permits
dae1eccc-c23e-53c5-a82d-0efd94bccfeb | note | Inspection Point: Quality Control Activity - Permit to excavate for the location has been endorsed by an authorised person.
4086823b-a3b0-5514-bed4-f7f9e3b60915 | note | ○ Existing service plans & locates
c1e5fd2a-aef6-51bf-8cd0-bb993a96c4c9 | note | ○ Close approach permits
e9ebe2eb-6bb3-5920-af4f-3e5f51dc6ced | note | ○ Notifiable works
c0184131-3963-58e5-89ee-4c85ee5a746b | note | Acceptance Criteria - Permit to excavate endorsed
ef5bff12-f195-5b6f-aa81-cb8850c90580 | note | Verifying Document - Ground Disturbance Permit
64acb508-1d91-553b-8bd2-2bec3032ca97 | note | Reference: Contract Specs/Standards - D1.7
7835cccc-5334-5c60-a2d5-886aa9e0b519 | note | Inspection Point/Signature & Date - PS
02c8290d-79fe-4b01-a4f8-43e9d4c6e881 | signoff | HOLD POINT
abbb431d-e004-44ec-b738-fab1868140b8 | section | Incoming Goods Inspections
2aa07f2e-4aed-4158-88a0-e6abf1872ee1 | checkpoint | 4.1 Pipe & Fitting Inspections
335e2b85-3765-5d7c-823f-1a30f4f4c2cd | note | Inspection Point: Quality Control Activity - Visual check of materials delivered:
3c2f6b16-25d4-518b-a78c-50cd0381e2b9 | note | ○ Correct Material & dimensions
38ce9bbf-d35b-56d0-9094-6888dbbe0772 | note | ○ Condition & Quantity
e0aca729-1137-5fa6-a9c4-e65d8d4be14e | note | ○ Free of defects – surface abrasion, ovality, not kinked or crushed
c7813b84-576f-505d-b003-53fb30070daf | note | ○ Batch/serial numbers present
e60eb730-8b8d-5bbe-9001-2c575dd38607 | note | Acceptance Criteria - Correct material & no defects
775a2f60-1a0d-5a61-a840-33859f5f5380 | note | Verifying Document - Packing Slips
5523d66d-7eb8-57b7-8130-17f63b83eb86 | note | Reference: Contract Specs/Standards - D2.4,D3.3, D4.3, D5.3, D8.3
4815886f-d85b-584d-a8bf-54bb43596b4d | note | Inspection Point/Signature & Date - PS
18a89c7a-07fc-4278-9ab2-46bbdeed02f3 | checkpoint | 4.2 Pipe & Fitting Storage
736fc6ca-0587-58a7-aa66-1e6006900b05 | note | Inspection Point: Quality Control Activity - Stored as per manufacturers specifications including maximum height limits and safely chocked in place.
88679b02-09b0-5f6d-85d2-86abe8c910f1 | note | ○ All pipes are end capped.
ace5e548-9b68-55f8-acb6-13682245a6d3 | note | ○ No scoring of pipe more than 10% of thickness.
0f1df64d-4495-5578-a941-f201cb9bd702 | note | ○ No damage to epoxy coating on Ductile fittings.
1dbf0fff-4157-5283-af1b-f1fa245cb0fd | note | Acceptance Criteria - Stored as per manufacturer
c2c2afc7-5301-5e5c-ba67-ba552d116bc1 | note | Verifying Document - Manufacturer’s Storage Instructions
99bbba7a-beec-5223-939d-15034191d36d | note | Reference: Contract Specs/Standards -
1dbd7e86-bf3c-5e32-8b08-073e38069992 | note | Inspection Point/Signature & Date - PS, CR
6b2618a5-8d30-4b91-a333-0dfd3ca9cf5f | signoff | HOLD POINT
1f6a3545-531a-431b-8950-db0056c6a96e | section | Construction Inspections
5b9fc0f7-1004-4407-be8c-24b464b7f09e | checkpoint | 5.1 Trench Excavation
02e391fc-3a18-522d-9c19-e2a03e270cfb | note | Inspection Point: Quality Control Activity - Trench width to be sufficient to safely lay the pipe (including shoring if required) and compact the side support of the new pipe. Bedding details below;
a6f490ee-48df-5ce7-ad7c-e1ea3aa3e379 | note | ○ Sufficient room to enable the pipe, joint, bed, haunch or surround shown in the drawings to be accommodated.
eec54b15-5ecd-5436-96af-7f3f1ec2feb7 | note | ○ Trench depth to enable pipe to be laid with the designed cover as shown on construction plans.
8fd021a9-e8d2-5b4c-8b4b-5843892fc6d1 | note | ○ If trench bottom to be suitable to compact pipe bedding as support pipe.
fc3f41ae-94b6-572c-ac89-2a9ef6fb22bf | note | Acceptance Criteria - Trench dimensions correct
e3b19d68-be79-52b1-b552-b4069f08f057 | note | Verifying Document - Daily Site Diary
84a404dc-63b4-5583-b4db-f3add2e91694 | note | Reference: Contract Specs/Standards - D2.6, D2.7
5aa888e2-14d6-582f-9a52-d9c849c2397e | note | Inspection Point/Signature & Date - PS
27edf7a6-5c6f-40e4-b0c0-9ab61a806878 | checkpoint | 5.2 Encountered Services
da1255de-facf-5b78-9de0-40b88d5693d6 | note | Inspection Point: Quality Control Activity - Block by block ensure existing live services are not unnecessarily damaged by works.
5fc0b366-4852-5bfe-a581-cba57122ba03 | note | ○ Repair any services that are temporarily removed during construction.
c6c5167f-c5f2-5998-b8d3-01f5f3e9341c | note | ○ Record any services found.
0631e0d3-22a9-5d7c-8b37-c6cbd46c7c91 | note | Acceptance Criteria - Existing services not damaged
81f412b2-a38d-50f2-a598-84775c34f384 | note | Verifying Document - Encountered Services Record
90c9acea-6aa9-5d0a-b22b-e74a722eebd8 | note | Reference: Contract Specs/Standards - D1.7, D2.7.7
7d0df532-6775-5e02-87ef-5933b5113c19 | note | Inspection Point/Signature & Date - PS
0bb6eb81-7e4a-451f-830e-1b4ed2ca3ea2 | checkpoint | 5.3 Pipe Installation
e9a5264d-e34d-57c2-b251-70577ea28002 | note | Inspection Point: Quality Control Activity - Interior of each pipe visually inspected to ensure free of debris.
4de7eba6-7a52-508a-8f6f-3da7ba17c6ad | note | ○ Re-cap end of pipe after installation.
9fcd0740-534d-500d-8189-e0970be0fe0f | note | ○ Check pipe installed at correct depth.
97372ff6-7a61-5b54-b317-dc368cef403b | note | ○ Ensure all collars are free from contamination in McDougall St berm
d141a6e9-ce08-571e-8cfd-8a4080f2f31b | note | Acceptance Criteria - Pipes free of debris & correctly installed
6c48859f-43ee-519f-b185-e2757b35f5ef | note | Verifying Document - Daily Site Diary
d6e34e20-3287-5bb8-accf-914843f1e5ed | note | Reference: Contract Specs/Standards - D2.5, D2.7, D8.4.2
c344ad27-9a7c-5088-8578-ce9de1f06115 | note | Inspection Point/Signature & Date - PS
315ca360-db4e-4b0f-b047-bcd13a88803d | checkpoint | 5.4 Concrete Pre-Pour Inspection
a0c3ca9d-7c53-5f00-a910-1efc9d53070f | note | Inspection Point: Quality Control Activity - Check dimensions of formwork match details in the Construction Drawings.
63a3685f-631f-50f2-b45b-5b550dd42985 | note | ○ Check pipe fitting joints are clear of concrete pour.
23788df5-5f26-5f32-a93c-2b6f87bf050f | note | ○ Thrust blocks to be poured against good solid natural ground.
2e389bbc-ca69-56cc-991e-0c7ae5298cfb | note | Acceptance Criteria - Thrust blocks against solid ground
4630ea02-6452-5ef8-9df0-b7baf484a9ae | note | Verifying Document - Daily Site Diary & Photos
2a52135d-b44a-5d64-8c2f-594fcb8d9444 | note | Reference: Contract Specs/Standards - D5.1, D5.3.2, D5.7
270f8374-94d2-5ff4-afe3-a9f4d98bb457 | note | Inspection Point/Signature & Date - PS, CR
02e5fe15-a3d0-4117-9c59-df286de87b71 | checkpoint | 5.5 Hydrant Depth
c166f8ac-68a4-56d5-a714-45a77c232876 | note | Inspection Point: Quality Control Activity - Confirm depth requirements have been met;
2f2ace55-1dbf-557c-880b-7b6a3dd25264 | note | ○ Hydrant outlet: 200mm min. to 400mm max.
285e10aa-95d7-51d9-ab64-3b2072cdb2d5 | note | Acceptance Criteria - Hydrant depth verified
9803aeb2-9d90-54ba-9e49-df36b5629658 | note | Verifying Document - Daily Site Diary
f8c94654-15c9-51e9-8452-342e59ecae6e | note | Reference: Contract Specs/Standards - D5.5
cc256614-c42e-5f6e-a39f-f68a89b87155 | note | Inspection Point/Signature & Date - PS
a0e3fce6-d131-4d47-b2fa-1afd64dedf22 | checkpoint | 5.6 Compaction Testing
ba0f25db-c515-54bf-af10-241ef05a2184 | note | Inspection Point: Quality Control Activity - Confirm trenches in paved areas are compacted to standard block by block.
49e7f8fd-7c6b-5d23-b61b-854926d2d227 | note | Acceptance Criteria - Compaction confirmed
22f4308c-0c3d-5079-b554-738af731d09f | note | Verifying Document - Clegg Record Sheet
ea3ff20d-d289-5332-88c3-7d7ac37a937a | note | Reference: Contract Specs/Standards - D2.7.10
bb591b35-fe0b-530a-8cb7-36e77516390e | note | Inspection Point/Signature & Date - PS
cdecfdb6-ad87-453e-b692-8fb65eb5cbe7 | checkpoint | 5.7 Watermain Pressure Testing
1da5f833-284a-5b18-99a9-331354fad608 | note | Inspection Point: Quality Control Activity - Hydrostatic pressure test on new pipeline and fittings block by block.
2f9a2668-68c2-5f33-8c5e-ec33a157d16e | note | Acceptance Criteria - Pressure test passed
36849462-809a-58b1-a71f-40568e648c95 | note | Verifying Document - Pressure Test Record Sheet
a57df2e3-9168-58b3-8e23-04a24658c806 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
2d130f10-37f0-55a1-8d72-a460b1f28c32 | note | Inspection Point/Signature & Date - PS, CR
a1e1175c-838a-44d4-97e2-105d86a88295 | checkpoint | 5.8 Watermain Sterilization
ce10429c-a3e0-5c3c-b478-43bc65ee371b | note | Inspection Point: Quality Control Activity - Flushing and sterilizing full length of new pipeline and fittings block by block.
14828d25-390c-5376-8cc6-48d3ee750694 | note | Acceptance Criteria - Sterilization completed
72845af4-3a77-57b0-bfd3-8c8b00ad194a | note | Verifying Document - Sterilization Record Sheet
c67f69b9-5827-576d-aa4b-e05ef53cf735 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
99631707-3d31-5b31-aff4-efb8e8c21979 | note | Inspection Point/Signature & Date - PS, CR
ddf7462a-b76e-41eb-a36d-0de8b8dd2a87 | checkpoint | 5.9 As-built Information
517e67db-4033-58c1-a6ca-d3362f98ca30 | note | Inspection Point: Quality Control Activity - Capture data for all new construction work.
ba450391-5c8a-5c55-b1c4-c22f0833b96c | note | Acceptance Criteria - Redline mark-up plan submitted
3eb797e2-7275-5590-8fac-676aa04c793f | note | Verifying Document - Redline Mark-up Plan
b2cc15a1-1e88-5f06-9c50-d2d2827d97a5 | note | Reference: Contract Specs/Standards - C1.22
3c06f156-3b4e-51b2-91ab-48d5a7624304 | note | Inspection Point/Signature & Date - PM
6fda002d-0146-4403-8542-79c60a61f794 | signoff | HOLD POINT
8b2fb51e-3dea-4864-85cf-ea6c1f2099ae | section | Final Inspection and Handover
e1185f06-97ee-41c3-ba68-9fa87ec8f197 | checkpoint | 6.1 Final Inspection of Works
937e6486-743d-5157-8e7e-d97207a69798 | note | Inspection Point: Quality Control Activity - Work is inspected by the authorised person and complies with the nominated specification/standards
17149ea4-e39d-5a08-9b34-a5a55b8544b8 | note | Acceptance Criteria - Work inspected & complies with standards
69020570-efe6-5843-a2ad-9a102698555a | note | Verifying Document - Practical Completion Certificate
b28f2ad8-0f63-5340-9f55-310a0e29c35a | note | Reference: Contract Specs/Standards -
5422ff6f-c5f8-5de4-8a22-f168bf4f557c | note | Inspection Point/Signature & Date - PM
aca660fb-dc8b-43a6-b666-e84980ea511b | signoff | HOLD POINT

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
4e743bd1-3071-40d7-af67-dd1c37717495 | checklist | ITP - Bay Road FS | itp | ITP - Bay Road FS
965ff0e8-2368-4f6d-bc31-19c894b9e57e | section | Contract
6fb9b74e-41f4-4872-ae05-3ee4f90a4b57 | checkpoint | 1 - D1.3
2b284b62-b994-525d-8b6d-036853a784b1 | note | Inspection / Test Point - Site Management Plan (QEHS, SSST, KSA)
5ae1e7d3-9bbf-5063-a3e8-e9d4b4f95332 | note | ACTION (W, M, H) - H
f21e4fa3-90fc-5d8f-9433-eb4600732400 | note | Activity by - WCL
04583950-b165-5487-b64f-292b7cd0e520 | note | Conformance Criteria (What's Required) - Ensure Quality, Environment, Health & Safety Management Systems Plan
4c779b13-dc05-5dc8-89af-0579e5df8b96 | note | ○ Site Specific Safety Plan and Key Step Analysis are approved.
3215cef9-2d64-51e2-986f-d6a569689027 | note | ○ Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times.
2d075cf7-6505-5cc2-90ca-01d244f2934c | note | Frequency / When? - Prior to commencement
f7e6d449-df64-50b6-8680-d2f33af93ca7 | note | Inspection / Test Method - Submission (NTE)
144b31f1-63c2-5d72-8b56-5b55de07302f | note | Records / evidence, WCL form - Sign This ITP, LN-01, FM-83, FM-69
a02d21b6-2a63-5a07-8649-1c59324a5568 | note | Standard - ICC STANDARD SPECIFICATIONS
5558891c-f346-51f6-a085-fce155bdac74 | note | Print, sign and date: Wilson - YES
51191baf-f4a4-566f-a236-bde2373f3fa4 | note | Print, sign and date: ICC - YES
a6e33481-362c-4222-97b3-5e00dd01d3f2 | signoff | HOLD POINT
7f0c711c-a4b6-477e-add6-251677329b64 | checkpoint | 2 - D1.18
554c33e9-2472-57ce-9b52-95f65dff806c | note | Inspection / Test Point - TMP
66eb8ea2-d4a7-5946-8f64-a411dd6d6583 | note | ACTION (W, M, H) - H
b8c2f70f-c58a-55f9-8014-767595daaffe | note | Activity by - WCL
7ae6c997-9ff3-587e-ba1a-266a68292d5e | note | Conformance Criteria (What's Required) - traffic management plan to be submitted and approved by Road Controlling Authority
8d6a30ca-8f2e-58d5-8518-2c7fe148c8ac | note | Frequency / When? - Prior to commencement
8d11d977-09e9-5b83-99e2-6729ade61c9e | note | Inspection / Test Method - Sumission (NTE)
c3d4037f-8a8d-50b0-966c-7def1f361f1d | note | Records / evidence, WCL form - Sign This ITP, TMP
e5a447a3-d87c-5091-80a3-44580ae7933a | note | Standard - Code of practice for temporary traffic management (CoPTTM)
e3fc40c9-dd1e-5ee2-893d-788b1a6013e5 | note | Print, sign and date: Wilson - YES
2c818efe-9607-5bbe-984a-7b4eaae76bb8 | note | Print, sign and date: ICC - YES
aaf9b921-653a-450d-ab35-4a606239a1c5 | signoff | HOLD POINT
e612326a-b798-47cb-b11c-a79b5262c64b | checkpoint | 3 - D1.4
e3551054-4cda-58ac-8a77-3d81b32efc85 | note | Inspection / Test Point - Works Access Permit
01e43dc3-931e-5925-a746-f14563722bce | note | ACTION (W, M, H) - H
f7426f18-aad6-5b10-b22a-3222dcbe3d04 | note | Activity by - WCL
1d00b0a2-16c0-5f6c-846e-08ade0a5904f | note | Conformance Criteria (What's Required) - TMP and Corridor Access Request to be sumbitted on myWorksites
59b4dac3-7757-503e-89bc-ed17944d3f49 | note | Frequency / When? - Prior to commencement
ea977307-eb24-53b2-b0c8-0498df2cd3f7 | note | Inspection / Test Method - Document
ceb9443f-7e4b-56de-8e40-7fc6fc2562b5 | note | Records / evidence, WCL form - Sign This ITP, WAP
fe7533b9-7c80-58c9-91b7-bbe690a45912 | note | Print, sign and date: Wilson - YES
30aa1d9f-e4eb-5a51-be30-718aecae7a85 | note | Print, sign and date: ICC - YES
a5e49e80-6e1e-4344-b676-fefe29eb8109 | signoff | HOLD POINT
4da13245-be23-4976-99ba-003898ac0500 | checkpoint | 4 -
898d598b-6f1d-5746-8812-34712bf9e948 | note | Inspection / Test Point - Permit to Enter
e8665dbd-4c38-5f89-8abb-df5a448f7a94 | note | ACTION (W, M, H) - H
904808d1-214b-53d4-8e5d-967144056d24 | note | Activity by - WCL
d85ed7b4-3200-5ed8-8eb7-83d9ad17b386 | note | Conformance Criteria (What's Required) - KiwiRail
496f627f-a331-549e-b94e-2e9d513b9eb0 | note | Frequency / When? - Prior to any work near the railway area
c7f24dbf-f11a-51d9-864b-b8adbdf79de7 | note | Inspection / Test Method - Document
3e20576b-c611-5d99-9f86-51f8c23ab241 | note | Records / evidence, WCL form - Permit to Enter
26119ffd-8ff9-52aa-9774-bc61bd7cf20c | note | Print, sign and date: Wilson - YES
c8052f05-76b1-545e-a82c-cbdeddf8a0f7 | note | Print, sign and date: ICC - YES
499649eb-3205-455b-929f-8ef8a4f12120 | signoff | HOLD POINT
5c9a9407-2488-496b-84b9-1783dd93dda2 | section | Material
7aa56850-338e-4359-93d7-e2a7d9e09d7f | checkpoint | 5 - D1.14
b7f7a70b-d06e-5ffa-8711-0583bceedddb | note | Inspection / Test Point - Client start-up meeting
cbe76cb5-de8b-523e-abc5-5bf9bd137876 | note | ACTION (W, M, H) - H
a111f0c9-44f9-50fd-afd1-ec3d19fb89de | note | Activity by - ICC, WCL
25a0955a-d1c9-5bd8-9c4f-1ca93bed0026 | note | Frequency / When? - Prior to commencement
cb530b57-a613-5692-b837-9c6a0bfe6af3 | note | Inspection / Test Method - Document
d8f82d1f-3f10-54d2-afc8-6ee6bab0f402 | note | Records / evidence, WCL form - Sign This ITP, MoM
0058473a-47a3-5f9c-9303-b223ebf12ea6 | note | Standard - ICC STANDARD SPECIFICATIONS
23cff45e-9641-54a6-84e1-372a33417175 | note | Print, sign and date: Wilson - YES
c7d7348b-44b1-5eca-afdf-41918d13b3ca | note | Print, sign and date: ICC - YES
f127d597-3107-4203-bc20-e26df05d27f8 | signoff | HOLD POINT
00fd7811-7524-40b9-9f17-b05f0d5cfd2c | checkpoint | 6 - D2.4.2
4281997e-c5f0-5fb4-85aa-578050ea7d93 | note | Inspection / Test Point - Bedding material
788465e7-25d9-578a-bf2b-30a4fc4b84c4 | note | ACTION (W, M, H) - W
601b266d-eb90-5274-9a48-c03c1c68c28a | note | Activity by - Lab
2b270acd-f9e6-5c70-a83e-827d4ffbe12c | note | Conformance Criteria (What's Required) - Material to comply with contract specification
d64320e4-3f00-5e84-93fd-85d7acbbcdc2 | note | Quantity - 650 m3
f81a97e4-e013-501a-bb90-83e668257eb8 | note | Frequency / When? - Prior to commencement
2a2a32a2-4950-5a59-80f1-38612fde9c0d | note | Inspection / Test Method - Lab report
6a5bd554-8fd7-50c8-beec-a0cdad6d26e1 | note | Records / evidence, WCL form - Grading Results
aa008f43-4190-57b3-961d-48850cc904ef | note | Standard - ICC STANDARD SPECIFICATIONS G3 of AS/NZS 2566.2
2d45366d-55ff-59cb-8ee8-880f55ce27fd | note | Print, sign and date: Wilson - YES
6f4714ce-f089-557a-b48f-5cfff97f31a6 | note | Print, sign and date: ICC - YES
95693472-f1c0-4f7b-b405-8c80976c604b | checkpoint | 7 - D2.4.3, D1.29.3
ead9f221-6acf-52f6-b323-183498a5929c | note | Inspection / Test Point - Sub Base Aggregate AP65
25c9253c-31f2-5dbd-81c5-0777e97e3eb8 | note | ACTION (W, M, H) - W
049f0113-8c97-567a-8ca4-a42355272e7a | note | Activity by - Lab
ddb8c9e4-9162-5c0b-a6c7-52af3f251786 | note | Conformance Criteria (What's Required) - Materials to comply with contract specification
139dcbc8-bc77-5783-9420-4850a94fada1 | note | Quantity - 2500 m3
1405ee4d-2c49-5c10-928d-832a6403f4f9 | note | Frequency / When? - Prior to commencement
b23a7cd7-92fc-5ff6-adec-2f0c7f01c7d8 | note | Inspection / Test Method - Lab report
bb6d8bac-02e7-54c4-be0b-08ee4e1f0c52 | note | Records / evidence, WCL form - MDD and Grading Results
e7c67276-4cbe-598d-b1af-abb3981ef42a | note | Standard - ICC STANDARD SPECIFICATIONS
65b2a427-22bf-5d13-8f82-6697a241c4d2 | note | Print, sign and date: Wilson - YES
92f3c54c-fc4c-57ac-991b-b090cec70da7 | note | Print, sign and date: ICC - YES
3929bddd-bfba-4163-809e-7246704c90bd | checkpoint | 8 - D1.29.4
a4e6a8e5-7c34-5da7-8817-8941e24c0226 | note | Inspection / Test Point - Crushed Basecource Aggregate M/4 AP40
a4a687b7-8d0a-5684-bba5-87f449bd3008 | note | ACTION (W, M, H) - W
f5f4ca02-9a18-5c30-ae9f-9a0f06823b08 | note | Activity by - Lab
9541a1b6-739e-584d-8e22-37b7307d6921 | note | Conformance Criteria (What's Required) - Materials to comply with contract specification
de3d7c4c-adf8-507a-a088-ddbe5394c6d1 | note | Quantity - 250 m3
2c29fddb-6f1d-5e6e-aafc-2db5624938f1 | note | Frequency / When? - Prior to commencement
4c2c7295-e8f8-5a47-9306-b4068fbb03e5 | note | Inspection / Test Method - Lab report
0b8d0c2f-8eff-56a9-a78e-ee66cac18fb1 | note | Records / evidence, WCL form - MDD and Grading Results
d011ed9a-fd92-57a2-ae3f-19ae061c2b57 | note | Standard - ICC STANDARD SPECIFICATIONS NZTA M/4
d1eb2162-a709-564a-871e-ab0699100e2d | note | Print, sign and date: Wilson - YES
fc91b21c-b1b2-5cbd-a1c2-bcadac16bc45 | note | Print, sign and date: ICC - YES
6fc717db-0a09-4c07-98a7-c32424d77ed0 | checkpoint | 9 - C1.4, D2.4.1
91ba5a80-820a-52a0-87c2-028e0c71c543 | note | Inspection / Test Point - Pipe material (F25402 - F25403)
072c33eb-3744-5758-a262-f16e3e487075 | note | ACTION (W, M, H) - M
e065fb57-6cf4-5719-abad-ef9070dd4694 | note | Activity by - WCL, ICC
47a7105a-7a03-5d44-bcb1-096ab2200ae3 | note | Conformance Criteria (What's Required) - DN300 uPVC SN16 RESTRAIN
8342e18f-a8fe-53b4-b741-42c465726e25 | note | Quantity - 30 m
86da84a7-3f5f-58a3-ae8f-9dbc67a8249b | note | Frequency / When? - 1 / delivery
68139518-5f8c-5715-8594-adda6ba22b7c | note | ○ WCL is to inspect all deliveries
839fb68b-4124-5783-b430-6cd0f625ded5 | note | ○ ICC to inspect deliveries as required
7d53b967-0319-5ec3-b45b-2e36e18cd614 | note | Inspection / Test Method - Visual inspection
11a51bb1-da1c-51ea-8bae-9d55992c8db6 | note | Records / evidence, WCL form - Sign This ITP
dc6a83df-2ed2-53d5-9982-e7259db3140d | note | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 1260:2017
695bd3b6-5969-5256-802b-8983a479c035 | note | Print, sign and date: Wilson - YES
821e8f47-93a2-5c8e-b892-7c1892cc24b4 | note | Print, sign and date: ICC - YES
8b10de04-3aa9-4229-bb78-707dca3f9dca | checkpoint | 10 - C1.4, D2.4.1
f064320f-bd45-5e05-9801-21480e2b1e70 | note | Inspection / Test Point - Pipe material (F25403 - F25406)
df8e704b-f1a6-5222-99cb-83ea7acc4822 | note | ACTION (W, M, H) - M
60e79779-ed0c-5de4-acfc-4a784dbdab0e | note | Activity by - WCL, ICC
fe725f0f-9567-5b50-b665-fce53c17988d | note | Conformance Criteria (What's Required) - DN300 uPVC SN8
8e45c9a8-eb58-5306-b6d2-6e8f3f20e46a | note | Quantity - 328 m
32d2bf53-cd62-50c9-9307-4c0d7f007997 | note | Frequency / When? - 1 / delivery
e0ed6591-afdb-515d-bdb5-f8d156da5a31 | note | ○ WCL is to inspect all deliveries
b957f2b7-1f5d-5055-b455-c03ffdbdb42e | note | ○ ICC to inspect deliveries as required
19da3f2c-2153-526e-bdaf-1a503fc83b7c | note | Inspection / Test Method - Visual inspection
ed7560c6-6459-5dac-8072-6eacb428959b | note | Records / evidence, WCL form - Sign This ITP
7826b495-68d3-53eb-ac0f-b5894ed2bc87 | note | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 1260:2017
b32e7092-e64e-57a0-b5b3-97fa908fd270 | note | Print, sign and date: Wilson - YES
e3442294-72b0-532a-b65c-5ee7e3ed4b19 | note | Print, sign and date: ICC - YES
ddd5a538-2e14-437f-a8bf-cc124e27a6ca | checkpoint | 11 - C1.4, D2.4.1
b57ff132-6759-542e-8395-9ab2344a39be | note | Inspection / Test Point - Pipe material (F25406 - F25410)
1d35ddaf-5c1c-5fab-9e43-3a39151a969f | note | ACTION (W, M, H) - M
90352bc2-9447-51a9-813a-329627839958 | note | Activity by - WCL, ICC
5c5f21d3-c488-578b-a2ff-a251e276b903 | note | Conformance Criteria (What's Required) - DN225 uPVC SN8
903d4cc0-b25a-53fe-9179-83bf667e93a6 | note | Quantity - 378 m
cc0a53a0-5075-5006-a2ab-7219119d4b40 | note | Frequency / When? - 1 / delivery
64dd1f7f-0e22-5401-98ba-4d146f1aa839 | note | ○ WCL is to inspect all deliveries
444f1f48-c9e2-5130-a92a-495567631cea | note | ○ ICC to inspect deliveries as required
d1e388d9-ce1f-594d-a451-968cb1b7b794 | note | Inspection / Test Method - Visual inspection
8f7caefd-ad2d-5a4b-b26d-dff0acccb105 | note | Records / evidence, WCL form - Sign This ITP
98f4f89b-cdfd-5f81-921e-089a92a75b41 | note | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 1260:2017
5ecfb9bb-10e6-553e-9c3d-7f5ec997b922 | note | Print, sign and date: Wilson - YES
389a169c-261e-5a4e-ae3a-f28b2fa60493 | note | Print, sign and date: ICC - YES
6ec0da88-d46b-466b-a883-33e6cc5343d6 | checkpoint | 12 - D4.3
f795ec99-0c0e-5dab-bdd5-a22235935f14 | note | Inspection / Test Point - Pipe material lateral
bdbad25a-ba40-51fb-8358-ca7a3c004268 | note | ACTION (W, M, H) - M
5bc9a035-f89b-5b9d-8030-03f4a0d381ea | note | Activity by - WCL, ICC
70515209-310c-5ea7-b7f5-3db0cca2e372 | note | Conformance Criteria (What's Required) - DN100 uPVC SN6
d9b735a5-fdf7-5fe2-a624-0b7b29d58a0b | note | Quantity - 780 m
0e65fae1-95af-52bc-a90b-8c89f4508452 | note | Frequency / When? - 1 / delivery
d90ef749-353b-5fc9-9126-337d50de1bd4 | note | ○ WCL is to inspect all deliveries
ee8b1f37-8cb0-565f-9b9f-467840f8b770 | note | ○ ICC to inspect deliveries as required
fa9beccd-8c08-5e4d-a6da-eb04f3c5e9c1 | note | Inspection / Test Method - Visual inspection
fe979c19-e26f-5265-b876-e01e28e6384f | note | Records / evidence, WCL form - Sign This ITP
fd7ddd44-3cf8-5662-aabb-6beea934d96a | note | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 1260:2017
0fc5cdb3-fc23-592b-b5ff-7fce4f0e34a1 | note | Print, sign and date: Wilson - YES
ac3d2520-0bd6-5980-bd68-c8de19733e6f | note | Print, sign and date: ICC - YES
2d19a991-e550-40eb-bfef-4ab7ddc74bca | checkpoint | 13 - D18.2
70ac5a87-1716-5c03-93fe-a32f44283b42 | note | Inspection / Test Point - Precast manhole elements
55673638-bccd-5ca5-93cc-98ef2e01e966 | note | ACTION (W, M, H) - M
9bba4590-e796-5cf2-98e5-7a775adf3743 | note | Activity by - WCL, ICC
23e8f704-5de0-570e-96f8-793842084605 | note | Conformance Criteria (What's Required) - min. 25 Mpa
617f137b-4ce4-5eef-a067-4dddd66357fd | note | ○ 1050 mm nominal diameter
090964ec-a2f0-5729-b01b-8243be1fb8c7 | note | ○ 150 mm lid (HO loading)
3862d94c-8b1a-50aa-8f10-55ecb3b85529 | note | Quantity - 8 MH
5aea4bb7-bf5b-5894-a436-7c22d9fa49dd | note | Frequency / When? - 1 / delivery
f737b966-4e1a-5167-b796-fd6c0183fcf4 | note | ○ WCL is to inspect all deliveries
a30f63e9-167b-5da3-b22d-5fdc33df4df6 | note | ○ ICC to inspect deliveries as required
baa71cc4-825a-5fc5-bc2f-75c2c946462e | note | Inspection / Test Method - Visual inspection
12d7c3fb-45f2-52c1-b3b5-e142ded5ffe8 | note | Records / evidence, WCL form - Sign This ITP
978c8c9b-d492-518d-85a6-40be26d7ac2a | note | Standard - ICC STANDARD SPECIFICATIONS NZS 4058, NZS 3107
298793b9-e617-5d8b-8e86-326817d9e041 | note | Print, sign and date: Wilson - YES
8263375f-0a7f-5079-a18f-eaba113ac9e8 | note | Print, sign and date: ICC - YES
3519935f-3382-4458-bae2-e4a31c42950a | checkpoint | 14 - D15.2
13fbccf5-7f04-58e8-9cd8-1fc63295897a | note | Inspection / Test Point - Manhole covers
7e768658-2a22-5d82-9f05-2e12450f0d59 | note | ACTION (W, M, H) - M
e5e782cc-6a25-539f-9b33-3b2f88db8618 | note | Activity by - WCL, ICC
c5967097-a7be-5135-a958-886b639dd182 | note | Conformance Criteria (What's Required) - Heavy Duty Ductile iron, HN-HO-72 hinged, 600 mm clear opening, gas seal
4548f563-44dc-5802-beb6-a82a5109e478 | note | Quantity - 8
9519d7b9-9655-5541-af71-ef5b4d3ee5fc | note | Frequency / When? - 1 / delivery
9f175308-cecc-599d-ba1f-4334070207f2 | note | ○ WCL is to inspect all deliveries
00c6017f-a2b5-52f7-82b7-695f629836f4 | note | ○ ICC to inspect deliveries as required
d6fcef7d-ff92-52a6-a5e3-2d6d31948bd5 | note | Inspection / Test Method - Visual inspection
20d8615e-0cda-5916-bf59-c52dada5395e | note | Records / evidence, WCL form - Sign This ITP
e050baa6-5e8a-5e34-8ed3-c216a96f2a3b | note | Standard - ICC STANDARD SPECIFICATIONS
b3c5db3f-b4b5-5cd7-98b6-9ff7353a03f8 | note | Print, sign and date: Wilson - YES
db787e12-9515-5184-9429-73f5e21b112c | note | Print, sign and date: ICC - YES
23bdf9d3-4ea4-4058-97f9-b996db974323 | checkpoint | 15 - D15.2, Fig. D9
a7756600-eb28-5df7-97c8-5792abf44dd2 | note | Inspection / Test Point - Cleaning eye cover
78f15c99-cad2-58ca-b08f-3ff0c6fa209c | note | ACTION (W, M, H) - M
57c666f5-508d-53bc-aa9b-83dab1c0d69f | note | Activity by - WCL, ICC
228443f7-6a54-5d8e-9604-9da457c0dc50 | note | Conformance Criteria (What's Required) - Warrior Surface box clear opening of 380mm x 224mm
06ee3fcc-9363-578f-809d-2c815539c711 | note | Quantity - 1
5ea7f530-8bc8-50be-b4ba-80c2333fb325 | note | Frequency / When? - 1 / delivery
15e912eb-6735-54dc-8958-870968dad5f5 | note | ○ WCL is to inspect all deliveries
bc214fc9-ccad-5e61-bb8d-84cdbbed6233 | note | ○ ICC to inspect deliveries as required
38ac5d4a-798b-5c08-989a-4071d200edd5 | note | Inspection / Test Method - Visual inspection
c9d272e6-0f74-5076-b44a-3ce39c260e91 | note | Records / evidence, WCL form - Sign This ITP
cb5e52a1-b32a-5385-944d-f673d28f0884 | note | Standard - ICC STANDARD SPECIFICATIONS
685e2e10-94ba-5bcd-ac58-69a3ade03c7c | note | Print, sign and date: Wilson - YES
622e1a6f-b35b-5f67-94ba-e3388a56393e | note | Print, sign and date: ICC - YES
574f4ae4-f6ab-4053-a7f9-15688fbce87f | checkpoint | 16 - D2.8.3, D12.3.1
e905cee0-5e10-5b00-818d-12c17a609faa | note | Inspection / Test Point - Asphalt (carriageways)
867aa6ac-ad34-5de3-87c8-ee3b5fd75a39 | note | ACTION (W, M, H) - W
b35ad506-5075-5104-b825-c0fab6317034 | note | Activity by - WCL, ICC
d797d4ab-f208-5548-b90d-241e2efeaa84 | note | Conformance Criteria (What's Required) - DG10
5e0168ab-b19e-5dc1-85ed-fd5368b953bd | note | Quantity - 730 m (main), 700 m (lateral)
6d19a562-a426-55a7-b692-22d0815ab091 | note | Frequency / When? - 1 / delivery
454db2b1-330c-5ec3-8d87-7d8956dc38fd | note | ○ WCL is to inspect all deliveries
2a105fe7-7123-5fbc-b1b3-5ea68f0635a1 | note | Inspection / Test Method - Document
4e2cf48d-29c5-5333-ba73-3ef5ee5197db | note | Records / evidence, WCL form - Sign This ITP, Delivery docket
65e2ebe3-83be-5ac7-b741-21592b9dd0e1 | note | Standard - ICC STANDARD SPECIFICATIONS
0b5362f4-ab6c-5e78-80d7-0369998e6eba | note | Print, sign and date: Wilson - YES
90792ef4-738b-598b-9ef6-03ead858805d | note | Print, sign and date: ICC - YES
85704370-e808-4b82-a85e-900419f41069 | checkpoint | 17 - D13.3.4
45f30bf9-cd7e-5a7a-a76f-ca67144ac0cf | note | Inspection / Test Point - Asphalt (footpath)
f17770a9-6666-5284-9ae8-c42fd5e95c23 | note | ACTION (W, M, H) - W
5e82bea0-2b75-5b87-839e-a46cb84c8384 | note | Activity by - WCL, ICC
307853fe-951b-5d73-9eec-5c5eee4872a5 | note | Conformance Criteria (What's Required) - mix DG7, 180/200 penetration grade bitumen
4d62004f-bec2-51b4-88ad-b5bcc8469d8d | note | Quantity - 58 x 1 m
680e5dec-ad16-5695-8671-ec3298562fde | note | Frequency / When? - 1 / delivery
1a5f7102-8b9a-5381-8f10-3020eeaefcc3 | note | ○ WCL is to inspect all deliveries
aaaf674d-a3fb-58e3-a495-d1027f82712a | note | Inspection / Test Method - Document
25615150-b843-5cac-b562-be07cdd2a5c0 | note | Records / evidence, WCL form - Sign This ITP, Delivery docket
33fab96d-8f33-53ef-bec9-2f8befe2b4e8 | note | Standard - ICC STANDARD SPECIFICATIONS
19a25c91-44b5-5b94-9575-d14fcb9db6e1 | note | Print, sign and date: Wilson - YES
3134f45c-bef3-5b13-bfec-f6a8c4f03f1c | note | Print, sign and date: ICC - YES
25c0e0e0-7009-4083-b5e5-4e29aef7691b | section | Pre Construction
333518b9-2090-49f7-a28b-e2e82525d87c | checkpoint | 18 - D1.5
35b6bb9f-75ea-5f72-a351-c2742dd81e36 | note | Inspection / Test Point - Pre-work site inspection
52078741-bde7-5ea2-bcfd-ac0f0d533d92 | note | ACTION (W, M, H) - H
ca438021-ddad-573a-be59-bf005fe01c6a | note | Activity by - WCL
7af5c17f-8acd-5d7b-a57e-162f919b7050 | note | Conformance Criteria (What's Required) - Video or photos near the construction zone to determine their pre construction condition. (landowners property)
b3164255-a763-552a-89cb-67047af8255b | note | Frequency / When? - Prior to commencement
3b1945ca-3bd8-5e35-9299-59aec49d4c9d | note | Inspection / Test Method - Inspection Document
1ed3c517-7367-5a46-b68b-d74f737108d1 | note | Records / evidence, WCL form - Sign This ITP, Video, Photo
c88da025-0734-57c7-8f45-095ed899d018 | note | Standard - ICC STANDARD SPECIFICATIONS
4422cc49-a0ba-5a4b-b4e9-6fb73288ad28 | note | Print, sign and date: Wilson - YES
9ab8b2fe-a85f-5552-8b96-17d45f2edc94 | note | Print, sign and date: ICC - YES
05958eef-3adb-40e5-961b-58657107525c | signoff | HOLD POINT
c5d966e8-259d-4d19-ba7b-3ad775e11bf4 | checkpoint | 19 - D1.18
630aa75e-0030-5c2d-a06e-bbaf9dae4b98 | note | Inspection / Test Point - Temporary traffic management
d3cab6b9-968f-5477-b6d6-538db9d3870b | note | ACTION (W, M, H) - H
a6aee16b-3b41-512a-81de-70a5098a40b7 | note | Activity by - WCL
8668d543-5d23-5797-a6aa-44470c2d362e | note | Conformance Criteria (What's Required) - Signs set up as per TMP, with a copy on site with STMS. TMP monitored for practicality. If changes are required these are to be agreed upon with the engineer.
57a6df62-b59f-5719-b8aa-9bd547e19785 | note | Frequency / When? - Prior to commencement
bc76a3fe-5dc7-5cdc-8bfd-531ecce7a985 | note | Inspection / Test Method - Visual inspection Document
833f318b-beba-50f8-92a8-22a5c7905275 | note | Records / evidence, WCL form - Sign This ITP, On-site record
702c84e1-73bf-5a75-a683-6fee417b075f | note | Standard - ICC STANDARD SPECIFICATIONS CoPTTM
2d5e779d-e4d5-5907-b2be-8ed3832d8f30 | note | Print, sign and date: Wilson - YES
3b8a145e-8103-58e5-aa33-c83a11cc421d | note | Print, sign and date: ICC - YES
2418fda9-ed62-4955-a682-2f0aeec094bb | signoff | HOLD POINT
17ce80fa-5128-4de0-8f3c-e83e0dd3ab1c | checkpoint | 20 - D2.7.1
0f1a2574-7e83-5214-9705-4b7a2165a7a5 | note | Inspection / Test Point - Set out
4e4e1e8d-0eba-52fc-a7ce-abfaa8256161 | note | ACTION (W, M, H) - W
9c519c78-4a4b-5dca-b476-def4df036fc0 | note | Activity by - ICC, WCL
953507ba-ae5e-5196-88fe-fe7930f27b50 | note | Conformance Criteria (What's Required) - Mark out of alignment for mains and laterals
22fddb57-5650-55cb-a2ab-557d194feb3f | note | Frequency / When? - Prior to commencement
bac01124-5f91-5845-9032-4214b859f0c5 | note | Inspection / Test Method - Surface marking
eb9601f2-530f-5d97-a89e-86fe2d0f3c14 | note | Records / evidence, WCL form - Sign This ITP
cd50f0c9-6e00-511b-a702-5fa11aa01c1f | note | Standard - ICC STANDARD SPECIFICATIONS
7078e4dc-3b05-589b-84c4-3b9b73193769 | note | Print, sign and date: Wilson - YES
445fb7cf-78aa-50ee-aff5-76b9279c8802 | note | Print, sign and date: ICC - YES
76bacf5e-29d8-421b-8dbe-661d3f0daef8 | checkpoint | 21 - D1.8
cf0c29a1-752a-5941-8dda-91cd1d793d4c | note | Inspection / Test Point - Protection and identification of other Services
43984a50-9f07-574a-99b3-1248617f35da | note | ACTION (W, M, H) - H
44d26b00-6449-5c57-8323-792679a8a7b1 | note | Activity by - WCL, asset owners
9336ed78-03ef-507e-b80a-a3906d60a957 | note | Conformance Criteria (What's Required) - Mark out on site of all services. Services to be potholed for as per Wilsons company policy
65c9fcc4-e7da-5086-bc32-9235d5168e54 | note | Frequency / When? - Prior to commencement
af392f60-61e4-5dbd-9838-3b6810c1aacb | note | Inspection / Test Method - Surface marking, Visual inspection
ace22e18-21c5-5053-8bfc-9bc509c4d617 | note | Records / evidence, WCL form - Sign This ITP
0ac01fd3-e456-5fe1-96b0-46678e6e3966 | note | Standard - ICC STANDARD SPECIFICATIONS, Wilson's prior to excavate policy
5ba106e2-8e6e-5dbf-bda9-b3ea33d7cb94 | note | Print, sign and date: Wilson - YES
9934fde7-b7fa-51ed-ba91-2c902cb55986 | note | Print, sign and date: ICC - YES
2aaadcf7-37e3-4824-8c90-301b0df288f4 | signoff | HOLD POINT
87235d93-db45-4fcd-9106-cdb6fdd17356 | checkpoint | 22 - D1.11, D9.5
5c374cbc-31e1-574a-823a-5dd81880ea4d | note | Inspection / Test Point - Notification to residents and businesses
266b1142-eeb2-5b3c-b544-c7f67018f943 | note | ACTION (W, M, H) - M
99dbcd59-b248-536f-bda3-ce9935823f1e | note | Activity by - WCL
55e422cd-ae46-5d7d-bba0-94521c8fd6b0 | note | Conformance Criteria (What's Required) - Letter drop / business visits
52a3f266-0cc6-54ba-b3e0-a925e3cc6573 | note | Frequency / When? - Prior to commencement (min. two working days prior to access restriction)
26995d30-2045-5fb8-93df-aa7b99b214f6 | note | Inspection / Test Method - Document delivered
71b3aa16-030e-5d74-9494-9f36ba237402 | note | Records / evidence, WCL form - Sign This ITP Notification letter
cdb5b204-1202-5ad7-b7c9-02b06360e3a2 | note | Standard - ICC STANDARD SPECIFICATIONS
0b740d44-407f-5ca2-b5bd-af78ae19504c | note | Print, sign and date: Wilson - YES
f7e6c8d1-a3ce-5652-9cdf-19e0e1ffefbb | note | Print, sign and date: ICC - YES
0448cd81-f385-4220-92a7-1198bdb952e2 | checkpoint | 23 - D1.32.7
4cb30ec4-f033-5560-b43f-262fb394d861 | note | Inspection / Test Point - Railway survey
bad4cf42-c94a-5b72-adaa-cdbce63c32c7 | note | ACTION (W, M, H) - M
197c048a-8200-5ad6-873c-bf28e6bac1bf | note | Activity by - WCL, SUR
21823761-70cd-571c-909f-6cb67c8c3711 | note | Conformance Criteria (What's Required) - survey monitoring for track settlement: 1 m increments along the track, 20 m either side of the work centreline, / 3 m of progress of the pipe’s installation under the track.
4f62cd43-f6c2-5b77-aa2d-052af5f02804 | note | Frequency / When? - Before and after the works
a29cd34a-326f-516a-99f2-69ec062bbd9e | note | Inspection / Test Method - Surveying
2083dc04-cd73-5724-8a64-10812e4bc1b7 | note | Records / evidence, WCL form - Survey record
70b30772-f3b7-53cb-964e-d8c3bd791230 | note | Standard - KiwiRail Civil Specification, Installation of Utility Structures on Railway Land (C-SP-AE-64322)
2cee7422-a9d6-5f2a-9c45-f322aaa109ba | note | Print, sign and date: Wilson - YES
e60897bf-18d6-5084-830d-607568b02f15 | note | Print, sign and date: ICC - YES
bd8e8af8-2c78-453c-8fe4-9d69bab6bf71 | checkpoint | 24 - C1.8, D1.6
9594db19-af44-5cd1-94d0-bbff4dc256bf | note | Inspection / Test Point - NZ Heritage induction
fa18fb60-a94d-5d36-80fa-e88a2dbe8b95 | note | ACTION (W, M, H) - H
b17abf66-1d82-54a3-93ac-eb00bff4d4fb | note | Activity by - WCL, ICC
14256b27-e995-5929-8fc3-075acf5014de | note | Conformance Criteria (What's Required) - Contractor briefing is to be completed by all personnel working on the project
93b50d02-fe9b-5a66-a181-e2f3c9846d4f | note | Frequency / When? - 48 hours prior to any work
7b8960ac-1f24-5522-8424-d87bd12a4d21 | note | Inspection / Test Method - Induction
c0264b3a-631d-597b-bad4-a3f7a9513e36 | note | Records / evidence, WCL form - induction record
15fea48b-08fd-5c76-a7b0-f2dde1641141 | note | Standard - ICC STANDARD SPECIFICATIONS
cc53f167-ad06-5244-81a8-571d5e2d19e8 | note | Print, sign and date: Wilson - YES
ada8e968-e3ef-5ea3-889f-0968ea3b0578 | note | Print, sign and date: ICC - YES
9f8bd1b6-6cc3-4d2e-85e5-1043934fe8aa | signoff | HOLD POINT
a157340c-41e4-4663-87e3-84455debe484 | section | Foul Sewer renewal
83dadeb6-9cf4-40f2-af28-2316e74f4a71 | checkpoint | 25 - D2.7.2
1850728e-4c84-5f0c-961f-370b169270e5 | note | Inspection / Test Point - Excavation
07bc1018-c6a2-5038-88a3-56c8f04f5984 | note | ACTION (W, M, H) - M
5c24489d-ea62-5147-b869-4a66062c0d55 | note | Activity by - WCL
333edc40-83f9-5d28-afd8-28f4e765baa8 | note | Conformance Criteria (What's Required) - The finished excavation surface shall be a smooth consistent surface at the appropriate grade. No tolerance on the excavation base level that reduces the depth of the bedding will be allowed.
c4e39a46-9072-5ba5-84b5-e2b2517f1baa | note | Quantity - 706 m - main, 780 m- lateral
0b73d57a-7b91-5878-b500-0d83af25ac26 | note | Frequency / When? - continuous
f5c6c12f-6efc-5820-a6d5-86c4c57a4b4a | note | Inspection / Test Method - Visual inspection, Levelling
c8340940-e09f-5bb3-a6aa-826d6db28041 | note | Records / evidence, WCL form - Sign This ITP
04728bcc-839b-5311-b2e7-fd5cb24fe5c5 | note | Standard - ICC STANDARD SPECIFICATIONS
3eee8df1-51ee-5639-a414-04491983edf1 | note | Print, sign and date: Wilson - YES
d1a69d55-351d-5b2c-bffa-18ca607236d1 | note | Print, sign and date: ICC - YES
246cc46d-dbd7-42fc-8a6a-b013ab28052f | checkpoint | 26 -
3a2a2d28-c9c3-508f-be58-0b80ae2bc357 | note | Inspection / Test Point - Removal of existing pipelines and manholes
b4b02ccc-8f3e-5511-9ac4-b04091f350df | note | ACTION (W, M, H) - W
f548883d-dbb1-5fbf-a876-3a561c018011 | note | Activity by - WCL
92ff444f-8dbb-5e3e-bf86-46da458b7255 | note | Conformance Criteria (What's Required) - Excavation will include the removal of existing redundant mains, manholes and property connections
cb0b8a0b-4e4c-5ece-8a8c-348c016810d7 | note | Quantity - 273 m D300
88abca5a-9354-5aa8-b6be-ef705b332c37 | note | ○ 378 m D225
7363e8ed-4af1-5f61-a73a-5e906538f375 | note | ○ 780 m D100
17865acc-ee8c-5c1f-ae10-d6185acf6685 | note | ○ 8 manholes
7e03e56a-940a-5362-be52-55405557b709 | note | Frequency / When? - during excavation
ea2d4da5-8f54-52de-a082-13929dcaa4b8 | note | Inspection / Test Method - Visual inspection
2367c08b-f2bb-51a8-a066-4aad888a5ea2 | note | Records / evidence, WCL form - Sign this ITP
487c2ff2-8457-5b20-af66-cd021ece2ee0 | note | Standard - ICC STANDARD SPECIFICATIONS
bc260817-3add-51df-8f11-3cb7d356bb65 | note | Print, sign and date: Wilson - YES
5f5770ce-9dcf-5329-a45e-d69b141b56f4 | note | Print, sign and date: ICC - YES
02660bde-2077-4fe5-a363-0838cdd3cfca | checkpoint | 27 - C1.11
45a1f3fb-1314-5d40-8869-77fffcf04a6a | note | Inspection / Test Point - Disposal of Surplus Materials
7f23d8e0-80c6-5fae-93a5-f7c8becfee9e | note | ACTION (W, M, H) - M
0fc00c57-7081-529c-8f39-87e549fddde9 | note | Activity by - WCL
b0d84ed1-8f63-5e8b-938b-b1f9282ed959 | note | Conformance Criteria (What's Required) - The Contractor shall dispose of any surplus materials in a safe and sustainable manner
ed2f3f74-d764-52bb-8939-41278c205f35 | note | Quantity - 3500 m3
80c26336-4fd5-5bfc-be39-479e8399a041 | note | Frequency / When? - Continuous
6f32ed32-8093-55dd-80dc-227f623757b4 | note | Inspection / Test Method - Document
79bffbf2-3699-5f13-b184-1cdd6958be56 | note | Records / evidence, WCL form - Sign this ITP, Disposal register
fc80b7be-f39a-5ed2-ae69-994d6213d728 | note | Standard - ICC STANDARD SPECIFICATIONS
e94deb2a-00a0-5359-bb4e-d5cfc9781720 | note | Print, sign and date: Wilson - YES
bc0e0221-e575-5aa9-91c3-983607d0bd3e | note | Print, sign and date: ICC - YES
ac664366-3ad2-40cd-8bc3-507d3bcade1a | checkpoint | 28 - D2.7.2
3255b2e9-5120-5649-8382-4f40bb3bf779 | note | Inspection / Test Point - Subgrade inspection
338ce5fc-d18e-54a5-82d9-79b68a2379fa | note | ACTION (W, M, H) - M
a31685c7-460c-503d-9f26-ef0168552821 | note | Activity by - WCL, ICC
3ae8fee3-0027-505a-918e-dbbd7a883750 | note | Conformance Criteria (What's Required) - To determine if improvements are required
61964a21-1fa6-57e7-83dc-793cd59ab5cd | note | Quantity - 706 m
31a54964-5ee8-5ab6-be69-ac0f78eb2789 | note | Frequency / When? - Prior to placement of bedding
ce6a332f-bb7f-5ecf-9456-39ef7b839c91 | note | Inspection / Test Method - Visual inspection
b609af25-41f5-59f7-a80c-7e97e4e17822 | note | Records / evidence, WCL form - Sign This ITP
48ff9058-b2ae-5bfa-b04e-632eaed84c8d | note | Standard - ICC STANDARD SPECIFICATIONS
d1d0ff00-8f87-5c94-9ba6-cab30cbac780 | note | Print, sign and date: Wilson - YES
07ca1818-f476-5e92-a72f-da1e0c365b3b | note | Print, sign and date: ICC - YES
d1be6d48-ffe6-4c0c-b89b-bccb2ad3ef5d | checkpoint | 29 - D2.4.2
59824be1-1718-5af3-a9f8-db1893df91de | note | Inspection / Test Point - Free draining material
05321a2e-b875-56c9-b81a-8b8c27cfb607 | note | ACTION (W, M, H) - M
cb6209be-2eee-5077-abad-18c3d6d8b16f | note | Activity by - WCL
90630d73-e54d-5a58-8c13-d00d73b96d28 | note | Conformance Criteria (What's Required) - pea gravel wrapped in a suitable geotextile up to 100 mm over the trench bed
486ec873-2791-58eb-bc9c-568d9f285a4f | note | Quantity - max 706 m
285a8744-aa82-5fd8-8d2e-f75f9309124b | note | Frequency / When? - Continous, in accordance with observed groundwater conditions
95f87df8-2944-56da-b9dd-f9775cec4fb8 | note | Inspection / Test Method - Secific approval should be given by the Engineer
32945b1b-c5fa-5868-86d8-39dbe8227315 | note | Records / evidence, WCL form - NTE, NTC
28b8a7f4-ecf7-56d5-9ab1-f0aefd1ba4df | note | Standard - ICC STANDARD SPECIFICATIONS
5ac9756a-1f16-55aa-b725-2ebf48e5632b | note | Print, sign and date: Wilson - YES
57c1e2be-478c-5459-954a-7d8ac1b68dc3 | note | Print, sign and date: ICC - YES
dfbfc09a-f8c6-4df5-8b59-515164c1bcc7 | checkpoint | 30 - D2.7.3, D2.5.1
d818d91a-2d8c-59f1-8f3f-656ede8cf9a0 | note | Inspection / Test Point - Pipe installation open trench (main: F25402 - F25410)
751489c4-a0e6-53ee-b253-b9a11a04d71e | note | ACTION (W, M, H) - M
a0a4c02c-3455-50c7-bfc2-0275be4c0085 | note | Activity by - WCL
3a2e5e4e-fec1-51bc-94dc-95363fcfaaff | note | Conformance Criteria (What's Required) - +/- 30mm (horizontal)
a49453e5-21c3-5087-aec8-fd3ce25a548c | note | ○ +/- 5mm (vertical)
70fd079f-eb77-5ca5-a4bc-8bee541045f6 | note | ○ joints as per manufacturers specifications (lubrication, chamfering, whiteness marking, etc)
524e7087-124b-5b76-b59b-0f9faf131cdf | note | Quantity - 651 m
063e85ac-b538-557d-9643-ee45136a0f45 | note | Frequency / When? - Continous (pipe laser)
efd1aafc-bee0-5743-b44a-6444da646d61 | note | ○ 1/20 m (independent optical level)
25c96461-2d99-557f-a4d4-292e4d71dd25 | note | Inspection / Test Method - Using calibrated pipe laser, Optical levelling
71a1cbf9-6bf9-509b-b01a-76b92ad9aa60 | note | Records / evidence, WCL form - Sign this ITP, Leveling record
1c95d995-ec32-5435-a501-c1f1a7899507 | note | Standard - ICC STANDARD SPECIFICATIONS manufacturers specifications.
9cad5395-394b-5529-80fb-d5b9a0beee36 | note | Print, sign and date: Wilson - YES
6179ae08-5986-50dc-b7c7-547ae481e7d3 | note | Print, sign and date: ICC - YES
e505a7cb-95b2-4ca9-bb27-9ed24927d923 | checkpoint | 31 - D4.4, Fig. D3, Fig. D4, Fig. D5
d51f81cc-d8d3-5fe9-b194-851b38c5e8e3 | note | Inspection / Test Point - Pipe installation (lateral)
ce9865b8-91af-5a30-bed2-d76b8f8ddb0c | note | ACTION (W, M, H) - M
631176cb-aacc-5b3f-b4b4-054f2c22c212 | note | Activity by - WCL
a0e2fcaf-9837-501e-acea-a3c3f4a07437 | note | Conformance Criteria (What's Required) - grade: min 1:100 (with laser)
ad71ecae-44c8-5e1f-a9b1-4dcc9c1aaf08 | note | ○ min 1:60 (with dumpy level)
312249f5-75e1-5694-ad30-74d4a16328d9 | note | ○ Connection to the main: 45° reducing wye
1c37434e-ff29-583d-a72c-acc0e25e99a9 | note | ○ Concrete haunching: 25 MPa
0de832c6-9872-5a22-bf7e-fc08bab848b9 | note | ○ Connection at boundary: slip coupler/plumbqwik
50e1f772-a60a-54aa-8b58-422e7643731f | note | Quantity - 58 lateral, 780 m
26b6ed5e-c06a-5174-948a-c2ac6f89b924 | note | Frequency / When? - Continous
deeb238d-e1d3-56a4-ac4e-280cca353736 | note | Inspection / Test Method - Measurement Document
79060308-5869-5010-9710-cf30efc14124 | note | Records / evidence, WCL form - Sign this ITP, Detailed Drainage Connection Sheet
c2c635b1-798a-5b2e-91f6-166d955d0f68 | note | Standard - ICC STANDARD SPECIFICATIONS
d3106b80-93c1-515c-8cb0-0eba258dd5c3 | note | Print, sign and date: Wilson - YES
2750f6a4-b25f-5441-88b7-73dcd3361f97 | note | Print, sign and date: ICC - YES
2a7a66c9-be60-4e01-800e-e25fc513ab75 | checkpoint | 32 - D2.7.6
609242dc-9389-5585-96a5-cee22c584b4a | note | Inspection / Test Point - Bedding - DN300 main (F25402 - F25406)
c17d0f14-9e56-51dd-9842-4be00ebb3b59 | note | ACTION (W, M, H) - M
89eccabe-2c3d-504d-ac8d-c36676b3357a | note | Activity by - WCL
4c3938bf-da23-5f3c-b8a8-8c308226de72 | note | Conformance Criteria (What's Required) - lb (depth below): min 100 mm
826c9a50-40d0-5240-a968-ba7de7eb589f | note | ○ lc (width beside): min 200 mm
df9fda41-6188-56b8-8153-c998a0cd4866 | note | ○ lo (depth above): min 150 mm
343f2ac6-85de-5b2f-810d-69764efcada6 | note | ○ compacted layers not exceeding 1/3 of the pipe OD
b55907ba-b48f-59a8-b36c-56444b0d1d7d | note | Quantity - 328 m
9a9a88f9-5ef9-54c9-ac92-2bb2ea3aa4b5 | note | Frequency / When? - continuous
862f07bb-5863-563f-bb96-bfcf4c798db9 | note | Inspection / Test Method - Measurement Levelling
b9b24d3a-f4f8-5abd-8901-99762ef216d7 | note | Records / evidence, WCL form - Sign this ITP
59bff15e-a731-529f-a47c-10df2ebee74d | note | Standard - AS/NZS 2566 table 4.2.
1b9e4bc2-4a6a-5e82-86ce-b672193f9438 | note | Print, sign and date: Wilson - YES
d79f00d7-73a1-57fe-bd7c-62147c170fbc | note | Print, sign and date: ICC - YES
159ca7d7-bb5d-43de-9a47-41bc56df1edb | checkpoint | 33 - D2.7.6
78a64614-4539-594f-b033-ab4f893f8817 | note | Inspection / Test Point - Bedding - DN225 main (F25406 - F25410)
1f126f0d-4c25-5fa6-a4a7-2c0f9322dec2 | note | ACTION (W, M, H) - M
b124df8b-1dd2-5090-9932-b0a6de431290 | note | Activity by - WCL
2d8285c4-82b1-59f3-892c-12262c273b75 | note | Conformance Criteria (What's Required) - lb (depth below): min 100 mm
cbf8389c-2710-53b2-a660-b26bd2e0295f | note | ○ lc (width beside): min 150 mm
0dc82cd0-3ec7-5ffd-b200-fd05f4ab74db | note | ○ lo (depth above): min 150 mm
9e28ca2d-c125-5651-8646-0d95565d24fb | note | ○ compacted layers not exceeding 1/3 of the pipe OD
bccaf07d-f163-50ec-9a2c-b4bb5406c7b7 | note | Quantity - 378 m
ab9d6b50-a98b-5632-acf1-b6acc3e6204d | note | Frequency / When? - continuous
7b413bd8-84a2-5b3e-a291-4e1f1e7d0156 | note | Inspection / Test Method - Measurement Levelling
943fdf23-2e2a-5ee0-9c47-4ca675f2e599 | note | Records / evidence, WCL form - Sign this ITP
eb51e28a-29ec-57c1-8dc7-3e62ffc0ae47 | note | Standard - AS/NZS 2566 table 4.2.
7175c649-7e57-573d-8c78-028d6b978152 | note | Print, sign and date: Wilson - YES
6944d854-75ec-5143-8141-aba75372dc01 | note | Print, sign and date: ICC - YES
9bac2007-3af8-4072-b793-d38107b7f8fb | checkpoint | 34 - D2.7.6
aa9f0270-0061-5387-ac12-7fca3945d001 | note | Inspection / Test Point - Bedding (lateral)
544c0ebc-d20a-5631-bb28-4a9c2e42e755 | note | ACTION (W, M, H) - M
2f9efa02-403f-5e0c-b633-2e27c2ae6759 | note | Activity by - WCL
644039ed-72e4-5a3d-ae82-2cbb97c3df2b | note | Conformance Criteria (What's Required) - lb (depth below): min 75 mm
693e23dd-aefc-5c9f-b31f-d32a2acd4842 | note | ○ lc (width beside): min 100 mm
5c1bb590-c3f0-5507-a3c3-79881bd185c8 | note | ○ lo (depth above): min 100 mm
230ca248-5610-5c45-9d70-2b5307117919 | note | ○ compacted layers not exceeding ⅓ of the pipe OD
9bb5548e-9a75-50ec-adac-9c57581af26c | note | Quantity - 780
e8e4395b-8fcf-58ff-b8b4-09049158e4bd | note | Frequency / When? - continuous
05daa0b6-93dd-52f4-a934-0c354fcb2d46 | note | Inspection / Test Method - Measurement Levelling
3502f539-dc38-5c2a-8a04-f2baf797f024 | note | Records / evidence, WCL form - Sign this ITP
69949970-9dee-5a61-8390-e54fb3134414 | note | Standard - AS/NZS 2566 table 4.2.
a8c79d3f-b707-5be2-9128-cce4eedadf53 | note | Print, sign and date: Wilson - YES
a4374d56-f5bd-5e4e-8737-810c274fe8e2 | note | Print, sign and date: ICC - YES
b853f04b-3863-4be6-8159-24dda065e206 | checkpoint | 35 - D18, Fig. D12
0b8d06dd-a329-5cdb-b1be-655442a7505b | note | Inspection / Test Point - Manhole (D1050)
ce9ffc58-d086-5cc7-aa55-9fa2538b455a | note | ACTION (W, M, H) - M
791fc691-acfa-5116-87c6-bf4b2edef935 | note | Activity by - WCL
004aedc1-e61b-53f9-8001-41c9dba7e80a | note | Conformance Criteria (What's Required) - neck depth ≤ 315 mm
b20678df-d7ec-568b-ac3e-fc00d4a55030 | note | ○ in-situ concrete packing
1c14d50c-04c9-54bb-bf58-1b4adba6b776 | note | ○ flexible joint located within 1 metre
24ddd71b-8b68-5ec5-9c84-c1979ba64275 | note | Quantity - 8
a91da2c7-4c7c-5bad-81da-60f0e99a0402 | note | Frequency / When? - 1 / manhole
554c994d-d24a-51e7-bfc7-8293a8b36d3f | note | Inspection / Test Method - Measurement Levelling Document
635d84fa-ab3a-510a-9286-e6000fe33487 | note | Records / evidence, WCL form - Sign this ITP, Manhole Inspection Sheet
478f81a5-3d40-51d6-baf8-4ae1a08c13f0 | note | Standard - NZS 3109:1997
31857876-eaa6-5ede-8a21-5bc2da17dd52 | note | Print, sign and date: Wilson - YES
e24133b9-605b-577e-a216-37830b529990 | note | Print, sign and date: ICC - YES
cfce5f1f-d17a-42be-a368-5c555967dfd3 | checkpoint | 36 - D18, Fig. D7
4f8259d1-d354-54eb-885b-aee5a256b23d | note | Inspection / Test Point - Cleaning eye
8ab880ea-8a20-5b44-9228-881397f58138 | note | ACTION (W, M, H) - M
7312a9f0-6c08-5719-858e-8f10240b724e | note | Activity by - WCL
063c80e2-81d7-5397-b1da-1e6c837f2714 | note | Conformance Criteria (What's Required) - as per Fig D7
7a4c9e41-ec8a-5457-aa22-8fc33e9f98ef | note | Quantity - 1
16f28e6d-685e-5f68-a0d6-6b61ae016e7c | note | Frequency / When? - 1 / installation
213435a9-23d9-5c78-b798-024c4242002c | note | Inspection / Test Method - Visual inspection Measurement
1f2c6c25-20ec-5c36-a3a1-96629f3d78cc | note | Records / evidence, WCL form - Sign this ITP
2c7b7783-d277-521d-9ae8-1e82d924b89b | note | Standard - ICC STANDARD SPECIFICATIONS
60d21a1f-d344-5da4-8992-6116c418ed03 | note | Print, sign and date: Wilson - YES
c988cc71-2c97-5439-aa5d-9f0273aeecbc | note | Print, sign and date: ICC - YES
f6e3e96f-a466-4c8e-bc24-385d91e8631c | checkpoint | 37 - Fig. D13 - D16
db6cb0e5-69da-5b08-b32f-d7eaa4d6cabb | note | Inspection / Test Point - Service cover (manhole)
18a8cea7-1641-5562-b200-e377c07e7210 | note | ACTION (W, M, H) - W
8f105d1e-4234-5ef5-ac38-5b5e4759e4ff | note | Activity by - WCL, ICC
0002c34c-072a-5406-bd29-7fc3773f2176 | note | Conformance Criteria (What's Required) - Cover levels to be adjusted to existing surface levels (+10mm, -0 mm)
fc408c5e-c699-526f-9cdf-09e8f5c73192 | note | ○ 25 Mpa concrete packing
952c6d64-5851-5a25-8793-4639637b753d | note | Quantity - 8
cd1aef4f-3a9a-5f6c-9ed1-1fa04446b96b | note | Frequency / When? - before surface reinstatement
4fea3932-a008-5fac-9951-a14e2c9d7a3f | note | Inspection / Test Method - Visual inspection Measurement
0feceb12-9d8f-5d1c-96d8-3d31493e3229 | note | Records / evidence, WCL form - Sign this ITP
c040232b-6b5f-5612-9241-1507afcbdb40 | note | Standard - ICC STANDARD SPECIFICATIONS
b8af4482-b339-5313-ae57-dd95709313bb | note | Print, sign and date: Wilson - YES
bd737c75-b3d3-56a7-bdd3-173137d61c53 | note | Print, sign and date: ICC - YES
88303b41-73fb-4e61-af10-5b1396f67759 | checkpoint | 38 - D15, Fig. D7
49ecbf3b-069e-54d2-8997-4cef98052d07 | note | Inspection / Test Point - Service cover (cleaning eye)
8e9953cf-b280-5692-bf22-a62dbb54adb6 | note | ACTION (W, M, H) - W
74f852f3-b267-5be5-8d2d-955b4ddd3dca | note | Activity by - WCL, ICC
fe41bd22-e727-5b7a-9286-c0146ead7e1b | note | Conformance Criteria (What's Required) - Cover levels to be adjusted to existing surface levels (+10mm, -0 mm) perpendicular / parallel the road alignment.
cb45f68c-9429-58fa-bbdd-c890e8ad8e9f | note | Quantity - 1
c72f9660-ff0f-5d5c-8fbc-90ac856c8da4 | note | Frequency / When? - before surface reinstatement
33f26abe-0042-5993-b462-8fca3947c34c | note | Inspection / Test Method - Visual inspection Measurement
5d2ddfdd-ea61-55ec-bbdc-65a216ea1d4e | note | Records / evidence, WCL form - Sign this ITP
e3b9da97-0a9c-5ebb-b4cc-5f9c0be161e4 | note | Standard - ICC STANDARD SPECIFICATIONS
2fd37edc-dcf0-5a11-89cd-cfa19ba2f3f9 | note | Print, sign and date: Wilson - YES
00ef8190-1802-5a5f-8b38-3ddbd2df07c1 | note | Print, sign and date: ICC - YES
64246f20-c6e4-4298-ac72-3314a64dae05 | checkpoint | 39 - D2.9.2
a732a2b4-cfb0-5b10-a14e-25a6cd50ea2a | note | Inspection / Test Point - Pressure test
41513b7e-99d8-50fa-8c6c-bb63f84bfdf3 | note | ACTION (W, M, H) - H
2b56f9ab-5a4a-59ea-b650-c82498e98eaf | note | Activity by - WCL, ICC
614d1590-66e5-54c9-b6e2-e347760d2622 | note | Conformance Criteria (What's Required) - (Main + N side laterals) + (S side laterals)
408af10b-2386-5ff5-bad8-51d0c47c962c | note | ○ Test length: as per table 6.1 AS/NZS 2566.2
6a757083-1348-57f0-8228-25dcc8179e59 | note | ○ Pressure: 25kPa
e8e8beff-62b9-54c4-ae63-595489c81299 | note | ○ Pressure loss < 7Kpa
d44f473d-14d2-54a1-b3dc-02b5a968d3f3 | note | Quantity - 8 section
9ffd7069-e602-5021-806f-789f5afcabbd | note | ○ 35 S side lat
5c7f3e44-8b0c-5865-ab36-f327c5d8648a | note | Frequency / When? - 1 / section (manhole to manhole)
17bf7250-ddd4-5238-902a-c25fd8000838 | note | ○ 1 / S side lateral)
9a264521-cdbd-50df-a2ea-4aecbf4dec16 | note | Inspection / Test Method - Low pressure air test
8009e9f6-4d84-5529-8e74-990209a17ed2 | note | Records / evidence, WCL form - Sign This ITP, Pressure test report, FM-119
f79008e3-8782-5830-a749-36b94bf70d55 | note | Standard - AS/NZS 2566:2:2002 6.4.2
2840049b-9882-56c1-b690-18f155846ed1 | note | Print, sign and date: Wilson - YES
1a3f2cfe-3101-5068-9f1d-cfa2f9def791 | note | Print, sign and date: ICC - YES
c0357e29-0b57-4af6-a23a-2d0908685b6b | signoff | HOLD POINT
bc737a71-23dc-4cec-923c-68ec36e4ae99 | checkpoint | 40 - D2.9.3
d0d17373-ded8-5f18-a5cc-cc224d49e4ce | note | Inspection / Test Point - CCTV Inspection and Cleaning
096710e1-4dee-5252-b253-edaa973284d0 | note | ACTION (W, M, H) - H
c1836164-f893-59cb-8884-23df14e64c3e | note | Activity by - WCL
debde6e6-e227-5590-ae95-7da68ed40f54 | note | Conformance Criteria (What's Required) - to confirm that the lines are free from debris and have no defects
da89f270-43ae-5dce-ac88-4321fc2e1148 | note | Quantity - 736 m (main)
cd078beb-4391-5b35-a8b9-204a67ea0a4c | note | Frequency / When? - prior to the final surface reinstatement
dba16999-2931-5a67-8d38-a155f12c5d5d | note | Inspection / Test Method - CCTV inspection
0fd7f96a-7354-50b0-b4da-66e206369ab3 | note | Records / evidence, WCL form - Sign this ITP, CCTV survey
609b45ba-3cb9-5f0a-b1e5-c03c11e4d9fe | note | Standard - New Zealand Pipe Inspection Manual AS/NZS 2566:2
3f438aae-29f1-585e-a5e8-ba7d1b025b0c | note | Print, sign and date: Wilson - YES
c034a2cf-689c-5946-a2d2-96d4c4cf41d5 | note | Print, sign and date: ICC - YES
66f0ad7b-dfe5-47a6-adac-9cb2c5cf7459 | signoff | HOLD POINT
03029858-6a78-45ca-b155-b7bc016d268b | section | Surface reinstatement
637b41d1-c6ff-46bc-8598-6878d8543f42 | checkpoint | 41 - D13
84686bc9-b1de-5d16-ab9c-afc8125d64bd | note | Inspection / Test Point - Landscaping
b3e14f24-307f-54e6-8b3c-bb7c05b1fd8f | note | ACTION (W, M, H) - W
9721bcf3-8fd4-5b74-bb3b-8db32ccde6f2 | note | Activity by - WCL
f5643ccd-c261-52a6-973f-0cfab6aa1ff2 | note | Conformance Criteria (What's Required) - The final surface in the berm area should match the existing levels
4ca7480a-4d81-54c7-9ba6-87a328851547 | note | Quantity - 58 laterals
43d9462f-22e4-550e-a894-848d5adb2703 | note | Frequency / When? - following lateral installation
032e6855-bd6a-5c59-ba82-cab95c61b381 | note | Inspection / Test Method - Visual inspection Levelling
639dd785-4d7b-5900-9437-70f3c5df1e8a | note | Records / evidence, WCL form - Sign this ITP
d028f08a-5176-5d37-a805-e433bd543efe | note | Standard - ICC STANDARD SPECIFICATIONS
ed8e957d-c254-56a5-b560-584f54275a93 | note | Print, sign and date: Wilson - YES
d60deff1-5b43-5f57-86b2-bdf97e207cdf | note | Print, sign and date: ICC - YES
1753e0dc-c9e9-47c4-b500-f8a8ea365e66 | checkpoint | 42 - D13.7
c1a63c43-836e-5388-bf73-9decb09ff288 | note | Inspection / Test Point - Grass seeding
2616b60c-b818-504d-b793-8a613a022f33 | note | ACTION (W, M, H) - W
2c335248-a795-5f18-a0e6-f872fa8d250c | note | Activity by - WCL
5f89b70f-79ff-5b56-94e3-3bfe4ad3363d | note | Conformance Criteria (What's Required) - approved seed mixture, 35 g/m2
a73b9c92-4a26-5093-a846-56a6089cf532 | note | Quantity - 58 laterals
53cc1707-8ae6-557d-b01f-35e9403fd8a1 | note | Frequency / When? - following landscaping
b4866425-db45-572e-a127-06038f6c30d6 | note | Inspection / Test Method - Visual inspection
7f8a37c1-a546-593e-843b-87136cda6dc0 | note | Records / evidence, WCL form - Sign this ITP, Blending docket
287d2344-5443-5bb5-89be-45119ab25a8e | note | Standard - ICC STANDARD SPECIFICATIONS
2a6a41a4-23aa-55d7-800a-db7799a2823e | note | Print, sign and date: Wilson - YES
81e53f00-54f4-581b-83bb-c71b21ba204f | note | Print, sign and date: ICC - YES
9db1665d-18e2-4315-b37e-d3a293536612 | checkpoint | 43 - D2.7.7
2b9e9a26-cfd5-5614-b140-cc7a632ecf9f | note | Inspection / Test Point - Subbase (AP65) compaction
37da6d6b-0ee1-510c-bf19-da9f95e0572b | note | ACTION (W, M, H) - H
d2b16bf4-8438-5a69-9401-f07001c8036c | note | Activity by - WCL
9018d273-70f5-528e-b998-4e3c97c1f862 | note | Conformance Criteria (What's Required) - Carriageway:
0ad53d5d-ee27-5d29-bbc8-b769d9ff900f | note | ○ 0.3 - 1.5 m deep: min 35 CIV
84c08999-aaed-5234-85fa-fcdf712630c3 | note | ○ > 1.5 m deep : min 25 CIV
710a8c33-a3f6-5790-9b1d-3af65cd6ce2c | note | Quantity - 706 m (main), 700 m (lateral)
9bf2074d-6bba-5ec3-aea9-4db1cdd88645 | note | Frequency / When? - During installation, every 200 mm layers at 6 m intervals for all trenches in carriageway above main and connections
1ba5ee61-54e1-54c2-a7ab-f8f858f1f55e | note | Inspection / Test Method - Clegg test
b5a9234a-2751-5d1a-beab-b437c24be826 | note | Records / evidence, WCL form - Sign This ITP, Clegg Test Result Sheet
058eed07-2f26-580c-92fa-2722a8d15667 | note | Standard - ICC STANDARD SPECIFICATIONS
ff02e237-8ff6-58ba-86e8-f5807b6bdd55 | note | Print, sign and date: Wilson - YES
17a4d9ff-18ce-58fd-b597-ae5a2e5e6931 | note | Print, sign and date: ICC - YES
1af7d6d8-ee84-498c-86cb-56a74eee678b | signoff | HOLD POINT
714c8bf2-bef1-4c29-9dee-897926ca8113 | checkpoint | 44 - D2.11.5
903a6588-cdbf-5dac-8b09-f09756cbc8df | note | Inspection / Test Point - Subbase (AP65) compaction
6a7c127b-116b-5bed-95d2-3a978fb8f643 | note | ACTION (W, M, H) - H
aab3737e-4fd1-5a33-8f74-d0f050c4d09b | note | Activity by - WCL / Lab ICC
a9b1bf5a-8643-5ebb-b2ad-c1acc4d8e987 | note | Conformance Criteria (What's Required) - 95% compaction rate
bc282ca3-5004-5375-8825-9eaa86856daa | note | ○ It is not required to complete NDM testing on connections
45de363a-7905-56b3-8c4f-07a7dcde45ab | note | Quantity - 706 m (main)
4c8da54c-77bf-5986-891f-8ad1702363a6 | note | Frequency / When? - At pipe laying commencement and reconfirmed at 120 m intervals for open trench every 200 mm layers
3cf6d06a-6765-53f6-bc51-97a85541227b | note | Inspection / Test Method - NDM test (direct transmission)
b3f91c45-5a88-5ffa-8078-4f01ebe10df9 | note | Records / evidence, WCL form - Sign This ITP, NDM Test Result Sheet
a97f9353-bfed-5953-b5e4-07c65feadf1b | note | Standard - ICC STANDARD SPECIFICATIONS
6e0c89f3-f5ca-5a2b-91ad-6cd6183e8970 | note | Print, sign and date: Wilson - YES
fe6c42ac-5b70-5c8b-a2ab-c13fdbca039a | note | Print, sign and date: ICC - YES
700d7c2a-d658-4d39-be29-9d899888c8f2 | signoff | HOLD POINT
f5383153-b63e-4861-afb7-8fb9e6a54c6e | checkpoint | 45 - D2.7
cdf17812-968f-505c-80c2-43a7f5e0e059 | note | Inspection / Test Point - Basecourse (AP40) compaction
5216683d-fa25-5449-8097-e16fdf5bd8b8 | note | ACTION (W, M, H) - H
905489fe-2f6a-569a-953e-962c46b0d5f0 | note | Activity by - WCL / Lab ICC
0a06951b-0a3e-5467-add0-a56fff670ae7 | note | Conformance Criteria (What's Required) - minimum depth of 150 mm
94f776e3-2edf-52a8-ad0c-ad082bfa73fc | note | ○ 98% compaction rate
a0308e83-5212-5c2f-87bc-1da0cceef704 | note | ○ It is not required to complete NDM testing on connections
fe24dd59-c7ff-5519-abd7-4b7796d6ff6f | note | Quantity - 706 m (main)
da50afb1-98ba-5560-8e54-e0736ba943d1 | note | Frequency / When? - 1 / 20 m of trench including one test at the start and end of the trench
11a54349-d273-56e6-aec5-935cd7175f7a | note | Inspection / Test Method - NDM test
5d494fbd-2ef1-5ac9-b2f3-808b487969c0 | note | Records / evidence, WCL form - Sign This ITP, NDM Test Result Sheet
92cc71f3-0496-560f-a072-50ab25f6091f | note | Standard - ICC STANDARD SPECIFICATIONS
90cee707-493c-5547-b7b6-8705ef275e28 | note | Print, sign and date: Wilson - YES
3ddc9676-60e7-50eb-8b53-b6e879cb63ae | note | Print, sign and date: ICC - YES
ce9f3d61-2e4e-4062-946d-0db051e245f4 | signoff | HOLD POINT
39d5570e-e826-4b4a-9686-0983fe0b869b | checkpoint | 46 - D2.8.3
5d380fc5-0da6-5c31-a67b-a8357aedb7aa | note | Inspection / Test Point - Trench reinstatement - marking out saw cutting
5e9d74fd-93ad-50fa-9950-917ba745fcaf | note | ACTION (W, M, H) - H
6afa2416-c8b9-57fb-ae47-06a10497c807 | note | Activity by - ICC
5d122643-6deb-5880-8242-04e35922739a | note | Conformance Criteria (What's Required) - Engineers rep to mark out saw cutting required
1cacc905-e0b6-5436-bc47-0fb496c00a5e | note | ○ 150 mm overcuts
fc616708-d937-581f-854f-1089e6da2021 | note | ○ 1 m rule
da7ccee1-52e5-5fa5-af29-2c2ae9ed96c4 | note | Quantity - 706 m (main)
d8f1b3a9-c09f-5351-a4eb-21d396e69db0 | note | ○ 700 m (lateral)
2f117fff-a065-5151-ad47-56cb7af40961 | note | ○ 58x1 m (footp)
9754e184-b037-584c-8314-b79a4b3eeced | note | Frequency / When? - Prior to sealing
8e972f58-8bdf-558e-a4a6-685b0cd569dc | note | Inspection / Test Method - Visual inspection, measurements (1 m rule)
fd78f973-9042-5358-a090-755639a8eefc | note | Records / evidence, WCL form - Sign This ITP, Pre seal inspection record (FM-114)
ae7c5688-6eb0-56fc-8ff0-067a0326fa22 | note | Standard - ICC STANDARD SPECIFICATIONS National Code of Practise for Utility Operators' Access to Transport Corridors
47851142-a5a8-5268-a1f5-72f3f8656d22 | note | Print, sign and date: Wilson - YES
362a3ae2-b895-541f-be21-0aaf29b82519 | note | Print, sign and date: ICC - YES
257748a2-ceb8-4c04-a47c-72b04a34a8eb | signoff | HOLD POINT
2b70e3f3-8f9d-494b-988d-7cde66a96390 | checkpoint | 47 - D2.7.7.2
b3492083-61a2-56f1-b94a-18f6300c0c6d | note | Inspection / Test Point - Basecourse (AP40) geometry
4a50f0bb-a89f-51cc-8227-98eae9e79d75 | note | ACTION (W, M, H) - H
9f0fe0f6-5243-55d1-b0f7-f1d5381bc64a | note | Activity by - WCL, ICC
6a825bfb-07ed-599c-bd31-105c2f2d6146 | note | Conformance Criteria (What's Required) - -5 mm +15 mm
ef924292-5455-585f-a606-94907eb5abae | note | ○ h = 45-65 mm (carriageways)
8bf3eda5-b359-5697-88a4-a78a270f9ba7 | note | ○ h = 25-45 mm (footpath)
2f50ceb8-6ad0-54c3-85fc-6912a2063d2d | note | Quantity - 730 m (main)
240a3c7b-1740-56f3-bbc6-fb7859b5cc15 | note | ○ 700 m (lateral)
57ba39d3-5282-5512-ad57-5f5ce4d8f606 | note | ○ 58x1 m (footp)
4e94205f-4be8-5316-b36f-818bffafaf26 | note | Frequency / When? - Prior to sealing
ca5878e2-1d77-5e0a-b3f5-457c415794bf | note | Inspection / Test Method - Visual inspection String line / straight edge inspection
8f216fa2-0969-5be1-9d7d-5349562d630e | note | Records / evidence, WCL form - Sign This ITP, Pre seal inspection record (FM-114)
03ca1da0-e7f6-54c3-9f83-6da27985f842 | note | Standard - ICC STANDARD SPECIFICATIONS NZTA B/2
faa594a0-f53d-53be-94ea-f9e19765099a | note | Print, sign and date: Wilson - YES
dd5a9015-d549-5e8b-a8a2-026c2dc4419c | note | Print, sign and date: ICC - YES
1281d224-7b05-463d-a731-60525ec5887e | signoff | HOLD POINT
53dcb38e-0e66-406f-8e97-880cf1501cad | checkpoint | 48 - D11.4.3
528f8032-3889-522e-91af-d128bf169080 | note | Inspection / Test Point - Membrane Seal
faf2c21c-fe02-5ace-926c-bae30c837b01 | note | ACTION (W, M, H) - H
d4e4d7de-7a02-5f15-997b-a69113f6fdfb | note | Activity by - WCL, ICC
2341e796-0c6b-524d-93b9-362479d7cf17 | note | Conformance Criteria (What's Required) - Residual bitumen application rate:
91a48d6c-a21a-5eb1-9d80-7fb0a2da4f0b | note | ○ 2.0 l/m2 +/- 10%. (spray truck)
38c7c12c-b5b8-582e-82d3-4029c86a5d6b | note | ○ ≥ 1.5 l/m2 (hand operated sprayer bar)
dc921ede-209c-5eef-93fd-1d3f11c3df9e | note | Quantity - 706 m (main), 700 m (lateral)
6ee46f12-6012-5fb9-b354-9206054523e8 | note | Frequency / When? - Prior to asphalting
eceb4b26-966b-52e9-98a2-ceebc554bc77 | note | Inspection / Test Method - Visual inspection
2a272f23-d84a-5314-a66f-588fec430d08 | note | Records / evidence, WCL form - Sign This ITP, Delivery docket
ab403f9a-d477-5c77-b3f8-0c6b04afed98 | note | Standard - ICC STANDARD SPECIFICATIONS
dee825c6-fc31-5193-9b12-cfe586f002f7 | note | Print, sign and date: Wilson - YES
1d660995-f92b-5a73-a15e-bdce7f4101fb | note | Print, sign and date: ICC - YES
9a4c81d3-0517-4657-ab30-92ca14e7db8b | signoff | HOLD POINT
266cc0cd-c35f-4db3-8489-fb0d1352cdf4 | checkpoint | 49 - D12.5
1e216a69-9c5c-5227-a058-f45aca5d9642 | note | Inspection / Test Point - Asphalt paving (carriageway)
533d7c9d-ef0c-565b-9a5d-81c7df5f17ca | note | ACTION (W, M, H) - H
a07922fc-915a-564d-ae3f-a92e1c18db00 | note | Activity by - WCL, ICC
68106f67-bf21-5e6a-976e-00bdd27faf2b | note | Conformance Criteria (What's Required) - trenches wider than 1.5 m shall be paver-laid
eac6f985-09af-5bb7-93d6-e7117504ec96 | note | ○ 5 mm from a 3 m straight edge laid longitudinally
5916cb7b-0bfc-51b4-a9ea-0da007c76fdc | note | ○ 5 mm from a 1 m straight edge laid transversely
01a44dd5-ff6f-5dd1-842d-07fb7d9e84a1 | note | ○ lips ≤ 5 mm (where it joins existing seal)
8b3e1136-b305-52d1-bb30-5552c41de7c0 | note | Quantity - 730 m (main), 700 m (lateral)
da8a0fd8-f4bf-595b-b97a-f4606f542bfa | note | Frequency / When? - 1 / finished surface
be6c2169-486a-5fbe-bae5-9a9f35baa178 | note | Inspection / Test Method - Post seal surface inspection
5a0c2af5-31a9-5132-9fe6-8ade8e6c6c60 | note | Records / evidence, WCL form - Sign This ITP
eaba3441-84c7-54f8-903b-c816d70b0fd8 | note | Standard - ICC STANDARD SPECIFICATIONS
5e5c48c5-a40f-565a-9e94-2a8e4f4fec7a | note | Print, sign and date: Wilson - YES
22a140e3-1664-5890-8623-becbcfd0954d | note | Print, sign and date: ICC - YES
54a20360-0242-472a-9d51-b6df7a312fb7 | signoff | HOLD POINT
5396fb3b-1f4f-493d-abfd-d9faf3b0b965 | checkpoint | 50 - D13.6
f3e93689-8080-52c7-997c-a7dedf5dc45d | note | Inspection / Test Point - Asphalt paving (footpath)
45161e5a-48a6-52d7-be8c-30b06d2113c9 | note | ACTION (W, M, H) - H
f9a12050-c318-595d-a2a2-75e1b1ecb031 | note | Activity by - WCL, ICC
2dd7aacc-8c86-52e5-a741-67882d5ced89 | note | Conformance Criteria (What's Required) - 30 mm Footpaths and Surfaced Frontages
2c62e661-d5d2-54c3-87e8-9cfdf0c3e129 | note | ○ 30 mm Residential Crossing
3739889e-37a0-52a9-a840-41b95cb166be | note | ○ 50 mm Heavy Duty Crossing
c281104e-7c0c-5faa-875f-943cec5650a0 | note | ○ 5mm above kerb edges, and flush with property vehicle accessways
cc51142c-72eb-5add-97fa-5829ed240b2f | note | ○ The gap under a 3m straight-edge placed longitudinally shall not exceed 5mm
daafa132-d57e-557a-8929-b48bdfce5df1 | note | ○ lips ≤ 3mm
c08b5f5b-9ebf-50ee-8661-fe2669c67136 | note | Quantity - 58x1 m
064173a5-cdfe-57d4-928d-6f1c1d864d73 | note | Frequency / When? - 1 / finished surface
c534b63c-cc8c-53d7-ae73-4b6d1f70a26d | note | Inspection / Test Method - Visual inspection, straight edge inspection
93e4b838-30a9-55d4-86a5-8c748d6ec857 | note | Records / evidence, WCL form - Sign This ITP, Delivery docket
c14ced2a-8d7d-503c-88d2-32ca187dcd8c | note | Standard - ICC STANDARD SPECIFICATIONS
8166d6d6-e688-5c89-9c3a-36ccb7a3ffeb | note | Print, sign and date: Wilson - YES
5e5a690c-eb5a-5e70-a2fc-8d11a48ba64a | note | Print, sign and date: ICC - YES
50973c83-47ed-4084-8600-0646f846e704 | signoff | HOLD POINT
8dd8a528-289f-4ce0-bd6c-39f834b63953 | checkpoint | 51 -
dac2ec62-7f75-5459-a612-1774389c0ce0 | note | Inspection / Test Point - Road markings
81848f7f-e219-5319-aecb-497c5c0b6d88 | note | ACTION (W, M, H) - W
01dd4532-49d5-5007-b6af-545597b66730 | note | Activity by - WCL, ICC
d2be10f0-4fba-5f7c-863b-7732fc1e3c80 | note | Conformance Criteria (What's Required) - Reinstatement of the existing markings
0d27de68-646f-5fac-b139-760b3519a41e | note | Frequency / When? - 1 / finished surface
c473dfc2-9986-5d52-a231-5b66b82f7538 | note | Inspection / Test Method - Post seal surface inspection
82ee5065-8dfb-57aa-b5ad-d3dd9531feba | note | Records / evidence, WCL form - Sign This ITP
72f4ba02-3e65-5ae3-bdf7-177b1c5d96e0 | note | Standard - ICC STANDARD SPECIFICATIONS
fecab3e7-5daf-5c24-912d-6fd924968e18 | note | Print, sign and date: Wilson - YES
ce1b7e61-1dcb-5c84-b8f0-ba19ae373e03 | note | Print, sign and date: ICC - YES
f86a4b83-0569-4c8e-9758-f542dd3a4e20 | section | Completion
6f448b09-feea-4447-90be-408ea9a5acf4 | checkpoint | 52 - D17
df41283c-bfb7-59d3-b898-b6273df720c2 | note | Inspection / Test Point - As-built information
0b9c6d29-a50c-5904-8b29-91dd4843650f | note | ACTION (W, M, H) - H
98377f69-4e58-5328-9b8f-3baf59afd153 | note | Activity by - WCL
b16c0133-bcc0-5889-8ce0-25c333285566 | note | Conformance Criteria (What's Required) - Encountered Services Record Sheet
1f6caf53-a865-575a-9c74-34656a1021ab | note | ○ Detailed Water Connection Sheet
03872028-9abf-555a-915b-e6dba7146080 | note | ○ As-built drawings as per D17
f3e14d84-226a-55f7-977e-70a1f0e3931e | note | Frequency / When? - Following/during completion of works
cd554443-5066-5e01-bd09-ad7df30b2665 | note | Inspection / Test Method - Document
fc33f414-ecd9-5021-9535-b7c5a6afec45 | note | Records / evidence, WCL form - Sign This ITP, DWCS, ESRS, As-built
fe5430ba-a0ed-5c65-b7b8-91109c747acf | note | Standard - ICC STANDARD SPECIFICATIONS KiwiRail specifications
2f2977cc-6ea0-5059-b409-b0d4d9b12476 | note | Print, sign and date: Wilson - YES
4aa92080-ec8e-5fe0-b21f-035fe2622bb1 | note | Print, sign and date: ICC - YES
f9966bb5-e041-4345-8a27-e58a48f789c9 | signoff | HOLD POINT
f5173616-863d-4571-8bcb-d8236a231a48 | checkpoint | 53 -
95e15d10-a1bd-5c5c-8d08-ee57da3c397e | note | Inspection / Test Point - Works Completion Notice
e6132124-fc8a-5e51-b429-c5a957ca1141 | note | ACTION (W, M, H) - H
80534755-b34a-5060-b28f-f55030801775 | note | Activity by - WCL
72d67662-79c0-5bd9-8442-20e30b888748 | note | Conformance Criteria (What's Required) - KiwiRail + myWorksites
bf539a4f-6bc1-5996-8812-c6ea25dfbfe6 | note | Print, sign and date: Wilson - YES
d3740c25-eeb0-5bfc-81c7-6d1b8b1dd60f | note | Print, sign and date: ICC - YES
86fed348-db20-4e4c-9be4-20e9445c77e2 | signoff | HOLD POINT
50ff4590-fee6-44e2-ba0c-674f4467757e | checkpoint | 54 -
8a52172d-d480-577f-b181-8bf376ace66d | note | Inspection / Test Point - Site walkover
beaa86ed-df0e-57af-87fb-570444381369 | note | ACTION (W, M, H) - H
5d541ec4-a255-5492-8d7d-244923114693 | note | Activity by - WCL, ICC
68d62e5c-b092-5bc3-b9d3-be89d823f757 | note | Conformance Criteria (What's Required) - Snag list to be compiled, and completed
4ca3dd5b-bd18-554f-8e9f-6210d7f7482a | note | Frequency / When? - At Completion
ac9f9f74-43bc-5e76-8656-fccd28fdc418 | note | Inspection / Test Method - Review
389c086f-c8dc-5bf2-9ba7-3b849d4eb7b0 | note | Records / evidence, WCL form - Sign This ITP, SNAG List
baf731b0-6969-5a3d-93d9-1f6fc0488023 | note | Standard - ICC STANDARD SPECIFICATIONS
e6b944b2-d705-53f3-aa23-39628710cf69 | note | Print, sign and date: Wilson - YES
e740b610-f7d8-5857-b5bd-5dc04c82924d | note | Print, sign and date: ICC - YES
8cbf926b-7396-4e12-bd9c-d2f3436ec5b8 | signoff | HOLD POINT
9c85ca3a-24ee-49dd-9a5f-8def011c46ea | checkpoint | Signoff
d9667348-4615-5967-bf4e-8837f9178430 | note | Wilsons Engineer
c6f76639-07b3-5f56-a0a9-e259a27cc191 | note | Signed By : Norbert Jacsek
1b836f80-a83c-5702-a494-c1306b9ae9d1 | note | Wilsons Contract Manager
84f94cd9-d770-5164-a717-13aa3e75ebce | note | Accepted By : Hamish Lindsay
11952918-db3f-5e31-860d-0d09c982307a | note | ICC Engineers Representative
87a7b047-4160-5ba2-b853-5e19d60979c1 | note | Accepted By : Tom Andersen
804f0158-dad0-4ed2-a589-2b409a5f0aed | signoff | Signature: