## Sheet1
1 | D1.3 | Site Management Plan (QEHS, SSST, KSA) | H | WCL | Ensure Quality, Environment, Health CHAR(AMP) Safety Management Systems Plan Site Specific Safety Plan and Key Step Analysis are approved. Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times. | — | Prior to commencement | Submission (NTE) | Sign This ITP LN-01, FM-83, FM-69 | ICC STANDARD SPECIFICATIONS | YES | YES | 1 - D1.3 | Inspection / Test Point - Site Management Plan (QEHS, SSST, KSA) | ACTION (W, M, H) - H | Activity by - WCL | Conformance Criteria (What's Required) - Ensure Quality, Environment, Health CHAR(AMP) Safety Management Systems Plan Site Specific Safety Plan and Key Step Analysis are approved. Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times. | Quantity - — | Frequency / When? - Prior to commencement | Inspection / Test Method - Submission (NTE) | Records / evidence, WCL form - Sign This ITP LN-01, FM-83, FM-69 | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | 1 - D1.3
Inspection / Test Point - Site Management Plan (QEHS, SSST, KSA)
ACTION (W, M, H) - H
Activity by - WCL
Conformance Criteria (What's Required) - Ensure Quality, Environment, Health CHAR(AMP) Safety Management Systems Plan Site Specific Safety Plan and Key Step Analysis are approved. Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times.
Quantity - —
Frequency / When? - Prior to commencement
Inspection / Test Method - Submission (NTE)
Records / evidence, WCL form - Sign This ITP LN-01, FM-83, FM-69
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES