## res_1630-P200-SYM-QAC-ITP-0013.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0017 Water Relocation | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0017 Water Relocation
section | 1.0 Pre-start activities
checkpoint | 1.1 - Check Survey Set-out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Ensure alignment setout has been completed and pegged.
button | Has all of the above been completed? | Yes,No
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map | Yes,No,N/A
checkpoint-no-status | 1.1.2 - Environmental Permit
button | Environmental permit | Yes,No,N/A
section | 2.0 Materials
checkpoint | 2.1 - Material Conformance
label | Ref docs - AS4130
label | Acceptance criteria - Assets installed are correct type, class & diameter and comply with AS4130 (as relevant) unless noted otherwise.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
button | Remarks/record | Yes,No,N/A
section | 3.0 Depth of Cover
checkpoint | 3.1 - Depth of Cover Requirements
label | Ref docs - VR Clause 706.03
label | Acceptance criteria - Cover requirements for water assets shall be:
label | • Pavement surface to top of conduit minimum 1200 mm.
label | • Invert of open drain to top of conduit minimum 750 mm.
label | • Unpaved areas to top of conduit minimum 600 mm.
label | • As per asset authority requirement for cover to other assets
label | Freq - Each Lot
label | Key - S
label | Resp - SE
button | Remarks/record | Yes,No,N/A
section | 4.0 Backfill of Excavated Trenches
checkpoint | 4.1 - Bedding / Embedment Material Properties
label | Ref docs - VR Clause 706.06 Table 706.061
label | • VR Clause 706.07
label | • VR Clause 706.09
label | Acceptance criteria - Bedding / embedment requirements are to be as specified by VR706 and VR Table 706.061.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record -
button | • Test Report (if applicable) | Yes,No,N/A
checkpoint | 4.2 - Bedding / Embedment Placement
label | Ref docs - VR Clause 706.07
label | Acceptance criteria - Placement of bedding / embedment is to be as per VR 706.07.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.3 - Backfill Material Properties (under paved areas)
label | Ref docs - VR Clause Table 706.061
label | Acceptance criteria - Backfill material properties to be as per Table 706.061 (See figure 1).
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record -
button | • NATA Test Report (if applicable) | Yes,No,N/A
checkpoint | 4.4 - Backfilling (under paved areas)
label | Ref docs - VR Clause 706.06, 706.08, 706.09
label | Acceptance criteria - Backfilling requirements and placement to be as per VR706.08 and VR706.09:
label | – Trench shall be backfilled up to the nominated or designed subgrade level with selected backfill material placed and compacted in layers not exceeding 150 mm loose thickness, and above that level with common backfill material.
label | – Moisture Content between 85-115% as determined in the Modified compactive effort.
label | – The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97% based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
label | – Considerations to be made to allow for Asset Owner Authority working restrictions, including vibratory restrictions.
label | – Detailed proposals for compaction of backfill materials of nominal size greater than 40mm shall be submitted to the Superintendent for review before commencing work
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | SI Key - H
label | Remarks/record -
button | • NATA Test Report (if applicable) | Yes,No,N/A
holdpoint | AUTHORITY HOLDPOINT
section | 5.0 Work Lot Close Out
checkpoint | 5.1 - Test Reports
label | Ref docs - VIC Roads Specifications
label | Acceptance criteria - All Test reports received and reviewed.
label | Any specific asset owner QA documents available to be submitted attached.
button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 5.2 - As-built Information
label | Acceptance criteria - Where applicable, as-built pickup or as constructed drawing been provided to the authority.
button | Has all of the above been completed correctly | Yes,No,N/A
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record -
button | • Survey Conformance Report or as-built drawings to authority | Yes,No,N/A
checkpoint | 5.3 - Product Non-Conformance
label | Ref docs - CQMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record -
button | • NCR reports | Yes,No,N/A
checkpoint | 5.4 - Quality Representative to check the above criteria and records to confirm
label | Ref docs - CQMP Lot Records
label | Acceptance criteria - All above criteria met, and records identified attached.
button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record -
button | Completed Checklist (if applicable) and reports and other compliance records attached. | Yes,No,N/A
checkpoint | 5.5 - Authority Asset Install Acceptance
label | Acceptance criteria - Audit and approval received from accredited SEW consultant.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP