## res_1630-P200-SYM-QAC-ITP-0013.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0037 Rock Beaching Type 1, 2, 5. | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0037 Rock Beaching Type 1, 2, 5.
section | 1.0 Pre-start activities
checkpoint | 1.1 - Conformity and Lot Maps
label | Ref docs - VR713.02 IFC Design
label | Acceptance criteria - Beaching finished surface shall conform to the levels, lines, and grades shown on the drawings or specified.
label | Freq - Prior to start of works
label | Key - I
label | Resp - SE
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map | Yes,No,N/A
checkpoint-no-status | 1.1.2 - Environmental Permit
button | Environmental permit | Yes,No,N/A
checkpoint | 1.2 - Material Approval
label | Ref docs - VR713.03
label | Acceptance criteria - The contractor shall nominate material source, supply specified test results, and provide a representative sample for approval by the superintendent.
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Beaching Material - Type 1 Ungrouted
label | Ref docs - VR713.03
label | Acceptance criteria - Type 1 Beaching material shall be:
label | • Field or quarry rock >50mm diameter and of mass 20-70kg with at least 60% of Qty greater than 40kg.
label | • Placed that the length of rock protection >100mm and the total layer thickness is >225mm.
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
label | Remarks/record - Import Docket
checkpoint | 1.4 - Beaching Material - Type 2 Grouted
label | Ref docs - VR713.03
label | Acceptance criteria - Type 2 Beaching material shall be:
label | • Field or quarry rock >50mm diameter and of mass 10-40kg with at least 60% of Qty greater than 25kg.
label | • Placed that the length of rock protection >100mm and the total layer thickness is >150mm.
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
label | Remarks/record - Import Docket
checkpoint | 1.5 - Beaching Material - Type 5
label | Ref docs - VR713.03
label | Acceptance criteria - Type 5 Beaching material shall be:
label | • Design accepted by Melbourne Water and record of acceptance provided for superintendent approval.
label | • Field or quarry rock >50mm diameter, angular in shape, and 5% mass of rock fines for interlocking.
label | • Unless specified, the minimum d50 shall be 300mm rock sizing of depth 2 x d50 (600mm). the minimum d50 shall be 300mm rock sizing of depth 2 x d50 (600mm).
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record - Import Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Beaching Placement OHS
label | Ref docs - VR713.05
label | Acceptance criteria - A completed job safety assessment and SWMS shall be submitted to Superintendent for review.
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record - SWMS
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Construction
checkpoint | 2.1 - Geotextile Placement
label | Ref docs - VR210.05(a)
label | Acceptance criteria - Geotextile is not to be placed without written superintendent approval.
label | • Geotextile placed shall be without punctures or tears and rolls with imperfections shall not be used.
label | • Covered with fill material within 48Hr of placement.
label | Freq - Each lot
label | Key - H
label | Resp - SE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Bedding and Geotextiles - Type 1
label | Ref docs - VR713.03(b) VR210
label | Acceptance criteria - Type 1 Beaching Material shall be placed on non-woven geotextile >250g/m2, laid with no kinks or folds.
label | • Geotextile shall be buried 300mm below beaching edges and placed under and around excavation for toe wall and other perimeter walls.
label | • Geotextiles are joined with 300-500mm overlap.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 2.3 - Bedding and Geotextiles - Type 2
label | Ref docs - VR713.03(b)
label | Acceptance criteria - Type 2 Beaching material shall not require bedding unless specified or in design.
label | Freq - Each Lot
label | Key - I
label | Resp - SE
checkpoint | 2.4 - Bedding and Geotextiles - Type 5
label | Ref docs - VR713.03(b) MWC 7251/08/103
label | Acceptance criteria - Type 5 Beaching Bedding shall be:
label | • Developed in conjunction with Melbourne Water.
label | • Well graded, and 0-100mm size for granular bedding.
label | • Granular filter thickness >100mm.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 2.5 - Preparation of underlying surface
label | Ref docs - VR713.04 VR210
label | Acceptance criteria - Beaching placement surface shall be:
label | • Excavated, compacted, and trimmed to provide a FSL of beaching in accordance with IFC design.
label | • Any scours or hollows backfilled with class 4.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 2.6 - Placing Rock Beaching – All Types
label | Ref docs - VR713.05
label | Acceptance criteria - All Beaching shall be placed such that:
label | • There is no beaching protrusion >50mm above surrounding ground levels.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 2.7 - Placing Rock Beaching – Type 1
label | Ref docs - VR713.05
label | Acceptance criteria - Type 1 Beaching shall be placed such that:
label | • A tight ‘interlocking grid’ is formed to retain each rock with gaps <60mm on average.
label | • There is not >100mm height variation along a 3m straight line along the finish surface.
label | • Voids filled mid-height of rock with topsoil.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 2.8 - Placing Rock Beaching – Type 2
label | Ref docs - VR713.05 VR13.06
label | Acceptance criteria - Type 2 Beaching shall be placed such that:
label | • An initial bed of mortar infiltrates the joints VR13.06.
label | • Width of joints vary are between 10-60mm, and not exceeding 40mm on average.
label | • There is not >75mm height variation along a 3m straight line along the finish surface.
label | • Joints are free from debris before grouting.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 2.9 - Placing Rock Beaching – Type 5
label | Ref docs - VR713.05
label | Acceptance criteria - Type 5 Beaching shall be placed such that:
label | • There is not >75mm height variation along a 3m straight line along the finish surface.
label | • Rocks are tightly interlocked, and voids are sealed with smaller rock for stability and sufficient water flow.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 2.10 - Grouting – Type 2
label | Ref docs - VR713.06
label | Acceptance criteria - Type 2 Beaching grouting shall be:
label | • With mortar one part Portland and 3 parts Sand by volume and thoroughly mixed with water.
label | • When air temperature >5°C and kept moist for 3 days.
label | • Such that joints are neatly finished and final mortar shall not be within 10mm of finished rock surface.
label | • Final grouting ensures mortar is firmly tamped into joints to fill the joints 20mm below general top of beaching.
label | Freq - Each lot
label | Key - I
label | Resp - SE
label | Remarks/record - Mortar Mix Product Detail
label | • Grout Product Detail
checkpoint | 2.11 - Toe Walls – Type 1
label | Ref docs - VR713.07 IFC design
label | Acceptance criteria - Type 1 Beaching Toe Walls shall be:
label | • Constructed where rock beaching slope >1:5 and be 600mm wide x 600mm deep.
label | • Constructed 300mm wide x 400mm deep at front face and reinforced with L8TM trench mesh top and bottom.
label | • Lined with geotextiles and filled with hand packed rock with larger voids filled with smaller stones.
label | Freq - Each lot
label | Key - I
label | Resp - SE
label | Remarks/record - Dockets
checkpoint | 2.12 - Perimeter Walls – Type 2
label | Ref docs - VR713.07 VR703.11
label | Acceptance criteria - Type 2 Beaching Concrete Perimeter Walls shall be:
label | • Constructed around exposed edges of beaching.
label | • N20 strength grade.
label | Freq - Each lot
label | Key - I
label | Resp - SE
label | Remarks/record - Dockets
checkpoint | 2.13 - Drainage
label | Ref docs - VR713.08 IFC design
label | Acceptance criteria - Where specified or shown on the design shall be:
label | • 100mm diameter PVC pipe laid down the batter in a trench beneath the bedding to discharge immediately above the top of the toe wall.
label | • The pipe securely bedded within the backfilled compacted crushed rock or natural gravel trench.
label | • Weepholes consisting of 75 mm diameter PVC pipes placed through the beaching at 2 m centres immediately above the top of the concrete toe wall and cut off flush with the face of beaching.
label | Freq - Each lot
label | Key - I
label | Resp - SE
section | 3.0 Completion
checkpoint | 3.1 - Cleaning
label | Ref docs - VR713.09
label | Acceptance criteria - Post-completion, beaching shall be cleaned, and foreign material and discolouration removed from surface.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 3.2 - Conformity with drawings
label | Ref docs - VR713.02
label | Acceptance criteria - Beaching finished surface conforms to the levels, lines, and grades as shown in IFC design or specified.
label | • As-built survey completed.
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record - As-built Survey
section | 4.0 Work Lot Close out
checkpoint | 4.1 - Product Non-Conformance
label | Ref docs - CQMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record -
text | • NCR No
checkpoint | 4.2 - Quality Representative to check the above criteria and records to confirm
label | Ref docs - CQMP Lot Records
label | Acceptance criteria - All above criteria met, and records identified attached.
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP