## res_1630-P200-SYM-QAC-ITP-0013.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0049 Fill Earthworks Type C | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0049 Fill Earthworks Type C
section | 1.0 Pre-start activities
checkpoint | 1.1 - Define Work Lot
label | Ref docs - 173.02 204.03 (h) Table 204.142 Lot Diagram
label | Acceptance criteria - Survey boundaries clearly define the Earthworks Type C Construction works.
label | • Lot diagram to be provided clearly marking up extents of lot area.
label | • Work Lot open on TeamBinder.
label | • Lot size with no more than one day’s production
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map | Yes,No,N/A
checkpoint-no-status | 1.1.2 - Environmental Permit
button | Environmental permit | Yes,No,N/A
section | 2.0 Set Out
checkpoint | 2.1 - Set Out Survey Completed
label | Ref docs - VR Clause 204.03 (a) IFC Drawings
label | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
section | 3.0 Placement of Type C Material
checkpoint | 3.1 - Underlying Layer Conformance
label | Ref docs - VR Clause 204.10(b) Construction Document
label | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
button | Approval to proceed granted? | Yes,No
label | Freq - Each Lot
label | Key - H W
label | Resp - SE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Placing of Fill
label | Ref docs - VR Clause 204.10(d)
label | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 300 mm.
label | • Where Type C material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 300 mm thick layer, the loose thickness of each layer may equal the maximum particle dimension of the rock up to a maximum layer thickness of 500 mm.
label | • Rocks with a maximum particle dimension of less than 800 mm may be placed in Type C material zones as specified, with sufficient spacing between larger rocks to enable full compaction of the Type C material.
label | • The material shall be placed and compacted such that voids are completely filled with fine material.
label | • Material shall be compacted at minimum moisture ratio of 80%
label | Freq - Once Each Lot
label | Key - W
label | Resp - SE
label | Remarks/record -
button | • Verification Records: | Yes,No
button | • Material Compliance Certificates & Material Approval Register | Yes,No
button | • VicRoads registration of recycled material blend (if applicable) | Yes,No
checkpoint | 3.3 - Keyed Fill Layers
label | Ref docs - VR Clause 204.10(c) 204.10(d) Construction Document
label | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
label | • Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill.
label | • The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
label | Freq - Once Each Lot
label | Key - W
label | Resp - SE
section | 4.0 Geotechnical Analysis
checkpoint | 4.1 - Compaction Testing / Moisture Testing
label | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) Table PS3020.072
label | Acceptance criteria - All areas of the job will be considered as scale A.
label | ○ Scale A Testing: HWKR Rd, Princes Freeway, All Freeway Interchange Ramps, All other arterial roads.
label | ○ Scale B Testing: All other local roads, SUP.
label | ○ Type C Material should meet the following compaction:
label | • 95% for Scale A
label | • 93% for Scale B
label | • 92% for Scale C
label | ○ Type C material is to be tested as per table 201.141 and table 201.142. And should meet the moisture content requirements as per VR204.
label | ○ >70% for any material within 150mm of subgrade.
label | ○ >80% for all material below cut floor level.
button | Have the results been achieved? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record -
button | • NATA Test Report: Compaction | Yes,No
checkpoint | 4.2 - Material Requirements
label | Ref docs - VR Clause Table 204.041
label | Acceptance criteria - Type C material shall be capable of being spread in layers of not more than 500 mm and compacted as specified to achieve a stable condition.
button | Have the results been achieved? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.3 - Reduced Frequency Post compaction testing of initial lots.
label | Ref docs - VR Clause 204.14 Table 204.142 PS3020.07 (f)
label | Acceptance criteria - Testing of compaction for each lot as per Table 204.142
label | • If Reduced frequency has been granted, the testing can be conducted at the following frequency:
label | • Compaction will only be required for every 6th lot.
button | Has the criteria been achieved? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | SI Key - R
section | 5.0 Completion
checkpoint | 5.1 - Conformity with IFC Drawings and Construction Tolerances
label | Ref docs - VR Clause 204.03 Table 204.031
label | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings.
button | Does the final product conform to the above criterial? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
label | Ref docs - VR Clause 204.15
label | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
label | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
button | Does the final product conform to the above criterial? | Yes,No
label | Freq - Each Lot
label | Key - R
label | Resp - SE
section | 6.0 Work Lot Close Out
checkpoint | 6.1 - Test Reports
label | Ref docs - DoT Specs
label | Acceptance criteria - All Test reports received and reviewed
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record - NATA Endorsed Test Reports
checkpoint | 6.2 - Product Non-Conformance
label | Ref docs - QMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record - NCR reports
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP